## Dashboard
Total Tickets |  |  | % Complete |  |  | Active Blockers | Sprints At Risk
60 |  |  | 41.7% |  |  | 9 | 1 — Sprint 14
Squad Health Radar — Sprint 14
Squad | Velocity | On-Time | BlockerRes | Completion | Health
Cloud Engineering | 1 | 1 | 1 | 1 | 0
DevOps & Automation | 0 | 0.88889 | 0.5 | 0 | 0
Cloud Architecture | 0 | 1 | 0.5 | 0 | 0
Security & Compliance | 0 | 0.88889 | 0 | 0 | 0
Sprint Scorecard
Sprint | Overall Completion % | Blocker Count | Health RAG
Sprint 12 | 75% | 2 | Amber
Sprint 13 | 45% | 3 | Red
Sprint 14 | 5% | 4 | Red
Risk Log
Ticket ID | Summary | Squad | Sprint | Priority | Blocker Reason
CL-318 | Provision cloud landing zone for Security & Compliance workl | Cloud Engineering | Sprint 12 | Critical | Cloud environment provisioning delayed — vendor procurement approval pending
CL-319 | Complete InfoSec review for cloud platform security baseline | Security & Compliance | Sprint 12 | Critical | Security policy review not completed — Cloud Security team sign-off outstanding
CL-334 | Configure cloud-to-on-prem connectivity for legacy migration | Cloud Architecture | Sprint 13 | Critical | Migration dependency blocked — legacy API decommission not approved by Platform team
CL-335 | Automate compliance evidence collection for InfoSec audit | Security & Compliance | Sprint 13 | Critical | Compliance sign-off pending — InfoSec review backlog exceeding SLA
CL-336 | Build enterprise key vault integration for cloud workloads | Security & Compliance | Sprint 13 | Medium | CI/CD pipeline dependency unresolved — third-party integration token expired
CL-350 | Configure automated FinOps reporting pipeline for cloud spen | DevOps & Automation | Sprint 14 | Critical | Cloud cost governance approval pending — FinOps board decision awaited
CL-351 | Integrate cloud security scanning into delivery pipeline | Cloud Architecture | Sprint 14 | High | IAM policy conflict unresolved — Identity team escalation raised
CL-352 | Deploy cloud-native identity governance framework | Security & Compliance | Sprint 14 | Critical | Architecture Decision Record awaiting Cloud Architecture Board and CTO approval
CL-353 | Implement enterprise data governance for cloud data platform | Security & Compliance | Sprint 14 | High | Compliance sign-off pending — InfoSec review backlog exceeding SLA
Sprint 14 Ceremony Insights — Technical Lead Escalations
Ceremony | Date | Key Decisions / Actions | Risks Raised | Status
Sprint Planning | 46111 | 20 tickets committed; team flagged resource risk — Arjun supporting external InfoSec audit week 2. Project Manager raised concern on accumulating blocker debt. | 20 tickets committed; team flagged resource risk — Arjun supporting external InfoSec audit week 2. Project Manager raised concern on accumulating blocker debt. | Escalated
Daily Standup Summary (Week 1) | 46115 | 6 tickets blocked — highest blocker count across 3 sprints. Project Manager called emergency triage with all squad leads and Head of Cloud Delivery. | 6 tickets blocked — highest blocker count across 3 sprints. Project Manager called emergency triage with all squad leads and Head of Cloud Delivery. | Escalated
Mid-Sprint Review | 46118 | Only 1 ticket done at midpoint; Project Manager escalated to CTO and CISO — sprint at critical risk, cloud platform delivery deadline in jeopardy. | Only 1 ticket done at midpoint; Project Manager escalated to CTO and CISO — sprint at critical risk, cloud platform delivery deadline in jeopardy. | Escalated
Sprint Review | 46122 | Sprint still in progress — formal review scheduled 10 April. Project Manager preparing risk summary and remediation plan for Head of Cloud Delivery. | Sprint still in progress — formal review scheduled 10 April. Project Manager preparing risk summary and remediation plan for Head of Cloud Delivery. | Escalated

## Sprint Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
CL-301 | Migrate primary workload cluster to AWS landing zone | Done | Critical | Aisha | Cloud Engineering | Sprint 12 | Cloud Infra Migration | 13 | 13 | 2026-03-06 | 2026-03-08 | 2026-03-05 | 2026-03-11 | Yes |  |  | 1
CL-302 | Design multi-region failover architecture for core platform | Done | High | Rohan | Cloud Engineering | Sprint 12 | Cloud Architecture Review | 8 | 8 | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-03-05 | Yes |  |  | 1
CL-303 | Build Terraform IaC module for VPC and subnet provisioning | Done | High | Priti | DevOps & Automation | Sprint 12 | Platform Engineering | 8 | 8 | 2026-03-09 | 2026-03-12 | 2026-03-08 | 2026-03-11 | No |  |  | 2
CL-304 | Implement RBAC policies for cloud identity platform | Done | High | Nadia | Security & Compliance | Sprint 12 | Identity & Access | 5 | 5 | 2026-03-03 | 2026-03-04 | 2026-03-04 | 2026-03-04 | No |  |  | 1
CL-305 | Deploy centralised log aggregation pipeline to Splunk | Done | Medium | Arjun | Security & Compliance | Sprint 12 | Observability & Monitoring | 8 | 8 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-11 | Yes |  |  | 1
CL-306 | Architect disaster recovery runbook for Tier-1 cloud workloads | Done | Medium | Leela | Cloud Architecture | Sprint 12 | Disaster Recovery | 5 | 5 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-09 | Yes |  |  | 1
CL-307 | Configure auto-scaling policies for DevOps toolchain | Done | High | Vikram | DevOps & Automation | Sprint 12 | CI/CD Pipeline Automation | 5 | 5 | 2026-03-03 | 2026-03-08 | 2026-03-03 | 2026-03-07 | No |  |  | 1
CL-308 | Build cloud cost tagging framework for FinOps reporting | Done | High | Rohan | Cloud Engineering | Sprint 12 | Cost Optimisation | 8 | 8 | 2026-03-02 | 2026-03-04 | 2026-03-03 | 2026-03-05 | Yes |  |  | 1
CL-309 | Design security posture baseline for cloud workloads | Done | Medium | Nadia | Security & Compliance | Sprint 12 | Security Posture Hardening | 5 | 5 | 2026-03-09 | 2026-03-13 | 2026-03-11 | 2026-03-12 | No |  | CL-304 | 2
CL-310 | Deploy vendor-managed firewall across cloud DMZ | Done | Medium | Sanjay | Cloud Architecture | Sprint 12 | Vendor Management | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-11 | 2026-03-15 | Yes |  |  | 2
CL-311 | Build observability dashboard for platform SLA monitoring | Done | Critical | Arjun | Security & Compliance | Sprint 12 | Observability & Monitoring | 3 | 3 | 2026-03-10 | 2026-03-12 | 2026-03-11 | 2026-03-10 | No |  | CL-305 | 2
CL-312 | Automate certificate rotation for all cloud endpoints | Done | Medium | Priti | DevOps & Automation | Sprint 12 | Security Posture Hardening | 8 | 8 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-14 | Yes |  |  | 2
CL-313 | Architect cloud-native DR solution for database tier | Done | High | Leela | Cloud Architecture | Sprint 12 | Disaster Recovery | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-10 | 2026-03-13 | No |  |  | 2
CL-314 | Design FinOps cost anomaly alerting model | Done | High | Vikram | DevOps & Automation | Sprint 12 | Cost Optimisation | 5 | 5 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-10 | No |  |  | 2
CL-315 | Configure cloud platform API gateway for internal services | Done | High | Sanjay | Cloud Architecture | Sprint 12 | Platform Engineering | 3 | 3 | 2026-03-08 | 2026-03-13 | 2026-03-10 | 2026-03-13 | Yes |  |  | 1
CL-316 | Build GitOps deployment pipeline for microservices platform | In Progress | High | Priti | DevOps & Automation | Sprint 12 | CI/CD Pipeline Automation | 2 | 2 | 2026-03-11 | 2026-03-13 | 2026-03-11 |  | Yes |  |  | 2
CL-317 | Design cloud networking blueprint for hybrid connectivity | In Progress | High | Aisha | Cloud Engineering | Sprint 12 | Cloud Architecture Review | 2 | 2 | 2026-03-08 | 2026-03-13 | 2026-03-10 |  | Yes |  |  | 1
CL-318 | Provision cloud landing zone for Security & Compliance workloads | Blocked | Critical | Rohan | Cloud Engineering | Sprint 12 | Cloud Infra Migration | 5 | 5 | 2026-03-05 | 2026-03-10 | 2026-03-04 |  | Yes | Cloud environment provisioning delayed — vendor procurement approval pending |  | 1
CL-319 | Complete InfoSec review for cloud platform security baseline | Blocked | Critical | Nadia | Security & Compliance | Sprint 12 | Security Posture Hardening | 3 | 3 | 2026-03-08 | 2026-03-11 | 2026-03-10 |  | Yes | Security policy review not completed — Cloud Security team sign-off outstanding |  | 2
CL-320 | Design data residency architecture for regulated workloads | To Do | Medium | Leela | Cloud Architecture | Sprint 12 | Cloud Architecture Review | 5 | 5 | 2026-03-12 | 2026-03-14 |  |  | No |  |  | 2
CL-321 | Complete cloud infra migration for secondary application tier | Done | Critical | Aisha | Cloud Engineering | Sprint 13 | Cloud Infra Migration | 5 | 5 | 2026-03-19 | 2026-03-21 | 2026-03-19 | 2026-03-22 | Yes |  | CL-318 | 3
CL-322 | Deliver CI/CD pipeline for automated regression testing | Done | Low | Rohan | Cloud Engineering | Sprint 13 | CI/CD Pipeline Automation | 3 | 3 | 2026-03-16 | 2026-03-21 | 2026-03-16 | 2026-03-20 | No |  | CL-308 | 3
CL-323 | Build cloud security incident response playbook | Done | High | Nadia | Security & Compliance | Sprint 13 | Security Posture Hardening | 8 | 8 | 2026-03-19 | 2026-03-22 | 2026-03-18 | 2026-03-21 | No |  |  | 3
CL-324 | Implement cloud-native secrets management solution | Done | High | Arjun | Security & Compliance | Sprint 13 | Identity & Access | 5 | 5 | 2026-03-16 | 2026-03-19 | 2026-03-16 | 2026-03-20 | No |  |  | 3
CL-325 | Deploy SLO-based alerting for platform engineering team | Done | Medium | Vikram | DevOps & Automation | Sprint 13 | Observability & Monitoring | 8 | 8 | 2026-03-22 | 2026-03-25 | 2026-03-21 | 2026-03-24 | No |  |  | 4
CL-326 | Design vendor management framework for cloud suppliers | Done | Medium | Sanjay | Cloud Architecture | Sprint 13 | Vendor Management | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-20 | 2026-03-22 | No |  |  | 3
CL-327 | Build FinOps optimisation report for cloud spend by squad | Done | High | Leela | Cloud Architecture | Sprint 13 | Cost Optimisation | 8 | 8 | 2026-03-19 | 2026-03-23 | 2026-03-20 | 2026-03-22 | No |  | CL-310 | 4
CL-328 | Architect cloud DR test plan for Tier-1 application failover | Done | Critical | Priti | DevOps & Automation | Sprint 13 | Disaster Recovery | 8 | 8 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-26 | Yes |  |  | 4
CL-329 | Map data flow architecture for cloud platform migration | In Progress | High | Aisha | Cloud Engineering | Sprint 13 | Cloud Infra Migration | 5 | 5 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
CL-330 | Architect real-time SLA monitoring for cloud engineering squad | In Progress | Low | Rohan | Cloud Engineering | Sprint 13 | Observability & Monitoring | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-18 |  | Yes |  |  | 3
CL-331 | Define cloud platform architecture for regulatory sandbox env | In Progress | Medium | Sanjay | Cloud Architecture | Sprint 13 | Cloud Architecture Review | 8 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
CL-332 | Tune automated cost anomaly detection model for FinOps | In Progress | Critical | Vikram | DevOps & Automation | Sprint 13 | Cost Optimisation | 5 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
CL-333 | Build platform engineering baseline for cloud delivery squads | Done | Medium | Leela | Cloud Architecture | Sprint 13 | Platform Engineering | 8 | 8 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-26 | Yes |  |  | 4
CL-334 | Configure cloud-to-on-prem connectivity for legacy migration | Blocked | Critical | Sanjay | Cloud Architecture | Sprint 13 | Cloud Infra Migration | 5 | 5 | 2026-03-22 | 2026-03-23 | 2026-03-23 |  | Yes | Migration dependency blocked — legacy API decommission not approved by Platform team | CL-320 | 3
CL-335 | Automate compliance evidence collection for InfoSec audit | Blocked | Critical | Arjun | Security & Compliance | Sprint 13 | Security Posture Hardening | 3 | 3 | 2026-03-22 | 2026-03-23 | 2026-03-22 |  | Yes | Compliance sign-off pending — InfoSec review backlog exceeding SLA |  | 3
CL-336 | Build enterprise key vault integration for cloud workloads | Blocked | Medium | Nadia | Security & Compliance | Sprint 13 | Identity & Access | 3 | 3 | 2026-03-19 | 2026-03-22 | 2026-03-21 |  | Yes | CI/CD pipeline dependency unresolved — third-party integration token expired |  | 3
CL-337 | Review cloud architecture design for platform engineering | Supervisor Review | High | Aisha | Cloud Engineering | Sprint 13 | Cloud Architecture Review | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
CL-338 | Validate cloud DR architecture for Tier-1 application | Supervisor Review | High | Rohan | Cloud Engineering | Sprint 13 | Disaster Recovery | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 4
CL-339 | Review security posture architecture for InfoSec submission | Supervisor Review | Medium | Priti | DevOps & Automation | Sprint 13 | Security Posture Hardening | 5 | 5 | 2026-03-22 | 2026-03-24 | 2026-03-22 |  | Yes |  |  | 4
CL-340 | Validate FinOps governance framework for cloud cost control | Supervisor Review | High | Vikram | DevOps & Automation | Sprint 13 | Cost Optimisation | 5 | 5 | 2026-03-22 | 2026-03-25 | 2026-03-22 |  | Yes |  |  | 4
CL-341 | Complete cloud infra migration for platform engineering workloads | Done | Critical | Aisha | Cloud Engineering | Sprint 14 | Cloud Infra Migration | 8 | 8 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-04-02 | Yes |  | CL-337 | 5
CL-342 | Architect microservice containerisation for DevOps toolchain | In Progress | High | Rohan | Cloud Engineering | Sprint 14 | Platform Engineering | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  | CL-341 | 5
CL-343 | Build cloud cost governance dashboard for FinOps review | In Progress | Medium | Leela | Cloud Architecture | Sprint 14 | Cost Optimisation | 8 | 8 | 2026-03-30 | 2026-04-02 | 2026-03-30 |  | Yes |  |  | 5
CL-344 | Integrate platform engineering CI/CD with cloud security scanning | In Progress | High | Priti | DevOps & Automation | Sprint 14 | CI/CD Pipeline Automation | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
CL-345 | Build SLO alerting dashboard for cloud observability platform | In Progress | Medium | Sanjay | Cloud Architecture | Sprint 14 | Observability & Monitoring | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
CL-346 | Design NPS data pipeline for cloud services customer analytics | In Progress | Low | Aisha | Cloud Engineering | Sprint 14 | Platform Engineering | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CL-347 | Architect ML-based anomaly detection for cloud security platform | In Progress | Critical | Rohan | Cloud Engineering | Sprint 14 | Security Posture Hardening | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CL-348 | Build cloud infrastructure monitoring dashboard for squads | In Progress | High | Vikram | DevOps & Automation | Sprint 14 | Observability & Monitoring | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CL-349 | Design microservice architecture for cloud platform upgrade | In Progress | Critical | Sanjay | Cloud Architecture | Sprint 14 | Cloud Architecture Review | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CL-350 | Configure automated FinOps reporting pipeline for cloud spend | Blocked | Critical | Vikram | DevOps & Automation | Sprint 14 | Cost Optimisation | 8 | 8 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | Cloud cost governance approval pending — FinOps board decision awaited | CL-335 | 5
CL-351 | Integrate cloud security scanning into delivery pipeline | Blocked | High | Leela | Cloud Architecture | Sprint 14 | Security Posture Hardening | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | IAM policy conflict unresolved — Identity team escalation raised |  | 5
CL-352 | Deploy cloud-native identity governance framework | Blocked | Critical | Arjun | Security & Compliance | Sprint 14 | Identity & Access | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Architecture Decision Record awaiting Cloud Architecture Board and CTO approval |  | 6
CL-353 | Implement enterprise data governance for cloud data platform | Blocked | High | Nadia | Security & Compliance | Sprint 14 | Security Posture Hardening | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Compliance sign-off pending — InfoSec review backlog exceeding SLA |  | 6
CL-354 | Review cloud platform solution architecture for CTO sign-off | Supervisor Review | High | Priti | DevOps & Automation | Sprint 14 | Cloud Architecture Review | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
CL-355 | Validate cloud DR architecture for business continuity review | Supervisor Review | High | Aisha | Cloud Engineering | Sprint 14 | Disaster Recovery | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CL-356 | Review API security architecture for cloud platform rollout | Supervisor Review | Medium | Rohan | Cloud Engineering | Sprint 14 | Platform Engineering | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CL-357 | Design DR strategy for cloud platform and on-prem hybrid | In Progress | High | Leela | Cloud Architecture | Sprint 14 | Disaster Recovery | 5 | 5 | 2026-04-06 | 2026-04-10 | 2026-04-06 |  | Yes |  |  | 6
CL-358 | Build data lineage map for cloud compliance submissions | To Do | Medium | Arjun | Security & Compliance | Sprint 14 | Security Posture Hardening | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
CL-359 | Architect event streaming platform for cloud analytics | To Do | High | Nadia | Security & Compliance | Sprint 14 | Observability & Monitoring | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
CL-360 | Complete vendor management framework for cloud suppliers | To Do | Medium | Sanjay | Cloud Architecture | Sprint 14 | Vendor Management | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
Facilitator note: Sprint 12 = Done 15, InProg 2, Blocked 2, ToDo 1 (healthy — 84.7% completion, Green). Sprint 13 = Done 9, InProg 4, Blocked 3, SupRev 4 (mixed — 52.3%, Amber; CL-333 Done). Sprint 14 = Done 1, InProg 8, Blocked 4, SupRev 3, ToDo 4 (at-risk — 7.3%, Red). Status totals: Done=25, InProg=15, Blocked=9, SupRev=7, ToDo=4 (=60). Amber-highlighted rows are Blocked tickets. Blocker Resistance in radar chart MUST be inverted — fewer blockers = higher score.

## Squad Targets
Squad | Sprint | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
Cloud Engineering | Sprint 12 | 30 | 85 | 3
Cloud Engineering | Sprint 13 | 28 | 80 | 3
Cloud Engineering | Sprint 14 | 32 | 80 | 3
DevOps & Automation | Sprint 12 | 27 | 90 | 3
DevOps & Automation | Sprint 13 | 24 | 90 | 2
DevOps & Automation | Sprint 14 | 30 | 90 | 2
Cloud Architecture | Sprint 12 | 28 | 80 | 3
Cloud Architecture | Sprint 13 | 26 | 80 | 2
Cloud Architecture | Sprint 14 | 32 | 80 | 2
Security & Compliance | Sprint 12 | 28 | 90 | 2
Security & Compliance | Sprint 13 | 24 | 85 | 2
Security & Compliance | Sprint 14 | 30 | 90 | 2
Facilitator note: Squad Targets feed the Radar Chart for Level 3. Planned Velocity provides the velocity denominator per squad. On-Time Target % is the benchmark. Max Blockers Allowed is the inversion upper bound for Blocker Resistance. Sprint 14 targets are highest but performance is worst — the coaching moment for a Project Manager audience.

## Sprint Ceremonies
Sprint | Ceremony | Date | Key Decisions / Notes
Sprint 12 | Sprint Planning | 2026-03-02 | 20 tickets committed; 2 cloud architecture designs carried over from previous delivery cycle. Project Manager confirmed scope freeze for cloud infra migration workstream.
Sprint 12 | Daily Standup Summary (Week 1) | 2026-03-06 | Cloud Engineering blocker on provisioning — Project Manager escalated to Vendor Account Manager for expedited approval decision.
Sprint 12 | Mid-Sprint Review | 2026-03-09 | 3 cloud architecture tickets re-estimated upward after complexity assessment; Security & Compliance flagged InfoSec review backlog impacting CL-319.
Sprint 12 | Sprint Review | 2026-03-13 | 15 of 20 tickets done; 2 blocked (CL-318, CL-319); 1 carried to Sprint 13. Project Manager signed off sprint delivery report.
Sprint 12 | Retrospective | 2026-03-13 | Action: improve cross-squad dependency tracking; Project Manager to add blocker escalation column to sprint tracker and review weekly.
Sprint 13 | Sprint Planning | 2026-03-16 | 20 tickets committed including 1 carryover; 1 new P1 compliance item added mid-week. Project Manager flagged capacity risk — one squad lead supporting InfoSec audit.
Sprint 13 | Daily Standup Summary (Week 1) | 2026-03-20 | Cloud Architecture ahead on cost optimisation work; Security & Compliance blocked on compliance evidence collection. Project Manager reviewing blocker SLA.
Sprint 13 | Mid-Sprint Review | 2026-03-23 | InfoSec team requested 2 additional security hardening tickets mid-sprint. Project Manager flagged scope risk — deferred pending Change Control approval.
Sprint 13 | Sprint Review | 2026-03-27 | 14 of 20 tickets done; velocity dip vs Sprint 12; 4 tickets in Supervisor Review. Project Manager escalated 3 blocked tickets to Head of Cloud Delivery and CISO.
Sprint 13 | Retrospective | 2026-03-27 | Action: no mid-sprint scope additions without Project Manager approval; blocker SLA set at 24 hours with daily check-in to Head of Cloud Delivery.
Sprint 14 | Sprint Planning | 2026-03-30 | 20 tickets committed; team flagged resource risk — Arjun supporting external InfoSec audit week 2. Project Manager raised concern on accumulating blocker debt.
Sprint 14 | Daily Standup Summary (Week 1) | 2026-04-03 | 6 tickets blocked — highest blocker count across 3 sprints. Project Manager called emergency triage with all squad leads and Head of Cloud Delivery.
Sprint 14 | Mid-Sprint Review | 2026-04-06 | Only 1 ticket done at midpoint; Project Manager escalated to CTO and CISO — sprint at critical risk, cloud platform delivery deadline in jeopardy.
Sprint 14 | Sprint Review | 2026-04-10 | Sprint still in progress — formal review scheduled 10 April. Project Manager preparing risk summary and remediation plan for Head of Cloud Delivery.
Facilitator note: Sprint 14 rows are amber-highlighted — these are the rows the Level 3 Ceremony Insights section must pull. All escalations reference the Project Manager, not PM or Tech Lead. The Sprint 14 Mid-Sprint Review row ('Only 1 ticket done at midpoint') is the key coaching moment. Any output referencing 'PM' as an abbreviation indicates the agent did not read the actual sheet data.