## Sprint Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
DM-301 | Define programme governance framework for banking transformation | Done | Critical | Kavya | Programme Delivery | Sprint 12 | Programme Governance | 13 | 13 | 2026-03-06 | 2026-03-08 | 2026-03-05 | 2026-03-11 | Yes |  |  | 1
DM-302 | Deliver change impact assessment for payments modernisation | Done | High | Rajan | Programme Delivery | Sprint 12 | Change Delivery | 8 | 8 | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-03-05 | Yes |  |  | 1
DM-303 | Build client MI reporting pack for quarterly review | Done | Low | Sonia | Change Management | Sprint 12 | Portfolio MI | 8 | 8 | 2026-03-09 | 2026-03-12 | 2026-03-08 | 2026-03-11 | No |  |  | 2
DM-304 | Implement risk register for regulatory remediation programme | Done | High | Pooja | Risk Governance | Sprint 12 | Risk Reporting | 5 | 5 | 2026-03-03 | 2026-03-04 | 2026-03-04 | 2026-03-04 | No |  |  | 1
DM-305 | Design client onboarding journey for private banking upgrade | Done | Medium | Deepa | Client Services | Sprint 12 | Client Onboarding | 8 | 8 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-11 | Yes |  |  | 1
DM-306 | Build resource capacity plan for Q2 programme delivery | Done | Medium | Vivek | Client Services | Sprint 12 | Resource Planning | 5 | 5 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-09 | Yes |  |  | 1
DM-307 | Define SLA management framework for operations team | Done | High | Kavya | Programme Delivery | Sprint 12 | SLA Management | 5 | 5 | 2026-03-03 | 2026-03-08 | 2026-03-03 | 2026-03-07 | No |  |  | 1
DM-308 | Draft regulatory compliance roadmap for FCA Consumer Duty | Done | High | Rajan | Programme Delivery | Sprint 12 | Regulatory Compliance | 8 | 8 | 2026-03-02 | 2026-03-04 | 2026-03-03 | 2026-03-05 | Yes |  | DM-302 | 1
DM-309 | Deliver stakeholder engagement plan for CBS migration | Done | Medium | Arun | Change Management | Sprint 12 | Stakeholder Engagement | 5 | 5 | 2026-03-09 | 2026-03-13 | 2026-03-11 | 2026-03-12 | No |  | DM-304 | 2
DM-310 | Build benefits realisation tracker for digital programme | Done | Medium | Sonia | Change Management | Sprint 12 | Benefits Realisation | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-11 | 2026-03-15 | Yes |  |  | 2
DM-311 | Deliver PRA regulatory reporting update to risk committee | Done | Critical | Arun | Change Management | Sprint 12 | Regulatory Compliance | 3 | 3 | 2026-03-10 | 2026-03-12 | 2026-03-11 | 2026-03-10 | No |  | DM-303 | 2
DM-312 | Complete resource onboarding for risk governance workstream | Done | Medium | Nitin | Risk Governance | Sprint 12 | Resource Planning | 8 | 8 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-14 | Yes |  |  | 2
DM-313 | Design multi-site delivery model for compliance programme | Done | High | Pooja | Risk Governance | Sprint 12 | Programme Governance | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-10 | 2026-03-13 | No |  |  | 2
DM-314 | Build SLA breach dashboard for client services team | Done | High | Vivek | Client Services | Sprint 12 | SLA Management | 5 | 5 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-10 | No |  |  | 2
DM-315 | Deliver change readiness assessment for digital channels | Done | High | Deepa | Client Services | Sprint 12 | Change Delivery | 3 | 3 | 2026-03-08 | 2026-03-13 | 2026-03-10 | 2026-03-13 | Yes |  |  | 1
DM-316 | Build portfolio MI framework for programme directors | In Progress | High | Nitin | Risk Governance | Sprint 12 | Portfolio MI | 2 | 2 | 2026-03-11 | 2026-03-13 | 2026-03-11 |  | Yes |  |  | 2
DM-317 | Design benefits realisation model for payments programme | In Progress | High | Kavya | Programme Delivery | Sprint 12 | Benefits Realisation | 2 | 2 | 2026-03-08 | 2026-03-13 | 2026-03-10 |  | Yes |  |  | 1
DM-318 | Deliver client onboarding pack for wholesale banking upgrade | Blocked | Critical | Rajan | Programme Delivery | Sprint 12 | Client Onboarding | 5 | 5 | 2026-03-05 | 2026-03-10 | 2026-03-04 |  | Yes | Client sign-off delayed — awaiting contracting team review |  | 1
DM-319 | Submit regulatory compliance evidence to PRA portal | Blocked | Critical | Sonia | Change Management | Sprint 12 | Regulatory Compliance | 3 | 3 | 2026-03-08 | 2026-03-11 | 2026-03-10 |  | Yes | FCA regulatory freeze — no change deployments permitted |  | 2
DM-320 | Design programme closure framework for legacy replacement | To Do | Medium | Arun | Change Management | Sprint 12 | Programme Governance | 5 | 5 | 2026-03-12 | 2026-03-14 |  |  | No |  |  | 2
DM-321 | Complete programme governance review for transformation | Done | Critical | Kavya | Programme Delivery | Sprint 13 | Programme Governance | 5 | 5 | 2026-03-19 | 2026-03-21 | 2026-03-19 | 2026-03-22 | Yes |  | DM-318 | 3
DM-322 | Deliver change management plan for payments go-live | Done | Low | Rajan | Programme Delivery | Sprint 13 | Change Delivery | 3 | 3 | 2026-03-16 | 2026-03-21 | 2026-03-16 | 2026-03-20 | No |  | DM-308 | 3
DM-323 | Build risk reporting pack for ExCo quarterly review | Done | High | Sonia | Change Management | Sprint 13 | Risk Reporting | 8 | 8 | 2026-03-19 | 2026-03-22 | 2026-03-18 | 2026-03-21 | No |  |  | 3
DM-324 | Deliver client onboarding framework for digital banking | Done | High | Pooja | Risk Governance | Sprint 13 | Client Onboarding | 5 | 5 | 2026-03-16 | 2026-03-19 | 2026-03-16 | 2026-03-20 | No |  |  | 3
DM-325 | Deploy SLA monitoring framework for operations | Done | Medium | Deepa | Client Services | Sprint 13 | SLA Management | 8 | 8 | 2026-03-22 | 2026-03-25 | 2026-03-21 | 2026-03-24 | No |  |  | 4
DM-326 | Design stakeholder comms plan for regulatory programme | Done | Medium | Nitin | Risk Governance | Sprint 13 | Stakeholder Engagement | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-20 | 2026-03-22 | No |  |  | 3
DM-327 | Build portfolio dashboard for Head of Delivery | Done | High | Arun | Change Management | Sprint 13 | Portfolio MI | 8 | 8 | 2026-03-19 | 2026-03-23 | 2026-03-20 | 2026-03-22 | No |  | DM-310 | 4
DM-328 | Deliver resource plan update for risk governance workstream | Done | Critical | Vivek | Client Services | Sprint 13 | Resource Planning | 8 | 8 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-26 | Yes |  |  | 4
DM-329 | Draft benefits realisation update for programme board | Done | High | Kavya | Programme Delivery | Sprint 13 | Benefits Realisation | 8 | 8 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-25 | Yes |  |  | 4
DM-330 | Develop regulatory change impact assessment for FCA rules | In Progress | High | Rajan | Programme Delivery | Sprint 13 | Regulatory Compliance | 5 | 5 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
DM-331 | Build client reporting MI for wholesale banking team | In Progress | Low | Deepa | Client Services | Sprint 13 | Portfolio MI | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-18 |  | Yes |  |  | 3
DM-332 | Design programme delivery model for payments modernisation | In Progress | Medium | Vivek | Client Services | Sprint 13 | Change Delivery | 8 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
DM-333 | Update SLA breach log for client services review | In Progress | Critical | Nitin | Risk Governance | Sprint 13 | SLA Management | 5 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
DM-334 | Deliver steering committee pack for transformation programme | Blocked | Critical | Arun | Change Management | Sprint 13 | Programme Governance | 5 | 5 | 2026-03-22 | 2026-03-23 | 2026-03-23 |  | Yes | Steering Committee approval not received — escalation pending | DM-320 | 3
DM-335 | Submit CCAR stress test evidence to risk committee | Blocked | Critical | Pooja | Risk Governance | Sprint 13 | Risk Reporting | 3 | 3 | 2026-03-22 | 2026-03-23 | 2026-03-22 |  | Yes | Testing environment not provisioned by infrastructure team |  | 3
DM-336 | Build resource onboarding pack for change programme | Blocked | Medium | Sonia | Change Management | Sprint 13 | Resource Planning | 3 | 3 | 2026-03-19 | 2026-03-22 | 2026-03-21 |  | Yes | Resource unavailable — key SME on regulatory secondment |  | 3
DM-337 | Review programme delivery plan for CBS migration | Supervisor Review | High | Kavya | Programme Delivery | Sprint 13 | Programme Governance | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
DM-338 | Validate risk data architecture for PRA submission | Supervisor Review | High | Rajan | Programme Delivery | Sprint 13 | Risk Reporting | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 4
DM-339 | Review regulatory compliance roadmap for FCA delivery | Supervisor Review | Medium | Vivek | Client Services | Sprint 13 | Regulatory Compliance | 5 | 5 | 2026-03-22 | 2026-03-24 | 2026-03-22 |  | Yes |  |  | 4
DM-340 | Validate client SLA framework for portfolio review | Supervisor Review | High | Arun | Change Management | Sprint 13 | SLA Management | 5 | 5 | 2026-03-22 | 2026-03-25 | 2026-03-22 |  | Yes |  |  | 4
DM-341 | Complete programme governance update for transformation board | Done | Critical | Kavya | Programme Delivery | Sprint 14 | Programme Governance | 8 | 8 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-04-02 | Yes |  | DM-337 | 5
DM-342 | Deliver change management plan for core banking cutover | In Progress | High | Rajan | Programme Delivery | Sprint 14 | Change Delivery | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  | DM-341 | 5
DM-343 | Design wealth advisory SLA pack for relationship managers | In Progress | Medium | Arun | Change Management | Sprint 14 | SLA Management | 8 | 8 | 2026-03-30 | 2026-04-02 | 2026-03-30 |  | Yes |  |  | 5
DM-344 | Build client onboarding tracker for digital channels | In Progress | High | Deepa | Client Services | Sprint 14 | Client Onboarding | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
DM-345 | Deliver portfolio MI dashboard for steering committee | In Progress | Medium | Vivek | Client Services | Sprint 14 | Portfolio MI | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
DM-346 | Build stakeholder engagement tracker for FCA programme | In Progress | Low | Kavya | Programme Delivery | Sprint 14 | Stakeholder Engagement | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
DM-347 | Draft programme closure checklist for legacy migration | In Progress | Critical | Rajan | Programme Delivery | Sprint 14 | Programme Governance | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
DM-348 | Design resource plan for regulatory remediation sprint | In Progress | High | Nitin | Risk Governance | Sprint 14 | Resource Planning | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
DM-349 | Build benefits realisation report for programme director | In Progress | Critical | Vivek | Client Services | Sprint 14 | Benefits Realisation | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
DM-350 | Deliver change impact update for regulatory programme | In Progress | High | Sonia | Change Management | Sprint 14 | Regulatory Compliance | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
DM-351 | Submit PRA regulatory evidence pack to compliance portal | Blocked | Critical | Nitin | Risk Governance | Sprint 14 | Regulatory Compliance | 8 | 8 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | FCA regulatory freeze — no change deployments permitted | DM-335 | 5
DM-352 | Deliver steering committee update for transformation | Blocked | High | Arun | Change Management | Sprint 14 | Programme Governance | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | Steering Committee approval not received — escalation pending |  | 5
DM-353 | Deploy client SLA reporting tool for operations team | Blocked | Critical | Deepa | Client Services | Sprint 14 | SLA Management | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Procurement approval delayed — vendor contract not executed |  | 6
DM-354 | Build risk data governance framework for BCBS submission | Blocked | High | Pooja | Risk Governance | Sprint 14 | Risk Reporting | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Programme decision record awaiting Portfolio Director approval |  | 6
DM-355 | Review delivery plan for mortgage origination programme | Supervisor Review | High | Pooja | Risk Governance | Sprint 14 | Change Delivery | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
DM-356 | Validate resource capacity plan for regulatory sprint | Supervisor Review | High | Kavya | Programme Delivery | Sprint 14 | Resource Planning | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
DM-357 | Review regulatory programme roadmap for FCA alignment | Supervisor Review | Medium | Rajan | Programme Delivery | Sprint 14 | Regulatory Compliance | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
DM-358 | Design programme exit criteria for digital banking launch | To Do | High | Arun | Change Management | Sprint 14 | Programme Governance | 5 | 5 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
DM-359 | Build benefits tracker for regulatory compliance programme | To Do | Medium | Nitin | Risk Governance | Sprint 14 | Benefits Realisation | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
DM-360 | Design stakeholder map for payments hub transformation | To Do | High | Sonia | Change Management | Sprint 14 | Stakeholder Engagement | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
Facilitator note: Sprint 12 = Done 15, InProg 2, Blocked 2, ToDo 1 (healthy). Sprint 13 = Done 9, InProg 4, Blocked 3, SupRev 4 (mixed). Sprint 14 = Done 1, InProg 9, Blocked 4, SupRev 3, ToDo 3 (at-risk). Status totals: Done=25, InProg=15, Blocked=9, SupRev=7, ToDo=4 (=60). Blocked rows amber-highlighted. Blocker Resistance in radar chart MUST be inverted — fewer blockers = higher score.

## Squad Targets
Squad | Sprint | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
Programme Delivery | Sprint 12 | 30 | 85 | 3
Programme Delivery | Sprint 13 | 28 | 80 | 3
Programme Delivery | Sprint 14 | 32 | 80 | 3
Change Management | Sprint 12 | 27 | 90 | 3
Change Management | Sprint 13 | 24 | 90 | 2
Change Management | Sprint 14 | 30 | 90 | 2
Risk Governance | Sprint 12 | 28 | 80 | 3
Risk Governance | Sprint 13 | 26 | 80 | 2
Risk Governance | Sprint 14 | 32 | 80 | 2
Client Services | Sprint 12 | 28 | 90 | 2
Client Services | Sprint 13 | 24 | 85 | 2
Client Services | Sprint 14 | 30 | 90 | 2
Facilitator note: Squad Targets feed the Radar Chart for Level 3. Planned Velocity provides the velocity denominator per squad. On-Time Target % is the benchmark. Max Blockers Allowed is the inversion upper bound for Blocker Resistance. Sprint 14 targets are highest but performance is worst — the coaching moment for a Delivery Manager audience.

## Sprint Ceremonies
Sprint | Ceremony | Date | Key Decisions / Notes
Sprint 12 | Sprint Planning | 2026-03-02 | 20 tickets committed; 2 delivery tasks carried over from previous cycle. Delivery Manager confirmed governance framework scope with Portfolio Director.
Sprint 12 | Daily Standup Summary (Week 1) | 2026-03-06 | Programme Delivery blocker on client onboarding pack — Delivery Manager escalated to contracting team lead for expedited sign-off.
Sprint 12 | Mid-Sprint Review | 2026-03-09 | 3 delivery tickets re-estimated after scope clarification from FCA; Change Management flagged testing environment instability impacting compliance work.
Sprint 12 | Sprint Review | 2026-03-13 | 15 of 20 tickets done; 2 blocked (DM-318, DM-319); 1 carried to Sprint 13. Delivery Manager signed off on programme governance decisions.
Sprint 12 | Retrospective | 2026-03-13 | Action: improve cross-squad dependency tracking; Delivery Manager to add escalation status column to weekly delivery report.
Sprint 13 | Sprint Planning | 2026-03-16 | 20 tickets committed including 1 carryover; 1 new P1 regulatory item added. Delivery Manager flagged capacity risk — one squad lead supporting FCA visit.
Sprint 13 | Daily Standup Summary (Week 1) | 2026-03-20 | Change Management ahead on portfolio work; Risk Governance blocked on testing environment. Delivery Manager reviewing steering committee schedule.
Sprint 13 | Mid-Sprint Review | 2026-03-23 | Client requested 2 additional MI reporting tickets mid-sprint. Delivery Manager flagged scope addition risk — deferred pending portfolio director approval.
Sprint 13 | Sprint Review | 2026-03-27 | 14 of 20 tickets done; velocity dip vs Sprint 12; 4 tickets in Supervisor Review. Delivery Manager escalated 3 blocked tickets to Head of Programme Delivery.
Sprint 13 | Retrospective | 2026-03-27 | Action: no mid-sprint scope additions without Delivery Manager approval; blocker SLA set at 24 hours with daily governance check-in.
Sprint 14 | Sprint Planning | 2026-03-30 | 20 tickets committed; team flagged resource risk — Pooja supporting PRA supervisory visit week 2. Delivery Manager raised concern on regulatory deadline.
Sprint 14 | Daily Standup Summary (Week 1) | 2026-04-03 | 6 tickets blocked — highest blocker count across 3 sprints. Delivery Manager called emergency governance triage with all squad leads and Programme Director.
Sprint 14 | Mid-Sprint Review | 2026-04-06 | Only 1 ticket done at midpoint; Delivery Manager escalated to Programme Director and Chief Risk Officer — FCA committed delivery date now at risk.
Sprint 14 | Sprint Review | 2026-04-10 | Sprint still in progress — formal review scheduled 10 April. Delivery Manager preparing risk summary for Head of Programme Delivery and FCA liaison.
Facilitator note: Sprint 14 rows are amber-highlighted — these are the rows the Level 3 Ceremony Insights section must pull. All escalations reference the Delivery Manager, not PM or Tech Lead. The Sprint 14 Mid-Sprint Review row ('Only 1 ticket done at midpoint') is the key coaching moment. Any output referencing 'PM' indicates the agent did not use actual sheet data.