## Sprint Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
PM-301 | Define project charter and governance framework for CBS upgrade | Done | Critical | Meera | Project Execution | Sprint 12 | Project Planning | 13 | 13 | 2026-03-06 | 2026-03-08 | 2026-03-05 | 2026-03-11 | Yes |  |  | 1
PM-302 | Deliver requirements traceability matrix for payments migration | Done | High | Sanjay | Project Execution | Sprint 12 | Requirements Management | 8 | 8 | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-03-05 | Yes |  |  | 1
PM-303 | Build stakeholder reporting dashboard for ExCo pack | Done | Low | Tara | Business Analysis | Sprint 12 | Stakeholder Reporting | 8 | 8 | 2026-03-09 | 2026-03-12 | 2026-03-08 | 2026-03-11 | No |  |  | 2
PM-304 | Implement project RAID log for regulatory remediation programme | Done | High | Laleh | Testing & QA | Sprint 12 | Issue & Risk Management | 5 | 5 | 2026-03-03 | 2026-03-04 | 2026-03-04 | 2026-03-04 | No |  |  | 1
PM-305 | Design UAT strategy for digital banking platform upgrade | Done | Medium | Sunita | Transition & Go-Live | Sprint 12 | UAT Coordination | 8 | 8 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-11 | Yes |  |  | 1
PM-306 | Deliver budget tracking model for programme delivery | Done | Medium | Vijay | Transition & Go-Live | Sprint 12 | Budget Tracking | 5 | 5 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-09 | Yes |  |  | 1
PM-307 | Define change control process for core banking migration | Done | High | Meera | Project Execution | Sprint 12 | Change Control | 5 | 5 | 2026-03-03 | 2026-03-08 | 2026-03-03 | 2026-03-07 | No |  |  | 1
PM-308 | Draft vendor management framework for IT service partners | Done | High | Sanjay | Project Execution | Sprint 12 | Vendor Management | 8 | 8 | 2026-03-02 | 2026-03-04 | 2026-03-03 | 2026-03-05 | Yes |  | PM-302 | 1
PM-309 | Deliver quality assurance plan for UAT execution cycle | Done | Medium | Kiran | Business Analysis | Sprint 12 | Quality Assurance | 5 | 5 | 2026-03-09 | 2026-03-13 | 2026-03-11 | 2026-03-12 | No |  | PM-304 | 2
PM-310 | Build go-live readiness checklist for payments cutover | Done | Medium | Tara | Business Analysis | Sprint 12 | Go-Live Management | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-11 | 2026-03-15 | Yes |  |  | 2
PM-311 | Deliver PRA evidence pack for regulatory checkpoint gate | Done | Critical | Kiran | Business Analysis | Sprint 12 | Issue & Risk Management | 3 | 3 | 2026-03-10 | 2026-03-12 | 2026-03-11 | 2026-03-10 | No |  | PM-303 | 2
PM-312 | Complete test script library for regression testing cycle | Done | Medium | Deepak | Testing & QA | Sprint 12 | UAT Coordination | 8 | 8 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-14 | Yes |  |  | 2
PM-313 | Design parallel run strategy for CBS migration cutover | Done | High | Laleh | Testing & QA | Sprint 12 | Go-Live Management | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-10 | 2026-03-13 | No |  |  | 2
PM-314 | Deliver weekly project status report for Steering Committee | Done | High | Vijay | Transition & Go-Live | Sprint 12 | Stakeholder Reporting | 5 | 5 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-10 | No |  |  | 2
PM-315 | Build UAT defect tracking log for testing team | Done | High | Sunita | Transition & Go-Live | Sprint 12 | Quality Assurance | 3 | 3 | 2026-03-08 | 2026-03-13 | 2026-03-10 | 2026-03-13 | Yes |  |  | 1
PM-316 | Develop project budget variance report for PMO | In Progress | High | Deepak | Testing & QA | Sprint 12 | Budget Tracking | 2 | 2 | 2026-03-11 | 2026-03-13 | 2026-03-11 |  | Yes |  |  | 2
PM-317 | Design benefits realisation framework for digital programme | In Progress | High | Meera | Project Execution | Sprint 12 | Project Planning | 2 | 2 | 2026-03-08 | 2026-03-13 | 2026-03-10 |  | Yes |  |  | 1
PM-318 | Deliver client acceptance testing pack for CBS release | Blocked | Critical | Sanjay | Project Execution | Sprint 12 | UAT Coordination | 5 | 5 | 2026-03-05 | 2026-03-10 | 2026-03-04 |  | Yes | Client sign-off delayed — legal review of contract amendment pending |  | 1
PM-319 | Submit FCA regulatory reporting update for remediation gate | Blocked | Critical | Tara | Business Analysis | Sprint 12 | Issue & Risk Management | 3 | 3 | 2026-03-08 | 2026-03-11 | 2026-03-10 |  | Yes | FCA regulatory freeze — change blackout period in effect |  | 2
PM-320 | Design project closure framework for legacy decommission | To Do | Medium | Kiran | Business Analysis | Sprint 12 | Project Planning | 5 | 5 | 2026-03-12 | 2026-03-14 |  |  | No |  |  | 2
PM-321 | Complete project governance review for transformation | Done | Critical | Meera | Project Execution | Sprint 13 | Project Planning | 5 | 5 | 2026-03-19 | 2026-03-21 | 2026-03-19 | 2026-03-22 | Yes |  | PM-318 | 3
PM-322 | Deliver change control log for payments modernisation | Done | Low | Sanjay | Project Execution | Sprint 13 | Change Control | 3 | 3 | 2026-03-16 | 2026-03-21 | 2026-03-16 | 2026-03-20 | No |  | PM-308 | 3
PM-323 | Build requirements validation pack for UAT sign-off | Done | High | Tara | Business Analysis | Sprint 13 | Requirements Management | 8 | 8 | 2026-03-19 | 2026-03-22 | 2026-03-18 | 2026-03-21 | No |  |  | 3
PM-324 | Deliver go-live rehearsal plan for digital banking launch | Done | High | Laleh | Testing & QA | Sprint 13 | Go-Live Management | 5 | 5 | 2026-03-16 | 2026-03-19 | 2026-03-16 | 2026-03-20 | No |  |  | 3
PM-325 | Deploy SLA monitoring framework for operations handover | Done | Medium | Sunita | Transition & Go-Live | Sprint 13 | UAT Coordination | 8 | 8 | 2026-03-22 | 2026-03-25 | 2026-03-21 | 2026-03-24 | No |  |  | 4
PM-326 | Deliver vendor performance review for IT partners | Done | Medium | Vijay | Transition & Go-Live | Sprint 13 | Vendor Management | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-20 | 2026-03-22 | No |  |  | 3
PM-327 | Build portfolio MI dashboard for Head of Programmes | Done | High | Kiran | Business Analysis | Sprint 13 | Stakeholder Reporting | 8 | 8 | 2026-03-19 | 2026-03-23 | 2026-03-20 | 2026-03-22 | No |  | PM-310 | 4
PM-328 | Deliver budget update to PMO for programme cost review | Done | Critical | Deepak | Testing & QA | Sprint 13 | Budget Tracking | 8 | 8 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-26 | Yes |  |  | 4
PM-329 | Draft quality assurance report for UAT completion gate | Done | High | Meera | Project Execution | Sprint 13 | Quality Assurance | 8 | 8 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-25 | Yes |  |  | 4
PM-330 | Develop regulatory change impact log for FCA submission | In Progress | High | Sanjay | Project Execution | Sprint 13 | Issue & Risk Management | 5 | 5 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
PM-331 | Build client reporting MI for UAT handover pack | In Progress | Low | Sunita | Transition & Go-Live | Sprint 13 | Stakeholder Reporting | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-18 |  | Yes |  |  | 3
PM-332 | Design test exit criteria for regression testing cycle | In Progress | Medium | Vijay | Transition & Go-Live | Sprint 13 | Quality Assurance | 8 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
PM-333 | Update RAID log for client go-live readiness review | In Progress | Critical | Deepak | Testing & QA | Sprint 13 | Issue & Risk Management | 5 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
PM-334 | Deliver Steering Committee update for programme gate | Blocked | Critical | Kiran | Business Analysis | Sprint 13 | Project Planning | 5 | 5 | 2026-03-22 | 2026-03-23 | 2026-03-23 |  | Yes | Steering Committee approval not received — quorum issue at last gate | PM-320 | 3
PM-335 | Submit UAT sign-off evidence to client acceptance team | Blocked | Critical | Laleh | Testing & QA | Sprint 13 | UAT Coordination | 3 | 3 | 2026-03-22 | 2026-03-23 | 2026-03-22 |  | Yes | UAT environment not provisioned — infrastructure request outstanding |  | 3
PM-336 | Build resource onboarding pack for testing workstream | Blocked | Medium | Tara | Business Analysis | Sprint 13 | Vendor Management | 3 | 3 | 2026-03-19 | 2026-03-22 | 2026-03-21 |  | Yes | Vendor dependency unresolved — third-party SLA breach escalated |  | 3
PM-337 | Review project delivery plan for CBS migration | Supervisor Review | High | Meera | Project Execution | Sprint 13 | Project Planning | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
PM-338 | Validate requirements baseline for payments go-live | Supervisor Review | High | Sanjay | Project Execution | Sprint 13 | Requirements Management | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 4
PM-339 | Review go-live readiness report for digital banking | Supervisor Review | Medium | Vijay | Transition & Go-Live | Sprint 13 | Go-Live Management | 5 | 5 | 2026-03-22 | 2026-03-24 | 2026-03-22 |  | Yes |  |  | 4
PM-340 | Validate change control log for Steering Committee | Supervisor Review | High | Kiran | Business Analysis | Sprint 13 | Change Control | 5 | 5 | 2026-03-22 | 2026-03-25 | 2026-03-22 |  | Yes |  |  | 4
PM-341 | Complete project governance pack for Steering Committee gate | Done | Critical | Meera | Project Execution | Sprint 14 | Project Planning | 8 | 8 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-04-02 | Yes |  | PM-337 | 5
PM-342 | Deliver change management plan for CBS cutover | In Progress | High | Sanjay | Project Execution | Sprint 14 | Change Control | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  | PM-341 | 5
PM-343 | Design client handover pack for digital banking launch | In Progress | Medium | Kiran | Business Analysis | Sprint 14 | Go-Live Management | 8 | 8 | 2026-03-30 | 2026-04-02 | 2026-03-30 |  | Yes |  |  | 5
PM-344 | Build UAT exit report for digital channels go-live | In Progress | High | Laleh | Testing & QA | Sprint 14 | UAT Coordination | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
PM-345 | Deliver portfolio MI report for Head of Programmes | In Progress | Medium | Vijay | Transition & Go-Live | Sprint 14 | Stakeholder Reporting | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
PM-346 | Build stakeholder comms plan for FCA programme closure | In Progress | Low | Meera | Project Execution | Sprint 14 | Stakeholder Reporting | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
PM-347 | Draft project lessons learned for PMO knowledge base | In Progress | Critical | Sanjay | Project Execution | Sprint 14 | Project Planning | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
PM-348 | Design resource transition plan for programme handover | In Progress | High | Deepak | Testing & QA | Sprint 14 | Vendor Management | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
PM-349 | Deliver benefits realisation report to programme sponsor | In Progress | Critical | Vijay | Transition & Go-Live | Sprint 14 | Budget Tracking | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
PM-350 | Deliver change impact log for regulatory programme closure | In Progress | High | Tara | Business Analysis | Sprint 14 | Issue & Risk Management | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
PM-351 | Submit FCA regulatory evidence pack for programme closure | Blocked | Critical | Deepak | Testing & QA | Sprint 14 | Issue & Risk Management | 8 | 8 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | FCA regulatory freeze — change blackout period in effect | PM-335 | 5
PM-352 | Deliver Steering Committee closure report for transformation | Blocked | High | Kiran | Business Analysis | Sprint 14 | Project Planning | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | Steering Committee approval not received — quorum issue at last gate |  | 5
PM-353 | Deploy client SLA reporting dashboard for operations | Blocked | Critical | Sunita | Transition & Go-Live | Sprint 14 | Go-Live Management | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Procurement approval delayed — vendor purchase order not executed |  | 6
PM-354 | Build project data governance framework for archive | Blocked | High | Laleh | Testing & QA | Sprint 14 | Quality Assurance | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Project decision log awaiting PMO Director and Sponsor sign-off |  | 6
PM-355 | Review delivery plan for CBS migration go-live | Supervisor Review | High | Tara | Business Analysis | Sprint 14 | Requirements Management | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
PM-356 | Validate resource capacity plan for programme closure | Supervisor Review | High | Meera | Project Execution | Sprint 14 | Project Planning | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
PM-357 | Review vendor management framework for PMO sign-off | Supervisor Review | Medium | Sanjay | Project Execution | Sprint 14 | Vendor Management | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
PM-358 | Design project archive strategy for digital banking PMO | To Do | High | Kiran | Business Analysis | Sprint 14 | Project Planning | 5 | 5 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
PM-359 | Build benefits tracker for regulatory compliance closure | To Do | Medium | Deepak | Testing & QA | Sprint 14 | Budget Tracking | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
PM-360 | Design handover checklist for Transition & Go-Live team | To Do | High | Sunita | Transition & Go-Live | Sprint 14 | Go-Live Management | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6

## Squad Targets
Squad | Sprint | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
Project Execution | Sprint 12 | 30 | 85 | 3
Project Execution | Sprint 13 | 28 | 80 | 3
Project Execution | Sprint 14 | 32 | 80 | 3
Business Analysis | Sprint 12 | 27 | 90 | 3
Business Analysis | Sprint 13 | 24 | 90 | 2
Business Analysis | Sprint 14 | 30 | 90 | 2
Testing & QA | Sprint 12 | 28 | 80 | 3
Testing & QA | Sprint 13 | 26 | 80 | 2
Testing & QA | Sprint 14 | 32 | 80 | 2
Transition & Go-Live | Sprint 12 | 28 | 90 | 2
Transition & Go-Live | Sprint 13 | 24 | 85 | 2
Transition & Go-Live | Sprint 14 | 30 | 90 | 2

## Sprint Ceremonies
Sprint | Ceremony | Date | Key Decisions / Notes
Sprint 12 | Sprint Planning | 2026-03-02 | 20 tickets committed; 2 project tasks carried over from previous cycle. Project Manager confirmed scope baseline and change control process with PMO.
Sprint 12 | Daily Standup Summary (Week 1) | 2026-03-06 | Project Execution blocker on client acceptance pack — Project Manager escalated to legal and contracting team for expedited sign-off.
Sprint 12 | Mid-Sprint Review | 2026-03-09 | 3 project tickets re-estimated after UAT scope clarification from client; Testing & QA flagged test environment instability impacting regression cycle.
Sprint 12 | Sprint Review | 2026-03-13 | 15 of 20 tickets done; 2 blocked (PM-318, PM-319); 1 carried to Sprint 13. Project Manager signed off on go-live readiness checklist.
Sprint 12 | Retrospective | 2026-03-13 | Action: improve cross-workstream dependency tracking; Project Manager to add blocker escalation status to weekly status report.
Sprint 13 | Sprint Planning | 2026-03-16 | 20 tickets committed including 1 carryover; 1 new P1 FCA regulatory item added. Project Manager flagged capacity risk — one workstream lead on client visit.
Sprint 13 | Daily Standup Summary (Week 1) | 2026-03-20 | Business Analysis ahead on requirements work; Testing & QA blocked on UAT environment. Project Manager reviewing Steering Committee gate schedule.
Sprint 13 | Mid-Sprint Review | 2026-03-23 | Client requested 2 additional UAT tickets mid-sprint. Project Manager flagged scope risk — deferred pending PMO Director and Sponsor approval.
Sprint 13 | Sprint Review | 2026-03-27 | 14 of 20 tickets done; velocity dip vs Sprint 12; 4 tickets in Supervisor Review. Project Manager escalated 3 blocked tickets to Programme Manager.
Sprint 13 | Retrospective | 2026-03-27 | Action: no mid-sprint scope additions without Project Manager approval; blocker SLA set at 24 hours with daily programme office check-in.
Sprint 14 | Sprint Planning | 2026-03-30 | 20 tickets committed; team flagged resource risk — Laleh supporting FCA supervisory visit week 2. Project Manager raised concern on go-live deadline.
Sprint 14 | Daily Standup Summary (Week 1) | 2026-04-03 | 6 tickets blocked — highest blocker count across 3 sprints. Project Manager called emergency governance triage with all workstream leads and Programme Manager.
Sprint 14 | Mid-Sprint Review | 2026-04-06 | Only 1 ticket done at midpoint; Project Manager escalated to Programme Manager and Chief Risk Officer — client go-live date now at serious risk.
Sprint 14 | Sprint Review | 2026-04-10 | Sprint still in progress — formal review scheduled 10 April. Project Manager preparing risk summary for PMO Director and FCA liaison team.