## Sprint Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
FI-301 | Migrate core banking settlement engine to cloud-native platform | Done | Critical | Priya | Retail Banking Tech | Sprint 12 | Core Banking Modernisation | 13 | 13 | 2026-03-06 | 2026-03-08 | 2026-03-05 | 2026-03-11 | Yes |  |  | 1
FI-302 | Design payment rail routing logic for ISO 20022 migration | Done | High | Arjun | Retail Banking Tech | Sprint 12 | Payments Infrastructure | 8 | 8 | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-03-05 | Yes |  |  | 1
FI-303 | Implement PSD2 open banking API gateway endpoint | Done | Low | Meena | Wholesale & Markets | Sprint 12 | API Gateway | 8 | 8 | 2026-03-09 | 2026-03-12 | 2026-03-08 | 2026-03-11 | No |  |  | 2
FI-304 | Build IAM role-based access control for trading systems | Done | High | Divya | Risk & Compliance Tech | Sprint 12 | Identity & Access Management | 5 | 5 | 2026-03-03 | 2026-03-04 | 2026-03-04 | 2026-03-04 | No |  |  | 1
FI-305 | Architect cloud landing zone for retail banking workloads | Done | Medium | Ananya | Digital & Channels | Sprint 12 | Cloud Migration | 8 | 8 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-11 | Yes |  |  | 1
FI-306 | Design data architecture for regulatory MI submissions | Done | Medium | Rohit | Digital & Channels | Sprint 12 | Data Architecture | 5 | 5 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-09 | Yes |  |  | 1
FI-307 | Define API contract standards for core banking integration | Done | High | Priya | Retail Banking Tech | Sprint 12 | API Gateway | 5 | 5 | 2026-03-03 | 2026-03-08 | 2026-03-03 | 2026-03-07 | No |  |  | 1
FI-308 | Architect fraud detection ML pipeline for card transactions | Done | High | Arjun | Retail Banking Tech | Sprint 12 | Fraud Detection | 8 | 8 | 2026-03-02 | 2026-03-04 | 2026-03-03 | 2026-03-05 | Yes |  | FI-302 | 1
FI-309 | Design customer data platform ingestion pipeline for CRM | Done | Medium | Karthik | Wholesale & Markets | Sprint 12 | Customer Data Platform | 5 | 5 | 2026-03-09 | 2026-03-13 | 2026-03-11 | 2026-03-12 | No |  | FI-304 | 2
FI-310 | Build operational resilience runbook for payment systems | Done | Medium | Meena | Wholesale & Markets | Sprint 12 | Operational Resilience | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-11 | 2026-03-15 | Yes |  |  | 2
FI-311 | Design CCAR regulatory reporting data model | Done | Critical | Karthik | Wholesale & Markets | Sprint 12 | Regulatory Reporting | 3 | 3 | 2026-03-10 | 2026-03-12 | 2026-03-11 | 2026-03-10 | No |  | FI-303 | 2
FI-312 | Implement zero-trust network architecture for branch network | Done | Medium | Sunil | Risk & Compliance Tech | Sprint 12 | Identity & Access Management | 8 | 8 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-14 | Yes |  |  | 2
FI-313 | Architect multi-region failover for core banking platform | Done | High | Divya | Risk & Compliance Tech | Sprint 12 | Operational Resilience | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-10 | 2026-03-13 | No |  |  | 2
FI-314 | Design AML transaction monitoring rules engine | Done | High | Rohit | Digital & Channels | Sprint 12 | Fraud Detection | 5 | 5 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-10 | No |  |  | 2
FI-315 | Architect mobile banking API gateway upgrade | Done | High | Ananya | Digital & Channels | Sprint 12 | API Gateway | 3 | 3 | 2026-03-08 | 2026-03-13 | 2026-03-10 | 2026-03-13 | Yes |  |  | 1
FI-316 | Build data lineage framework for PRA reporting submissions | In Progress | High | Sunil | Risk & Compliance Tech | Sprint 12 | Regulatory Reporting | 2 | 2 | 2026-03-11 | 2026-03-13 | 2026-03-11 |  | Yes |  |  | 2
FI-317 | Design event-driven architecture for real-time payments | In Progress | High | Priya | Retail Banking Tech | Sprint 12 | Payments Infrastructure | 2 | 2 | 2026-03-08 | 2026-03-13 | 2026-03-10 |  | Yes |  |  | 1
FI-318 | Configure CBS API integration for real-time balance enquiry | Blocked | Critical | Arjun | Retail Banking Tech | Sprint 12 | Core Banking Modernisation | 5 | 5 | 2026-03-05 | 2026-03-10 | 2026-03-04 |  | Yes | Vendor SLA breach on Core Banking System API — patch delayed |  | 1
FI-319 | Automate PRA regulatory MI pack distribution pipeline | Blocked | Critical | Meena | Wholesale & Markets | Sprint 12 | Regulatory Reporting | 3 | 3 | 2026-03-08 | 2026-03-11 | 2026-03-10 |  | Yes | PRA sign-off not received — regulatory approval pending |  | 2
FI-320 | Design disaster recovery architecture for digital channels | To Do | Medium | Karthik | Wholesale & Markets | Sprint 12 | Operational Resilience | 5 | 5 | 2026-03-12 | 2026-03-14 |  |  | No |  |  | 2
FI-321 | Complete cloud migration for mortgage origination workload | Done | Critical | Priya | Retail Banking Tech | Sprint 13 | Cloud Migration | 5 | 5 | 2026-03-19 | 2026-03-21 | 2026-03-19 | 2026-03-22 | Yes |  | FI-318 | 3
FI-322 | Deliver ISO 20022 payment message transformation layer | Done | Low | Arjun | Retail Banking Tech | Sprint 13 | Payments Infrastructure | 3 | 3 | 2026-03-16 | 2026-03-21 | 2026-03-16 | 2026-03-20 | No |  | FI-308 | 3
FI-323 | Build real-time fraud scoring API for card authorisation | Done | High | Meena | Wholesale & Markets | Sprint 13 | Fraud Detection | 8 | 8 | 2026-03-19 | 2026-03-22 | 2026-03-18 | 2026-03-21 | No |  |  | 3
FI-324 | Implement customer identity verification for digital onboarding | Done | High | Divya | Risk & Compliance Tech | Sprint 13 | Identity & Access Management | 5 | 5 | 2026-03-16 | 2026-03-19 | 2026-03-16 | 2026-03-20 | No |  |  | 3
FI-325 | Deploy API management platform for open banking ecosystem | Done | Medium | Ananya | Digital & Channels | Sprint 13 | API Gateway | 8 | 8 | 2026-03-22 | 2026-03-25 | 2026-03-21 | 2026-03-24 | No |  |  | 4
FI-326 | Design operational resilience playbook for cyber incidents | Done | Medium | Rohit | Digital & Channels | Sprint 13 | Operational Resilience | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-20 | 2026-03-22 | No |  |  | 3
FI-327 | Integrate customer data platform with wealth advisory CRM | Done | High | Karthik | Wholesale & Markets | Sprint 13 | Customer Data Platform | 8 | 8 | 2026-03-19 | 2026-03-23 | 2026-03-20 | 2026-03-22 | No |  | FI-310 | 4
FI-328 | Build data architecture for BCBS 239 risk data aggregation | Done | Critical | Sunil | Risk & Compliance Tech | Sprint 13 | Data Architecture | 8 | 8 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-26 | Yes |  |  | 4
FI-329 | Map enterprise data migration schema for core banking upgrade | In Progress | High | Priya | Retail Banking Tech | Sprint 13 | Core Banking Modernisation | 5 | 5 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
FI-330 | Architect real-time SLA monitoring for payments team | In Progress | Low | Arjun | Retail Banking Tech | Sprint 13 | Payments Infrastructure | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-18 |  | Yes |  |  | 3
FI-331 | Define solution architecture for regulatory sandbox environment | In Progress | Medium | Rohit | Digital & Channels | Sprint 13 | Regulatory Reporting | 8 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
FI-332 | Tune ML model parameters for credit risk scoring engine | In Progress | Critical | Ananya | Digital & Channels | Sprint 13 | Fraud Detection | 5 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
FI-333 | Draft architecture blueprint for payments hub modernisation | Done | Medium | Divya | Risk & Compliance Tech | Sprint 13 | Payments Infrastructure | 8 | 8 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-26 | Yes |  |  | 4
FI-334 | Configure auto-settlement integration for wholesale trading desk | Blocked | Critical | Karthik | Wholesale & Markets | Sprint 13 | Payments Infrastructure | 5 | 5 | 2026-03-22 | 2026-03-23 | 2026-03-23 |  | Yes | FCA regulatory hold — change freeze in effect | FI-320 | 3
FI-335 | Automate CCAR stress test data submission to regulators | Blocked | Critical | Sunil | Risk & Compliance Tech | Sprint 13 | Regulatory Reporting | 3 | 3 | 2026-03-22 | 2026-03-23 | 2026-03-22 |  | Yes | UAT environment not provisioned by infrastructure team |  | 3
FI-336 | Build enterprise key management service for cloud workloads | Blocked | Medium | Meena | Wholesale & Markets | Sprint 13 | Identity & Access Management | 3 | 3 | 2026-03-19 | 2026-03-22 | 2026-03-21 |  | Yes | Third-party integration certificate expired — renewal in progress |  | 3
FI-337 | Review architecture design for CBS-payments integration | Supervisor Review | High | Priya | Retail Banking Tech | Sprint 13 | Core Banking Modernisation | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
FI-338 | Validate data architecture for BCBS 239 compliance | Supervisor Review | High | Arjun | Retail Banking Tech | Sprint 13 | Data Architecture | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 4
FI-339 | Review cloud security architecture for PRA submission | Supervisor Review | Medium | Rohit | Digital & Channels | Sprint 13 | Cloud Migration | 5 | 5 | 2026-03-22 | 2026-03-24 | 2026-03-22 |  | Yes |  |  | 4
FI-340 | Validate operational resilience framework for FCA review | Supervisor Review | High | Karthik | Wholesale & Markets | Sprint 13 | Operational Resilience | 5 | 5 | 2026-03-22 | 2026-03-25 | 2026-03-22 |  | Yes |  |  | 4
FI-341 | Complete core banking API migration to cloud-native layer | Done | Critical | Priya | Retail Banking Tech | Sprint 14 | Core Banking Modernisation | 8 | 8 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-04-02 | Yes |  | FI-337 | 5
FI-342 | Finalise fraud detection model for real-time card screening | In Progress | High | Meena | Wholesale & Markets | Sprint 14 | Fraud Detection | 5 | 5 | 2026-03-30 | 2026-04-01 | 2026-03-30 |  | Yes |  |  | 5
FI-343 | Architect microservice decomposition for legacy CBS modules | In Progress | High | Arjun | Retail Banking Tech | Sprint 14 | Core Banking Modernisation | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  | FI-341 | 5
FI-344 | Design wealth management API for RM digital portal | In Progress | Medium | Karthik | Wholesale & Markets | Sprint 14 | Customer Data Platform | 8 | 8 | 2026-03-30 | 2026-04-02 | 2026-03-30 |  | Yes |  |  | 5
FI-345 | Integrate mobile banking platform with ISO 20022 payment rail | In Progress | High | Ananya | Digital & Channels | Sprint 14 | Payments Infrastructure | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
FI-346 | Build SLA monitoring architecture for branch technology stack | In Progress | Medium | Rohit | Digital & Channels | Sprint 14 | Operational Resilience | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
FI-347 | Design NPS data pipeline for retail customer analytics | In Progress | Low | Priya | Retail Banking Tech | Sprint 14 | Customer Data Platform | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
FI-348 | Architect ML feature store for credit risk scoring platform | In Progress | Critical | Arjun | Retail Banking Tech | Sprint 14 | Fraud Detection | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
FI-349 | Build branch technology infrastructure monitoring dashboard | In Progress | High | Sunil | Risk & Compliance Tech | Sprint 14 | Operational Resilience | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
FI-350 | Design microservice architecture for payments hub upgrade | In Progress | Critical | Rohit | Digital & Channels | Sprint 14 | Payments Infrastructure | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
FI-351 | Configure PRA regulatory reporting automation pipeline | Blocked | Critical | Sunil | Risk & Compliance Tech | Sprint 14 | Regulatory Reporting | 8 | 8 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | PRA sign-off not received — regulatory approval pending | FI-335 | 5
FI-352 | Integrate wholesale trading settlement with new payments platform | Blocked | High | Karthik | Wholesale & Markets | Sprint 14 | Payments Infrastructure | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | Legacy CBS integration handshake failing — vendor escalation raised |  | 5
FI-353 | Deploy open banking API gateway for PSD2 third-party access | Blocked | Critical | Ananya | Digital & Channels | Sprint 14 | API Gateway | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Cloud infrastructure provisioning delayed — procurement approval pending |  | 6
FI-354 | Implement enterprise data governance framework for BCBS 239 | Blocked | High | Meena | Wholesale & Markets | Sprint 14 | Data Architecture | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Architecture Decision Record awaiting CTO and CRO sign-off |  | 6
FI-355 | Review solution architecture for mortgage LOS modernisation | Supervisor Review | High | Divya | Risk & Compliance Tech | Sprint 14 | Core Banking Modernisation | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
FI-356 | Validate cloud architecture for PRA operational resilience | Supervisor Review | High | Priya | Retail Banking Tech | Sprint 14 | Cloud Migration | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
FI-357 | Review API security architecture for open banking rollout | Supervisor Review | Medium | Arjun | Retail Banking Tech | Sprint 14 | API Gateway | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
FI-358 | Design DR strategy for digital banking platform and CBS | To Do | High | Karthik | Wholesale & Markets | Sprint 14 | Operational Resilience | 5 | 5 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
FI-359 | Build data lineage map for PRA regulatory submissions | To Do | Medium | Sunil | Risk & Compliance Tech | Sprint 14 | Regulatory Reporting | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
FI-360 | Architect event streaming platform for real-time analytics | To Do | High | Divya | Risk & Compliance Tech | Sprint 14 | Data Architecture | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
Facilitator note: Sprint 12 = Done 15, InProg 2, Blocked 2, ToDo 1 (healthy — 81.0% completion, Green). Sprint 13 = Done 8, InProg 5, Blocked 3, SupRev 4 (mixed — 50.9%, Amber). Sprint 14 = Done 2, InProg 8, Blocked 4, SupRev 3, ToDo 3 (at-risk — 11.3%, Red). Status totals: Done=25, InProg=15, Blocked=9, SupRev=7, ToDo=4 (=60). Amber-highlighted rows are Blocked tickets. Blocker Resistance in radar chart MUST be inverted — fewer blockers = higher score.

## Squad Targets
Squad | Sprint | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
Retail Banking Tech | Sprint 12 | 30 | 85 | 3
Retail Banking Tech | Sprint 13 | 28 | 80 | 3
Retail Banking Tech | Sprint 14 | 32 | 80 | 3
Wholesale & Markets | Sprint 12 | 27 | 90 | 3
Wholesale & Markets | Sprint 13 | 24 | 90 | 2
Wholesale & Markets | Sprint 14 | 30 | 90 | 2
Risk & Compliance Tech | Sprint 12 | 28 | 80 | 3
Risk & Compliance Tech | Sprint 13 | 26 | 80 | 2
Risk & Compliance Tech | Sprint 14 | 32 | 80 | 2
Digital & Channels | Sprint 12 | 28 | 90 | 2
Digital & Channels | Sprint 13 | 24 | 85 | 2
Digital & Channels | Sprint 14 | 30 | 90 | 2
Facilitator note: Squad Targets feed the Radar Chart for Level 3. Planned Velocity provides the velocity denominator per squad. On-Time Target % is the benchmark. Max Blockers Allowed is the inversion upper bound for Blocker Resistance. Sprint 14 targets are highest but performance is worst — the coaching moment for a Technical Architect audience.

## Sprint Ceremonies
Sprint | Ceremony | Date | Key Decisions / Notes
Sprint 12 | Sprint Planning | 2026-03-02 | 20 tickets committed; 2 architecture designs carried over from previous delivery cycle. Technical Architect confirmed API contract freeze for core banking integration.
Sprint 12 | Daily Standup Summary (Week 1) | 2026-03-06 | Retail Banking Tech blocker on CBS API — Technical Architect escalated to vendor account manager for expedited patch SLA.
Sprint 12 | Mid-Sprint Review | 2026-03-09 | 3 architecture tickets re-estimated upward after CBS complexity assessment; Risk & Compliance Tech flagged UAT environment instability impacting integration test cycles.
Sprint 12 | Sprint Review | 2026-03-13 | 15 of 20 tickets done; 2 blocked (FI-318, FI-319); 1 carried to Sprint 13. Technical Architect signed off on cloud architecture decision records.
Sprint 12 | Retrospective | 2026-03-13 | Action: improve cross-squad dependency tracking; Technical Architect to add ADR approval column to sprint tracker and review ADR backlog weekly.
Sprint 13 | Sprint Planning | 2026-03-16 | 20 tickets committed including 1 carryover; 1 new P1 PRA remediation item added mid-week. Technical Architect flagged capacity risk — one squad lead on FCA visit support.
Sprint 13 | Daily Standup Summary (Week 1) | 2026-03-20 | Wholesale & Markets ahead on payments work; Risk & Compliance Tech blocked on CCAR submission UAT. Technical Architect reviewing CBS-payments integration ADR.
Sprint 13 | Mid-Sprint Review | 2026-03-23 | PRA requested 2 additional regulatory reporting tickets mid-sprint. Technical Architect flagged architecture impact — scope addition deferred pending ADR review.
Sprint 13 | Sprint Review | 2026-03-27 | 14 of 20 tickets done; velocity dip vs Sprint 12; 4 tickets in Supervisor Review. Technical Architect escalated 3 blocked tickets to Head of Technology and CRO.
Sprint 13 | Retrospective | 2026-03-27 | Action: no mid-sprint scope additions without Technical Architect approval; blocker SLA set at 24 hours with CTO daily check-in.
Sprint 14 | Sprint Planning | 2026-03-30 | 20 tickets committed; team flagged resource risk — Divya supporting PRA supervisory visit week 2. Technical Architect raised architecture debt concern on CBS legacy coupling.
Sprint 14 | Daily Standup Summary (Week 1) | 2026-04-03 | 6 tickets blocked — highest blocker count across 3 sprints. Technical Architect called emergency architecture triage with all squad leads and CTO.
Sprint 14 | Mid-Sprint Review | 2026-04-06 | Only 2 tickets done at midpoint; Technical Architect escalated to CTO and Chief Risk Officer — sprint at critical risk, PRA deadline in jeopardy.
Sprint 14 | Sprint Review | 2026-04-10 | Sprint still in progress — formal review scheduled 10 April. Technical Architect preparing risk summary for Head of Technology and PRA liaison.
Facilitator note: Sprint 14 rows are amber-highlighted — these are the rows the Level 3 Ceremony Insights section must pull. All escalations reference the Technical Architect, not PM or Tech Lead. The Sprint 14 Mid-Sprint Review row ('Only 2 tickets done at midpoint') is the key coaching moment. Any output referencing 'PM' indicates the agent did not use actual sheet data.