## Sprint Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
CBG-301 | Configure home loan origination workflow in LOS | Done | Critical | Priya | Retail Lending | Sprint 12 | Home Loan Origination | 13 | 13 | 2026-03-06 | 2026-03-08 | 2026-03-05 | 2026-03-11 | Yes |  |  | 1
CBG-302 | Build pre-qualification scorecard for personal loans | Done | High | Arjun | Retail Lending | Sprint 12 | Personal Loan Servicing | 8 | 8 | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-03-05 | Yes |  |  | 1
CBG-303 | Design credit card transaction dispute resolution flow | Done | Low | Meena | Wealth & Cards | Sprint 12 | Credit Card Operations | 8 | 8 | 2026-03-09 | 2026-03-12 | 2026-03-08 | 2026-03-11 | No |  |  | 2
CBG-304 | Implement KYC document verification module | Done | High | Divya | KYC & Onboarding | Sprint 12 | KYC Compliance | 5 | 5 | 2026-03-03 | 2026-03-04 | 2026-03-04 | 2026-03-04 | No |  |  | 1
CBG-305 | Set up digital onboarding journey for savings accounts | Done | Medium | Ananya | Digital Channels | Sprint 12 | Digital Onboarding | 8 | 8 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-11 | Yes |  |  | 1
CBG-306 | Build MI reporting template for branch performance | Done | Medium | Rohit | Digital Channels | Sprint 12 | MI Reporting | 5 | 5 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-09 | Yes |  |  | 1
CBG-307 | Document API gateway integration specs for LOS | Done | High | Priya | Retail Lending | Sprint 12 | API Gateway | 5 | 5 | 2026-03-03 | 2026-03-08 | 2026-03-03 | 2026-03-07 | No |  |  | 1
CBG-308 | Configure nightly batch processing for loan repayments | Done | High | Arjun | Retail Lending | Sprint 12 | Personal Loan Servicing | 8 | 8 | 2026-03-02 | 2026-03-04 | 2026-03-03 | 2026-03-05 | Yes |  | CBG-302 | 1
CBG-309 | Integrate core banking system with credit card platform | Done | Medium | Karthik | Wealth & Cards | Sprint 12 | Branch Integration | 5 | 5 | 2026-03-09 | 2026-03-13 | 2026-03-11 | 2026-03-12 | No |  | CBG-304 | 2
CBG-310 | Build customer data platform ingestion pipeline | Done | Medium | Meena | Wealth & Cards | Sprint 12 | Customer Data Platform | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-11 | 2026-03-15 | Yes |  |  | 2
CBG-311 | Design regulatory reporting template for RBI returns | Done | Critical | Karthik | Wealth & Cards | Sprint 12 | Regulatory Reporting | 3 | 3 | 2026-03-10 | 2026-03-12 | 2026-03-11 | 2026-03-10 | No |  | CBG-303 | 2
CBG-312 | Build QA scorecard for KYC audit readiness | Done | Medium | Sunil | KYC & Onboarding | Sprint 12 | KYC Compliance | 8 | 8 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-14 | Yes |  |  | 2
CBG-313 | Configure branch integration middleware for CBS | Done | High | Divya | KYC & Onboarding | Sprint 12 | Branch Integration | 5 | 5 | 2026-03-11 | 2026-03-13 | 2026-03-10 | 2026-03-13 | No |  |  | 2
CBG-314 | Deploy automated compliance check for AML alerts | Done | High | Rohit | Digital Channels | Sprint 12 | Regulatory Reporting | 5 | 5 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-10 | No |  |  | 2
CBG-315 | Design IVR routing logic for loan collections calls | Done | High | Ananya | Digital Channels | Sprint 12 | Digital Onboarding | 3 | 3 | 2026-03-08 | 2026-03-13 | 2026-03-10 | 2026-03-13 | Yes |  |  | 1
CBG-316 | Map data fields for legacy loan system migration | In Progress | High | Sunil | KYC & Onboarding | Sprint 12 | KYC Compliance | 2 | 2 | 2026-03-11 | 2026-03-13 | 2026-03-11 |  | Yes |  |  | 2
CBG-317 | Configure CBS API connection for real-time balance check | Blocked | High | Priya | Retail Lending | Sprint 12 | API Gateway | 5 | 5 | 2026-03-05 | 2026-03-10 | 2026-03-04 |  | Yes | Core Banking API unavailable — pending vendor patch |  | 1
CBG-318 | Automate regulatory MI pack distribution to RBI | Blocked | Critical | Arjun | Retail Lending | Sprint 12 | Regulatory Reporting | 3 | 3 | 2026-03-08 | 2026-03-11 | 2026-03-10 |  | Yes | Regulatory sign-off not received from Compliance team |  | 2
CBG-319 | Build loan restructuring approval workflow | To Do | Medium | Meena | Wealth & Cards | Sprint 12 | Home Loan Origination | 5 | 5 | 2026-03-12 | 2026-03-14 |  |  | No |  |  | 2
CBG-320 | Set up weekly MI pack for retail lending team | To Do | Low | Karthik | Wealth & Cards | Sprint 12 | MI Reporting | 2 | 7 | 2026-03-11 | 2026-03-13 |  |  | No |  | CBG-304 | 1
CBG-321 | Complete credit appraisal module for home loans | In Progress | Critical | Priya | Retail Lending | Sprint 13 | Home Loan Origination | 5 | 5 | 2026-03-19 | 2026-03-21 | 2026-03-19 |  | Yes |  | CBG-317 | 3
CBG-322 | Finalise personal loan disbursement workflow | In Progress | Low | Arjun | Retail Lending | Sprint 13 | Personal Loan Servicing | 3 | 3 | 2026-03-16 | 2026-03-21 | 2026-03-16 |  | Yes |  | CBG-308 | 3
CBG-323 | Build rewards point reconciliation for credit cards | Done | High | Meena | Wealth & Cards | Sprint 13 | Credit Card Operations | 8 | 8 | 2026-03-19 | 2026-03-22 | 2026-03-18 | 2026-03-21 | No |  |  | 3
CBG-324 | Implement video KYC session integration | Done | High | Divya | KYC & Onboarding | Sprint 13 | Digital Onboarding | 5 | 5 | 2026-03-16 | 2026-03-19 | 2026-03-16 | 2026-03-20 | No |  |  | 3
CBG-325 | Deploy digital account opening API for mobile app | Done | Medium | Ananya | Digital Channels | Sprint 13 | Digital Onboarding | 8 | 8 | 2026-03-22 | 2026-03-25 | 2026-03-21 | 2026-03-24 | No |  |  | 4
CBG-326 | Configure branch performance dashboard for MIS | In Progress | Medium | Rohit | Digital Channels | Sprint 13 | MI Reporting | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-20 |  | Yes |  |  | 3
CBG-327 | Integrate CDP with CRM for 360-degree customer view | Done | High | Karthik | Wealth & Cards | Sprint 13 | Customer Data Platform | 8 | 8 | 2026-03-19 | 2026-03-23 | 2026-03-20 | 2026-03-22 | No |  | CBG-310 | 4
CBG-328 | Automate RPA bot for loan data extraction from CBS | In Progress | Critical | Sunil | KYC & Onboarding | Sprint 13 | API Gateway | 5 | 5 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
CBG-329 | Map data migration schema for core banking upgrade | Done | High | Priya | Retail Lending | Sprint 13 | Branch Integration | 5 | 5 | 2026-03-20 | 2026-03-22 | 2026-03-21 | 2026-03-23 | No |  |  | 3
CBG-330 | Build real-time SLA breach alert for loans team | Done | Low | Arjun | Retail Lending | Sprint 13 | Personal Loan Servicing | 5 | 5 | 2026-03-19 | 2026-03-22 | 2026-03-18 | 2026-03-22 | No |  |  | 3
CBG-331 | Draft solution architecture for API gateway upgrade | Done | Medium | Rohit | Digital Channels | Sprint 13 | API Gateway | 8 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 | 2026-03-25 | Yes |  |  | 4
CBG-332 | Tune RPA bot for credit card data reconciliation | In Progress | Critical | Ananya | Digital Channels | Sprint 13 | Credit Card Operations | 5 | 8 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
CBG-333 | Build P2 escalation handling workflow for complaints | Done | Medium | Divya | KYC & Onboarding | Sprint 13 | KYC Compliance | 8 | 8 | 2026-03-23 | 2026-03-25 | 2026-03-23 | 2026-03-26 | Yes |  |  | 4
CBG-334 | Configure auto-dialler integration for collections | Blocked | Critical | Karthik | Wealth & Cards | Sprint 13 | Branch Integration | 5 | 5 | 2026-03-22 | 2026-03-23 | 2026-03-23 |  | Yes | Core Banking API unavailable — pending vendor patch |  | 3
CBG-335 | Automate QA audit report distribution to compliance | Blocked | Critical | Sunil | KYC & Onboarding | Sprint 13 | Regulatory Reporting | 3 | 3 | 2026-03-22 | 2026-03-23 | 2026-03-22 |  | Yes | Client-side KYC documentation not yet submitted |  | 3
CBG-336 | Build onboarding knowledge base for branch staff | Blocked | Medium | Meena | Wealth & Cards | Sprint 13 | Digital Onboarding | 3 | 3 | 2026-03-19 | 2026-03-22 | 2026-03-21 |  | Yes | UAT environment access not provisioned for team |  | 3
CBG-337 | Review architecture for CBS-LOS integration | Supervisor Review | High | Priya | Retail Lending | Sprint 13 | Branch Integration | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
CBG-338 | Validate regulatory data model for CERSAI reporting | Supervisor Review | High | Arjun | Retail Lending | Sprint 13 | Regulatory Reporting | 3 | 3 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 4
CBG-339 | Review customer data platform architecture design | Supervisor Review | Medium | Rohit | Digital Channels | Sprint 13 | Customer Data Platform | 5 | 5 | 2026-03-22 | 2026-03-24 | 2026-03-22 |  | Yes |  |  | 4
CBG-340 | Validate home loan LOS solution design for RBI pilot | Supervisor Review | High | Karthik | Wealth & Cards | Sprint 13 | Home Loan Origination | 5 | 5 | 2026-03-22 | 2026-03-25 | 2026-03-22 |  | Yes |  |  | 4
CBG-341 | Complete home loan sanction letter automation | Done | Critical | Priya | Retail Lending | Sprint 14 | Home Loan Origination | 8 | 8 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-04-02 | Yes |  | CBG-337 | 5
CBG-342 | Finalise credit card statement generation module | Done | High | Meena | Wealth & Cards | Sprint 14 | Credit Card Operations | 5 | 5 | 2026-03-30 | 2026-04-01 | 2026-03-30 | 2026-04-01 | No |  |  | 5
CBG-343 | Deploy digital KYC verification for NRI accounts | In Progress | High | Divya | KYC & Onboarding | Sprint 14 | KYC Compliance | 8 | 8 | 2026-03-30 | 2026-04-02 | 2026-03-30 |  | Yes |  |  | 5
CBG-344 | Build loan foreclosure request workflow | In Progress | High | Arjun | Retail Lending | Sprint 14 | Home Loan Origination | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  | CBG-341 | 5
CBG-345 | Configure wealth advisory dashboard for RM portal | In Progress | Medium | Karthik | Wealth & Cards | Sprint 14 | Customer Data Platform | 8 | 8 | 2026-03-30 | 2026-04-02 | 2026-03-30 |  | Yes |  |  | 5
CBG-346 | Integrate mobile banking app with loan origination system | In Progress | High | Ananya | Digital Channels | Sprint 14 | Digital Onboarding | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
CBG-347 | Build SLA monitoring dashboard for branch operations | In Progress | Medium | Rohit | Digital Channels | Sprint 14 | MI Reporting | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
CBG-348 | Configure automated NPS survey for loan customers | In Progress | Low | Priya | Retail Lending | Sprint 14 | Customer Data Platform | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CBG-349 | Tune ML model for credit risk scoring engine | In Progress | Critical | Arjun | Retail Lending | Sprint 14 | API Gateway | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CBG-350 | Build branch dashboard for daily loan pipeline view | In Progress | High | Sunil | KYC & Onboarding | Sprint 14 | Branch Integration | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CBG-351 | Design microservice architecture for payments hub | In Progress | Critical | Rohit | Digital Channels | Sprint 14 | API Gateway | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CBG-352 | Configure RBI regulatory reporting automation | Blocked | Critical | Sunil | KYC & Onboarding | Sprint 14 | Regulatory Reporting | 8 | 8 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | Regulatory sign-off not received from Compliance team | CBG-335 | 5
CBG-353 | Integrate CBS with new digital lending platform | Blocked | High | Karthik | Wealth & Cards | Sprint 14 | Branch Integration | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes | Data migration sign-off pending Risk committee approval |  | 5
CBG-354 | Deploy API gateway for open banking PSD2 compliance | Blocked | Critical | Ananya | Digital Channels | Sprint 14 | API Gateway | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Cloud infrastructure provisioning delayed by procurement |  | 6
CBG-355 | Implement customer risk profiling engine for wealth | Blocked | High | Meena | Wealth & Cards | Sprint 14 | Customer Data Platform | 8 | 8 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes | Architecture decision record awaiting CTO approval |  | 6
CBG-356 | Review solution design for home loan LOS upgrade | Supervisor Review | High | Divya | KYC & Onboarding | Sprint 14 | Home Loan Origination | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
CBG-357 | Validate data architecture for CDP rollout | Supervisor Review | High | Priya | Retail Lending | Sprint 14 | Customer Data Platform | 5 | 5 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CBG-358 | Review CERSAI integration architecture design | Supervisor Review | Medium | Arjun | Retail Lending | Sprint 14 | Regulatory Reporting | 3 | 3 | 2026-04-06 | 2026-04-08 | 2026-04-06 |  | Yes |  |  | 6
CBG-359 | Design DR strategy for digital banking platform | To Do | High | Karthik | Wealth & Cards | Sprint 14 | API Gateway | 5 | 5 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
CBG-360 | Build data lineage map for regulatory submissions | To Do | Medium | Sunil | KYC & Onboarding | Sprint 14 | Regulatory Reporting | 3 | 3 | 2026-04-08 | 2026-04-10 |  |  | No |  |  | 6
Facilitator note: Sprint 12=Done 14, InProg 2, Blocked 2, ToDo 2 (healthy). Sprint 13=Done 8, InProg 5, Blocked 3, SupRev 4 (mixed). Sprint 14=Done 3, InProg 8, Blocked 4, SupRev 3, ToDo 2 (at-risk). Status totals: Done=25, InProgress=15, Blocked=9, SupRev=7, ToDo=4 (total=60). Blocked ticket rows are amber-highlighted. Sprint 14 completion rate is <50% — must trigger Red in the scorecard. Blocker Resistance metric for radar chart must be INVERTED (fewer blockers = higher score).

## Squad Targets
Squad | Sprint | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
Retail Lending | Sprint 12 | 30 | 85 | 3
Retail Lending | Sprint 13 | 28 | 80 | 3
Retail Lending | Sprint 14 | 32 | 80 | 3
Wealth & Cards | Sprint 12 | 27 | 90 | 3
Wealth & Cards | Sprint 13 | 24 | 90 | 2
Wealth & Cards | Sprint 14 | 30 | 90 | 2
KYC & Onboarding | Sprint 12 | 28 | 80 | 3
KYC & Onboarding | Sprint 13 | 26 | 80 | 2
KYC & Onboarding | Sprint 14 | 32 | 80 | 2
Digital Channels | Sprint 12 | 28 | 90 | 2
Digital Channels | Sprint 13 | 24 | 85 | 2
Digital Channels | Sprint 14 | 30 | 90 | 2
Facilitator note: Squad Targets feed into the Radar Chart normalisation for Level 3. Velocity planned provides the denominator for velocity score. On-Time Target % is the benchmark. Max Blockers Allowed is the upper bound for Blocker Resistance inversion. Sprint 14 targets are highest but performance is worst — this is the coaching moment.

## Sprint Ceremonies
Sprint | Ceremony | Date | Key Decisions / Notes
Sprint 12 | Sprint Planning | 2026-03-02 | 20 tickets committed; 2 architecture tasks carried over from previous delivery cycle. Solution Architect confirmed API gateway design freeze.
Sprint 12 | Daily Standup Summary (Week 1) | 2026-03-06 | Retail Lending blocker on Core Banking API — Solution Architect escalated to vendor account lead for expedited patch.
Sprint 12 | Mid-Sprint Review | 2026-03-09 | 3 tickets re-estimated upward after CBS complexity surfaced; KYC & Onboarding flagged UAT environment instability impacting test cycles.
Sprint 12 | Sprint Review | 2026-03-13 | 14 of 20 tickets done; 2 blocked (CBG-317, CBG-318); 2 carried to Sprint 13. Solution Architect signed off on integration design docs.
Sprint 12 | Retrospective | 2026-03-13 | Action: improve dependency tracking across squads; Solution Architect to add architecture decision column to daily standup tracker.
Sprint 13 | Sprint Planning | 2026-03-16 | 20 tickets committed including 2 carryovers; 1 new P1 RBI compliance item added. Solution Architect confirmed bandwidth risk — one squad lead on short leave.
Sprint 13 | Daily Standup Summary (Week 1) | 2026-03-20 | Wealth & Cards ahead of schedule; KYC & Onboarding blocked on client documentation. Solution Architect reviewing CBS-LOS architecture alignment.
Sprint 13 | Mid-Sprint Review | 2026-03-23 | Client requested 2 new digital onboarding tickets mid-sprint. Solution Architect flagged scope addition risk — architecture impact assessment required before acceptance.
Sprint 13 | Sprint Review | 2026-03-27 | 14 of 20 tickets done; velocity dip noted vs Sprint 12; 4 tickets in Supervisor Review. Solution Architect escalated 3 blocked tickets to delivery head.
Sprint 13 | Retrospective | 2026-03-27 | Action: no mid-sprint scope additions without Solution Architect approval; blocker SLA set at 24 hours with daily check-in.
Sprint 14 | Sprint Planning | 2026-03-30 | 20 tickets committed; team flagged resource risk — Divya on leave week 2. Solution Architect raised architecture debt concern on API gateway design.
Sprint 14 | Daily Standup Summary (Week 1) | 2026-04-03 | 6 tickets blocked — highest blocker count across 3 sprints. Solution Architect called emergency triage with all squad leads.
Sprint 14 | Mid-Sprint Review | 2026-04-06 | Only 3 tickets done at midpoint; Solution Architect escalated to Delivery Head and Banking CTO — sprint at serious risk of carryover.
Sprint 14 | Sprint Review | 2026-04-10 | Sprint still in progress — formal review scheduled 10 April. Solution Architect preparing risk summary for Head of Digital Banking.
Facilitator note: Sprint 14 rows are amber-highlighted — these are the rows Level 3 Ceremony Insights section must pull. Reference to 'PM' must not appear — all escalations are by the Solution Architect. Sprint 14 Mid-Sprint Review row ('Only 3 tickets done at midpoint') is the key coaching moment for the session.