## Sprint Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
CF-1201 | Draft Q3 Annual Operating Plan milestone tracker | Done | High | Arjun Mehta | Strategy & Planning | 12 | Annual Operating Plan | 5 | 5 | 2025-01-06 | 2025-01-09 | 2025-01-06 | 2025-01-09 | No |  |  | 1
CF-1202 | Align cross-functional delivery timelines with HR and Finance | Done | High | Priya Nair | Strategy & Planning | 12 | Annual Operating Plan | 5 | 5 | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-10 | No |  | CF-1201 | 1
CF-1203 | Consolidate process documentation for ISO readiness review | Done | Medium | Rohan Verma | Process Excellence | 12 | Process Standardisation Programme | 4 | 4 | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-09 | No |  |  | 1
CF-1204 | Map end-to-end policy exceptions workflow for governance team | Done | High | Kiran Bhat | Governance & Risk | 12 | Policy Governance Framework | 6 | 6 | 2025-01-06 | 2025-01-10 | 2025-01-06 | 2025-01-10 | No |  |  | 1
CF-1205 | Prepare Q1 stakeholder communication calendar | Done | Medium | Siddharth Rao | Stakeholder Engagement | 12 | Stakeholder Reporting Suite | 3 | 3 | 2025-01-06 | 2025-01-09 | 2025-01-06 | 2025-01-09 | No |  |  | 1
CF-1206 | Define KPIs for process standardisation programme Phase 1 | Done | High | Sneha Iyer | Process Excellence | 12 | Process Standardisation Programme | 5 | 5 | 2025-01-07 | 2025-01-13 | 2025-01-07 | 2025-01-13 | No |  | CF-1203 | 2
CF-1207 | Review and update RACI matrix for policy governance framework | Done | Medium | Ananya Das | Governance & Risk | 12 | Policy Governance Framework | 4 | 4 | 2025-01-07 | 2025-01-14 | 2025-01-07 | 2025-01-14 | No |  | CF-1204 | 2
CF-1208 | Draft workforce planning dashboard requirements document | Done | Medium | Arjun Mehta | Strategy & Planning | 12 | Workforce Planning Initiative | 5 | 5 | 2025-01-07 | 2025-01-14 | 2025-01-07 | 2025-01-14 | No |  |  | 2
CF-1209 | Prepare executive steering committee deck for AOP sign-off | Done | High | Priya Nair | Strategy & Planning | 12 | Annual Operating Plan | 6 | 6 | 2025-01-08 | 2025-01-15 | 2025-01-08 | 2025-01-15 | No |  | CF-1201 | 2
CF-1210 | Update executive dashboard data feeds from Finance systems | Done | Medium | Meghna Pillai | Stakeholder Engagement | 12 | Executive Dashboard Rollout | 4 | 4 | 2025-01-08 | 2025-01-14 | 2025-01-08 | 2025-01-14 | No |  |  | 2
CF-1211 | Document change management impact assessment template | Done | Medium | Rohan Verma | Process Excellence | 12 | Change Management Playbook | 4 | 4 | 2025-01-09 | 2025-01-16 | 2025-01-09 | 2025-01-15 | No |  |  | 2
CF-1212 | Facilitate Q4 retrospective action log review | Done | Low | Siddharth Rao | Stakeholder Engagement | 12 | Stakeholder Reporting Suite | 3 | 3 | 2025-01-09 | 2025-01-15 | 2025-01-09 | 2025-01-15 | No |  |  | 2
CF-1213 | Consolidate budget variance report for CFO review | In Progress | High | Kiran Bhat | Governance & Risk | 12 | Budget Cycle Management | 6 | 6 | 2025-01-13 | 2025-01-17 | 2025-01-13 |  | No |  |  | 2
CF-1214 | Draft digital transformation roadmap presentation for CXO | In Progress | High | Arjun Mehta | Strategy & Planning | 12 | Digital Transformation Roadmap | 5 | 5 | 2025-01-13 | 2025-01-17 | 2025-01-13 |  | No |  |  | 2
CF-1215 | Update risk register entries for Q1 compliance audit | In Progress | Medium | Ananya Das | Governance & Risk | 12 | Risk & Compliance Audit | 4 | 4 | 2025-01-14 | 2025-01-17 | 2025-01-14 |  | No |  |  | 2
CF-1216 | Obtain CFO sign-off on revised budget assumptions | Blocked | High | Sneha Iyer | Process Excellence | 12 | Budget Cycle Management | 5 | 5 | 2025-01-13 | 2025-01-17 |  |  | Yes | Awaiting CFO approval — sign-off meeting rescheduled | CF-1213 | 2
CF-1217 | Finalise GDPR data handling addendum for vendor contracts | Blocked | High | Kiran Bhat | Governance & Risk | 12 | Policy Governance Framework | 4 | 4 | 2025-01-14 | 2025-01-17 |  |  | Yes | Legal team review pending — contract redline not returned | CF-1204 | 2
CF-1218 | Review draft workforce planning model assumptions | Supervisor Review | Medium | Meghna Pillai | Stakeholder Engagement | 12 | Workforce Planning Initiative | 4 | 4 | 2025-01-13 | 2025-01-17 | 2025-01-13 |  | No |  | CF-1208 | 2
CF-1219 | Submit Q1 risk & compliance readiness report for sign-off | Supervisor Review | High | Priya Nair | Strategy & Planning | 12 | Risk & Compliance Audit | 5 | 5 | 2025-01-14 | 2025-01-17 | 2025-01-14 |  | No |  | CF-1215 | 2
CF-1220 | Design quarterly business review (QBR) scorecard template | To Do | Medium | Rohan Verma | Process Excellence | 12 | Stakeholder Reporting Suite | 3 | 3 | 2025-01-16 | 2025-01-17 |  |  | No |  |  | 2
CF-1301 | Publish Digital Transformation Roadmap v1.0 to SharePoint | Done | High | Arjun Mehta | Strategy & Planning | 13 | Digital Transformation Roadmap | 6 | 6 | 2025-01-20 | 2025-01-24 | 2025-01-20 | 2025-01-23 | No |  | CF-1214 | 3
CF-1302 | Validate workforce planning headcount assumptions with HR | Done | High | Priya Nair | Strategy & Planning | 13 | Workforce Planning Initiative | 5 | 5 | 2025-01-20 | 2025-01-24 | 2025-01-20 | 2025-01-24 | No |  | CF-1208 | 3
CF-1303 | Baseline process maturity scores for all four operational teams | Done | Medium | Rohan Verma | Process Excellence | 13 | Process Standardisation Programme | 5 | 5 | 2025-01-20 | 2025-01-24 | 2025-01-20 | 2025-01-23 | No |  | CF-1206 | 3
CF-1304 | Draft Q1 governance exceptions summary report | Done | Medium | Kiran Bhat | Governance & Risk | 13 | Policy Governance Framework | 4 | 4 | 2025-01-20 | 2025-01-23 | 2025-01-20 | 2025-01-22 | No |  | CF-1207 | 3
CF-1305 | Complete stakeholder engagement plan for change mgmt programme | Done | High | Siddharth Rao | Stakeholder Engagement | 13 | Change Management Playbook | 5 | 5 | 2025-01-21 | 2025-01-28 | 2025-01-21 | 2025-01-28 | No |  | CF-1211 | 4
CF-1306 | Finalise executive dashboard layout and KPI definitions | Done | High | Meghna Pillai | Stakeholder Engagement | 13 | Executive Dashboard Rollout | 6 | 6 | 2025-01-21 | 2025-01-28 | 2025-01-21 | 2025-01-27 | No |  | CF-1210 | 4
CF-1307 | Conduct mid-year budget reforecast data collection | Done | Medium | Ananya Das | Governance & Risk | 13 | Budget Cycle Management | 5 | 5 | 2025-01-22 | 2025-01-29 | 2025-01-22 | 2025-01-29 | No |  | CF-1213 | 4
CF-1308 | Prepare QBR deck for Strategy & Planning squad | Done | Medium | Sneha Iyer | Process Excellence | 13 | Stakeholder Reporting Suite | 4 | 4 | 2025-01-22 | 2025-01-29 | 2025-01-22 | 2025-01-28 | No |  | CF-1220 | 4
CF-1309 | Develop automated reporting pipeline for executive dashboard | In Progress | High | Arjun Mehta | Strategy & Planning | 13 | Executive Dashboard Rollout | 6 | 6 | 2025-01-27 | 2025-01-31 | 2025-01-27 |  | No |  | CF-1306 | 4
CF-1310 | Implement feedback loop from QBR into AOP tracker | In Progress | Medium | Priya Nair | Strategy & Planning | 13 | Annual Operating Plan | 5 | 5 | 2025-01-27 | 2025-01-31 | 2025-01-27 |  | No |  | CF-1209 | 4
CF-1311 | Review risk controls adequacy against updated compliance framework | In Progress | High | Kiran Bhat | Governance & Risk | 13 | Risk & Compliance Audit | 5 | 5 | 2025-01-27 | 2025-01-31 | 2025-01-27 |  | No |  | CF-1215 | 4
CF-1312 | Document Lean process improvement recommendations for PS programme | In Progress | Medium | Rohan Verma | Process Excellence | 13 | Process Standardisation Programme | 4 | 4 | 2025-01-27 | 2025-01-31 | 2025-01-27 |  | No |  | CF-1303 | 4
CF-1313 | Prepare Workforce Planning Initiative business case | In Progress | High | Sneha Iyer | Process Excellence | 13 | Workforce Planning Initiative | 5 | 5 | 2025-01-28 | 2025-01-31 | 2025-01-28 |  | No |  | CF-1302 | 4
CF-1314 | Draft change management communications for Phase 2 rollout | In Progress | Medium | Siddharth Rao | Stakeholder Engagement | 13 | Change Management Playbook | 4 | 4 | 2025-01-28 | 2025-01-31 | 2025-01-28 |  | No |  | CF-1305 | 4
CF-1315 | Obtain HR data freeze confirmation for headcount planning | Blocked | High | Meghna Pillai | Stakeholder Engagement | 13 | Workforce Planning Initiative | 5 | 5 | 2025-01-27 | 2025-01-31 |  |  | Yes | HR data freeze not confirmed — HRIS system update in progress | CF-1302 | 4
CF-1316 | Resolve data quality issues in Finance ERP extract | Blocked | High | Ananya Das | Governance & Risk | 13 | Budget Cycle Management | 5 | 5 | 2025-01-27 | 2025-01-31 |  |  | Yes | Finance ERP data reconciliation blocked — awaiting IT ticket resolution | CF-1307 | 4
CF-1317 | Complete external audit evidence pack for Q1 compliance | Blocked | High | Kiran Bhat | Governance & Risk | 13 | Risk & Compliance Audit | 6 | 6 | 2025-01-28 | 2025-01-31 |  |  | Yes | External auditor availability clash — rescheduled to Sprint 14 | CF-1311 | 4
CF-1318 | Review digital transformation initiative cost-benefit analysis | Supervisor Review | High | Priya Nair | Strategy & Planning | 13 | Digital Transformation Roadmap | 5 | 5 | 2025-01-28 | 2025-01-31 | 2025-01-28 |  | No |  | CF-1309 | 4
CF-1319 | Approve Q1 governance framework exception register | Supervisor Review | Medium | Rohan Verma | Process Excellence | 13 | Policy Governance Framework | 4 | 4 | 2025-01-29 | 2025-01-31 | 2025-01-29 |  | No |  | CF-1304 | 4
CF-1320 | Define onboarding process improvements for new joiners | To Do | Low | Siddharth Rao | Stakeholder Engagement | 13 | Change Management Playbook | 3 | 3 | 2025-01-30 | 2025-01-31 |  |  | No |  |  | 4
CF-1401 | Publish Q1 compliance audit findings report | Done | High | Ananya Das | Governance & Risk | 14 | Risk & Compliance Audit | 5 | 5 | 2025-02-03 | 2025-02-07 | 2025-02-03 | 2025-02-06 | No |  | CF-1317 | 5
CF-1402 | Complete executive dashboard UAT with senior leadership | Done | High | Meghna Pillai | Stakeholder Engagement | 14 | Executive Dashboard Rollout | 6 | 6 | 2025-02-03 | 2025-02-07 | 2025-02-03 | 2025-02-07 | No |  | CF-1306 | 5
CF-1403 | Finalise AOP tracker with approved headcount numbers | Done | High | Arjun Mehta | Strategy & Planning | 14 | Annual Operating Plan | 5 | 5 | 2025-02-03 | 2025-02-07 | 2025-02-03 | 2025-02-06 | No |  | CF-1310 | 5
CF-1404 | Document process standardisation baseline metrics | Done | Medium | Rohan Verma | Process Excellence | 14 | Process Standardisation Programme | 4 | 4 | 2025-02-04 | 2025-02-10 | 2025-02-04 | 2025-02-10 | No |  | CF-1312 | 6
CF-1405 | Deliver Workforce Planning Initiative business case to ExCo | Done | High | Sneha Iyer | Process Excellence | 14 | Workforce Planning Initiative | 5 | 5 | 2025-02-04 | 2025-02-10 | 2025-02-04 | 2025-02-09 | No |  | CF-1313 | 6
CF-1406 | Build automated variance tracking model in Excel for AOP | In Progress | High | Priya Nair | Strategy & Planning | 14 | Annual Operating Plan | 6 | 6 | 2025-02-10 | 2025-02-14 | 2025-02-10 |  | No |  | CF-1403 | 6
CF-1407 | Develop risk appetite statement for updated governance framework | In Progress | High | Kiran Bhat | Governance & Risk | 14 | Policy Governance Framework | 5 | 5 | 2025-02-10 | 2025-02-14 | 2025-02-10 |  | No |  | CF-1304 | 6
CF-1408 | Draft Phase 2 change management training materials | In Progress | Medium | Siddharth Rao | Stakeholder Engagement | 14 | Change Management Playbook | 4 | 4 | 2025-02-10 | 2025-02-14 | 2025-02-10 |  | No |  | CF-1314 | 6
CF-1409 | Prepare mid-year reforecast summary for Board presentation | In Progress | High | Ananya Das | Governance & Risk | 14 | Budget Cycle Management | 6 | 6 | 2025-02-10 | 2025-02-14 | 2025-02-10 |  | No |  | CF-1316 | 6
CF-1410 | Integrate stakeholder feedback into digital transformation roadmap v2 | In Progress | Medium | Arjun Mehta | Strategy & Planning | 14 | Digital Transformation Roadmap | 5 | 5 | 2025-02-11 | 2025-02-14 | 2025-02-11 |  | No |  | CF-1318 | 6
CF-1411 | Complete process improvement pilot for PS programme — Phase 2 | In Progress | Medium | Rohan Verma | Process Excellence | 14 | Process Standardisation Programme | 4 | 4 | 2025-02-11 | 2025-02-14 | 2025-02-11 |  | No |  | CF-1404 | 6
CF-1412 | Obtain Group Legal sign-off on revised vendor contract templates | Blocked | High | Kiran Bhat | Governance & Risk | 14 | Policy Governance Framework | 5 | 5 | 2025-02-10 | 2025-02-14 |  |  | Yes | Group Legal review stalled — senior counsel on leave until Feb 17 | CF-1407 | 6
CF-1413 | Resolve HRIS integration error blocking headcount data feed | Blocked | High | Priya Nair | Strategy & Planning | 14 | Workforce Planning Initiative | 5 | 5 | 2025-02-10 | 2025-02-14 |  |  | Yes | HRIS API integration broken — IT escalation raised by Product Manager, ETA unknown | CF-1315 | 6
CF-1414 | Complete Finance ERP reconciliation for reforecast model | Blocked | High | Ananya Das | Governance & Risk | 14 | Budget Cycle Management | 6 | 6 | 2025-02-10 | 2025-02-14 |  |  | Yes | ERP data extract failing — cross-team dependency on Finance IT patch deployment | CF-1409 | 6
CF-1415 | Submit updated external audit evidence pack for Q1 | Blocked | High | Sneha Iyer | Process Excellence | 14 | Risk & Compliance Audit | 5 | 5 | 2025-02-10 | 2025-02-14 |  |  | Yes | External auditor portal access issue — Product Manager escalated to vendor support | CF-1401 | 6
CF-1416 | Review and approve Change Management Phase 2 delivery plan | Supervisor Review | High | Meghna Pillai | Stakeholder Engagement | 14 | Change Management Playbook | 5 | 5 | 2025-02-11 | 2025-02-14 | 2025-02-11 |  | Yes |  | CF-1408 | 6
CF-1417 | Review Budget Cycle Management mid-year reforecast assumptions | Supervisor Review | High | Siddharth Rao | Stakeholder Engagement | 14 | Budget Cycle Management | 5 | 5 | 2025-02-11 | 2025-02-14 | 2025-02-11 |  | Yes |  | CF-1409 | 6
CF-1418 | Approve Digital Transformation Roadmap v2 for stakeholder distribution | Supervisor Review | High | Arjun Mehta | Strategy & Planning | 14 | Digital Transformation Roadmap | 5 | 5 | 2025-02-12 | 2025-02-14 | 2025-02-12 |  | Yes |  | CF-1410 | 6
CF-1419 | Design post-implementation review framework for AOP cycle | To Do | Medium | Priya Nair | Strategy & Planning | 14 | Annual Operating Plan | 4 | 4 | 2025-02-13 | 2025-02-14 |  |  | No |  | CF-1406 | 6
CF-1420 | Draft lessons-learned report for Sprints 12-14 programme cycle | To Do | Low | Rohan Verma | Process Excellence | 14 | Change Management Playbook | 3 | 3 | 2025-02-13 | 2025-02-14 |  |  | No |  |  | 6
FACILITATOR NOTE — Sheet 1 Sprint Backlog: Status totals Done=25 ¦ In Progress=15 ¦ Blocked=9 ¦ Supervisor Review=7 ¦ To Do=4. Sprint 14 has the most blockers (4) and lowest completion (5 done). Blocker rows shaded red. Weeks 1-2 = Sprint 12, Weeks 3-4 = Sprint 13, Weeks 5-6 = Sprint 14.

## Squad Targets
Squad | Sprint | Planned Velocity (pts) | On-Time Target % | Max Blockers Allowed
Strategy & Planning | 12 | 20 | 85% | 2
Process Excellence | 12 | 20 | 85% | 2
Governance & Risk | 12 | 20 | 85% | 2
Stakeholder Engagement | 12 | 20 | 85% | 2
Strategy & Planning | 13 | 20 | 85% | 2
Process Excellence | 13 | 20 | 85% | 2
Governance & Risk | 13 | 20 | 85% | 2
Stakeholder Engagement | 13 | 20 | 85% | 2
Strategy & Planning | 14 | 20 | 85% | 2
Process Excellence | 14 | 20 | 85% | 2
Governance & Risk | 14 | 20 | 85% | 2
Stakeholder Engagement | 14 | 20 | 85% | 2
FACILITATOR NOTE — Squad Targets: All squads share the same 85% on-time target and max 2 blockers per sprint. Sprint 14 rows (amber) are where performance falls below target in the VBA scorecard. Planned Velocity 20 pts × 4 squads = 80 pts total per sprint.

## Sprint Ceremonies
Sprint | Ceremony | Date | Attendees | Key Outcomes | Action Owner | Notes
12 | Sprint Planning | 2025-01-06 | All 4 squads, Product Manager, Delivery Lead | Backlog groomed; 20 tickets allocated; priorities set for AOP & Policy Governance workstreams | Product Manager | Capacity confirmed; GDPR addendum risk flagged as potential blocker
12 | Daily Standup Summary (Week 1) | 2025-01-10 | Strategy & Planning, Process Excellence squads | Week 1 velocity on track; 5 tickets closed; no blockers raised | Squad Leads | Governance & Risk squad flagged legal review dependency; tracked in risk log
12 | Mid-Sprint Review | 2025-01-14 | All 4 squads, Product Manager, Senior Stakeholders | 12 tickets done; 2 blockers active (Budget sign-off, Legal review); burndown ahead of ideal | Product Manager | CFO sign-off delayed by 3 days; Product Manager to re-prioritise CF-1216
12 | Sprint Review | 2025-01-17 | All 4 squads, Product Manager, Sponsor | Sprint 12 complete: 12 Done, 3 In Progress, 2 Blocked, 2 Supervisor Review; velocity 50/80 pts | Product Manager | 2 blockers carried to Sprint 13; stakeholders satisfied with AOP milestone tracker delivery
12 | Retrospective | 2025-01-17 | All 4 squads, Product Manager | Went well: early alignment on AOP; Improve: legal dependency management; Try: weekly pre-blocker check | Product Manager | Action: Product Manager to introduce weekly dependency review in Sprint 13
13 | Sprint Planning | 2025-01-20 | All 4 squads, Product Manager, Delivery Lead | Sprint 13 scope agreed; 3 carry-over blockers included; Digital Transformation Roadmap v1.0 prioritised | Product Manager | HR data freeze risk escalated; ERP data quality issue added to watch list
13 | Daily Standup Summary (Week 3) | 2025-01-24 | Governance & Risk, Stakeholder Engagement squads | 8 tickets closed in first two weeks; ERP blocker unresolved; audit evidence pack dependency identified | Squad Leads | Product Manager raised HRIS and ERP issues with IT leadership; resolution ETA pending
13 | Mid-Sprint Review | 2025-01-28 | All 4 squads, Product Manager, Finance Lead | 3 new blockers raised; burndown diverging from ideal; Sprint 14 risk of under-delivery identified | Product Manager | Product Manager escalated HR and Finance blockers to Programme Director
13 | Sprint Review | 2025-01-31 | All 4 squads, Product Manager, Sponsor, Programme Director | Sprint 13: 8 Done, 6 In Progress, 3 Blocked, 2 Supervisor Review; on-time rate 61%; below 85% target | Product Manager | 3 blockers unresolved; formal risk escalation logged; Sprint 14 scope descoped to protect delivery
13 | Retrospective | 2025-01-31 | All 4 squads, Product Manager | Went well: Exec Dashboard UAT approved; Improve: ERP data dependencies; Try: blocker SLA tracking | Product Manager | Action: Product Manager to define blocker resolution SLA process before Sprint 14 starts
14 | Sprint Planning | 2025-02-03 | All 4 squads, Product Manager, Programme Director | Reduced scope sprint; 5 priority tickets descoped; 4 carry-over blockers included from Sprint 13 | Product Manager | Product Manager flagged delivery risk to ExCo; sprint scope reduced by agreement
14 | Daily Standup Summary (Week 5) | 2025-02-07 | All 4 squads, Product Manager | 5 tickets closed in first two weeks; 4 active blockers showing no movement; burndown significantly behind ideal | Product Manager | Product Manager formally escalated HRIS and ERP blockers to CTO and CFO respectively
14 | Mid-Sprint Review | 2025-02-11 | All 4 squads, Product Manager, CTO, CFO, Programme Director | Blockers unresolved; 3 tickets in Supervisor Review; Product Manager requested emergency governance intervention | Product Manager | CTO and CFO committed to resolution by Feb 14; Product Manager tracking daily; sprint completion at risk
14 | Sprint Review | 2025-02-14 | All 4 squads, Product Manager, ExCo Sponsor, Programme Director | Sprint 14: 5 Done, 6 In Progress, 4 Blocked, 3 Supervisor Review, 2 To Do; on-time rate 32%; red status | Product Manager | Product Manager presented formal programme health report to ExCo; recovery sprint planned for week 7-8
FACILITATOR NOTE — Sprint Ceremonies: Sprint 14 rows are amber/red. The Product Manager is the escalation owner throughout — critical for Level 3 Ceremony Insights section. Sprint 14 Review (row 15) should show on-time rate 32% and Red status. Action Owner column confirms Product Manager drove all escalations.