## Sprint Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
TEL-0001 | Configure 5G SA core UPF nodes for Circle South | To Do | Low | Ravi Shankar | Network Operations | Sprint 12 | 5G Core Network Rollout | 8 | 8 | 2025-03-03 | 2025-03-09 |  |  | No |  |  | 1
TEL-0002 | Migrate legacy mediation layer to cloud-native stack | Done | Medium | Arun Patel | Service Assurance | Sprint 12 | OSS/BSS Platform Migration | 3 | 3 | 2025-03-10 | 2025-03-11 | 2025-03-09 | 2025-03-13 | Yes |  |  | 2
TEL-0003 | Analyse VoLTE call-drop heatmaps for Tier-1 cities | In Progress | Critical | Suresh Babu | Customer Experience | Sprint 12 | VoLTE Quality Enhancement | 5 | 1 | 2025-03-04 | 2025-03-06 | 2025-03-05 |  | Yes |  |  | 1
TEL-0004 | Track fibre splice completion rate across 12 districts | Done | Medium | Karthik Nair | Infrastructure Planning | Sprint 12 | Fibre-to-the-Home Expansion | 5 | 5 | 2025-03-12 | 2025-03-15 | 2025-03-13 | 2025-03-14 | No |  |  | 2
TEL-0005 | Define network slice SLA template for enterprise clients | Done | Critical | Meena Iyer | Network Operations | Sprint 12 | Network Slicing Configuration | 8 | 8 | 2025-03-03 | 2025-03-09 | 2025-03-04 | 2025-03-09 | No |  |  | 1
TEL-0006 | Automate enterprise SIM activation workflow | Done | High | Divya Krishnan | Service Assurance | Sprint 12 | Customer Onboarding Automation | 3 | 3 | 2025-03-11 | 2025-03-13 | 2025-03-12 | 2025-03-13 | No |  |  | 2
TEL-0007 | Model interference impact of 2100 MHz refarming in Zone A | In Progress | Low | Priya Venkat | Customer Experience | Sprint 12 | Spectrum Refarming Programme | 8 | 5 | 2025-03-03 | 2025-03-07 | 2025-03-04 |  | Yes |  |  | 1
TEL-0008 | Build automated SLA breach alerting dashboard | Supervisor Review | Medium | Lakshmi Rao | Infrastructure Planning | Sprint 12 | SLA Compliance Monitoring | 5 | 5 | 2025-03-10 | 2025-03-12 | 2025-03-11 |  | Yes |  |  | 2
TEL-0009 | Provision MEC nodes at 5 metro cell sites | Done | Critical | Ravi Shankar | Network Operations | Sprint 12 | Edge Computing Deployment | 3 | 3 | 2025-03-04 | 2025-03-06 | 2025-03-05 | 2025-03-08 | Yes |  |  | 1
TEL-0010 | Implement lawful intercept v3.1 upgrade across all MSCs | Done | Medium | Arun Patel | Service Assurance | Sprint 12 | Regulatory Compliance Upgrade | 3 | 3 | 2025-03-10 | 2025-03-11 | 2025-03-11 | 2025-03-12 | Yes |  |  | 2
TEL-0011 | Validate N2/N3 interface handover latency thresholds | Blocked | Critical | Suresh Babu | Customer Experience | Sprint 12 | 5G Core Network Rollout | 8 | 8 | 2025-03-05 | 2025-03-10 | 2025-03-06 |  | Yes | Regulatory approval pending from TRAI | TEL-0015 | 1
TEL-0012 | Validate billing reconciliation post-migration Sprint 12 | Done | High | Karthik Nair | Infrastructure Planning | Sprint 12 | OSS/BSS Platform Migration | 3 | 3 | 2025-03-11 | 2025-03-12 | 2025-03-10 | 2025-03-11 | No |  |  | 2
TEL-0013 | Implement codec fallback logic for low-signal zones | Done | Critical | Meena Iyer | Network Operations | Sprint 12 | VoLTE Quality Enhancement | 3 | 3 | 2025-03-03 | 2025-03-06 | 2025-03-03 | 2025-03-05 | No |  |  | 1
TEL-0014 | Resolve municipal permit backlog for last-mile trenching | Done | High | Divya Krishnan | Service Assurance | Sprint 12 | Fibre-to-the-Home Expansion | 5 | 5 | 2025-03-12 | 2025-03-15 | 2025-03-13 | 2025-03-16 | Yes |  |  | 2
TEL-0015 | Test eMBB slice throughput under peak-hour conditions | Done | Low | Priya Venkat | Customer Experience | Sprint 12 | Network Slicing Configuration | 8 | 8 | 2025-03-05 | 2025-03-11 | 2025-03-04 | 2025-03-12 | Yes |  |  | 1
TEL-0016 | Integrate eKYC API with CRM for zero-touch onboarding | In Progress | Medium | Lakshmi Rao | Infrastructure Planning | Sprint 12 | Customer Onboarding Automation | 13 | 2 | 2025-03-10 | 2025-03-17 | 2025-03-11 |  | Yes |  |  | 2
TEL-0017 | Coordinate refarming schedule with transmission planning | Done | High | Ravi Shankar | Network Operations | Sprint 12 | Spectrum Refarming Programme | 3 | 3 | 2025-03-03 | 2025-03-06 | 2025-03-04 | 2025-03-07 | Yes |  |  | 1
TEL-0018 | Audit P1 incident resolution times for Q1 compliance | Done | Medium | Arun Patel | Service Assurance | Sprint 12 | SLA Compliance Monitoring | 8 | 8 | 2025-03-12 | 2025-03-16 | 2025-03-13 | 2025-03-17 | Yes |  |  | 2
TEL-0019 | Validate edge application latency for gaming partner PoC | Done | Critical | Suresh Babu | Customer Experience | Sprint 12 | Edge Computing Deployment | 13 | 13 | 2025-03-05 | 2025-03-13 | 2025-03-04 | 2025-03-13 | No |  |  | 1
TEL-0020 | Prepare TRAI QoS quarterly report dataset | Done | Medium | Karthik Nair | Infrastructure Planning | Sprint 12 | Regulatory Compliance Upgrade | 5 | 5 | 2025-03-12 | 2025-03-16 | 2025-03-11 | 2025-03-17 | Yes |  |  | 2
TEL-0021 | Update programme milestone tracker for Phase 2 go-live | Blocked | High | Ravi Shankar | Network Operations | Sprint 13 | 5G Core Network Rollout | 5 | 5 | 2025-03-17 | 2025-03-20 | 2025-03-18 |  | Yes | Spectrum allocation conflict | TEL-0016 | 3
TEL-0022 | Coordinate UAT sign-off with revenue assurance team | In Progress | High | Arun Patel | Service Assurance | Sprint 13 | OSS/BSS Platform Migration | 2 | 1 | 2025-03-24 | 2025-03-25 | 2025-03-26 |  | Yes |  |  | 4
TEL-0023 | Prepare VoLTE KPI improvement report for steering committee | Done | Low | Suresh Babu | Customer Experience | Sprint 13 | VoLTE Quality Enhancement | 5 | 5 | 2025-03-19 | 2025-03-21 | 2025-03-18 | 2025-03-23 | Yes |  |  | 3
TEL-0024 | Update FTTH rollout Gantt chart for board review | In Progress | Medium | Karthik Nair | Infrastructure Planning | Sprint 13 | Fibre-to-the-Home Expansion | 8 | 6 | 2025-03-26 | 2025-04-01 | 2025-03-27 |  | Yes |  |  | 4
TEL-0025 | Document URLLC slice config for manufacturing IoT pilot | In Progress | Critical | Meena Iyer | Network Operations | Sprint 13 | Network Slicing Configuration | 3 | 2 | 2025-03-18 | 2025-03-20 | 2025-03-20 |  | Yes |  |  | 3
TEL-0026 | Track onboarding TAT reduction against quarterly target | Supervisor Review | Medium | Divya Krishnan | Service Assurance | Sprint 13 | Customer Onboarding Automation | 8 | 8 | 2025-03-25 | 2025-03-31 | 2025-03-26 |  | Yes |  |  | 4
TEL-0027 | Track spectrum refarming completion across 8 circles | Done | Medium | Priya Venkat | Customer Experience | Sprint 13 | Spectrum Refarming Programme | 2 | 2 | 2025-03-17 | 2025-03-18 | 2025-03-17 | 2025-03-17 | No |  |  | 3
TEL-0028 | Coordinate SLA penalty review with enterprise contracts team | In Progress | Medium | Lakshmi Rao | Infrastructure Planning | Sprint 13 | SLA Compliance Monitoring | 8 | 3 | 2025-03-26 | 2025-03-30 | 2025-03-26 |  | Yes |  |  | 4
TEL-0029 | Coordinate edge security policy with InfoSec team | Done | Critical | Ravi Shankar | Network Operations | Sprint 13 | Edge Computing Deployment | 2 | 2 | 2025-03-19 | 2025-03-20 | 2025-03-18 | 2025-03-19 | No |  |  | 3
TEL-0030 | Coordinate EMF audit schedule with circle compliance leads | Supervisor Review | Medium | Arun Patel | Service Assurance | Sprint 13 | Regulatory Compliance Upgrade | 2 | 2 | 2025-03-24 | 2025-03-27 | 2025-03-24 |  | Yes |  |  | 4
TEL-0031 | Coordinate RAN-core integration test window with vendor | Done | Critical | Suresh Babu | Customer Experience | Sprint 13 | 5G Core Network Rollout | 5 | 5 | 2025-03-18 | 2025-03-20 | 2025-03-19 | 2025-03-20 | No |  |  | 3
TEL-0032 | Update OSS cutover runbook with rollback checkpoints | Done | High | Karthik Nair | Infrastructure Planning | Sprint 13 | OSS/BSS Platform Migration | 8 | 8 | 2025-03-26 | 2025-03-31 | 2025-03-25 | 2025-04-02 | Yes |  |  | 4
TEL-0033 | Coordinate IMS node patching with change advisory board | Done | High | Meena Iyer | Network Operations | Sprint 13 | VoLTE Quality Enhancement | 13 | 13 | 2025-03-17 | 2025-03-23 | 2025-03-16 | 2025-03-25 | Yes |  |  | 3
TEL-0034 | Coordinate CPE procurement with logistics partner | In Progress | High | Divya Krishnan | Service Assurance | Sprint 13 | Fibre-to-the-Home Expansion | 5 | 1 | 2025-03-25 | 2025-03-29 | 2025-03-25 |  | Yes |  |  | 4
TEL-0035 | Coordinate slice orchestration demo for key accounts team | Blocked | High | Priya Venkat | Customer Experience | Sprint 13 | Network Slicing Configuration | 8 | 8 | 2025-03-17 | 2025-03-22 | 2025-03-18 |  | Yes | Fibre route permit held by municipal authority | TEL-0052 | 3
TEL-0036 | Fix order-fallout loop in self-service provisioning portal | Done | Low | Lakshmi Rao | Infrastructure Planning | Sprint 13 | Customer Onboarding Automation | 13 | 13 | 2025-03-24 | 2025-03-30 | 2025-03-23 | 2025-04-01 | Yes |  |  | 4
TEL-0037 | Prepare regulatory compliance dossier for DoT submission | Blocked | Critical | Ravi Shankar | Network Operations | Sprint 13 | Spectrum Refarming Programme | 3 | 3 | 2025-03-17 | 2025-03-19 | 2025-03-18 |  | Yes | Vendor firmware update delayed | TEL-0016 | 3
TEL-0038 | Track mean-time-to-restore trend for fibre backbone | To Do | Low | Arun Patel | Service Assurance | Sprint 13 | SLA Compliance Monitoring | 13 | 13 | 2025-03-25 | 2025-04-02 |  |  | No |  |  | 4
TEL-0039 | Track MEC hardware delivery against project baseline | Done | Low | Suresh Babu | Customer Experience | Sprint 13 | Edge Computing Deployment | 2 | 2 | 2025-03-19 | 2025-03-22 | 2025-03-18 | 2025-03-21 | No |  |  | 3
TEL-0040 | Update CDR retention policy per latest DoT directive | Supervisor Review | Medium | Karthik Nair | Infrastructure Planning | Sprint 13 | Regulatory Compliance Upgrade | 13 | 13 | 2025-03-24 | 2025-03-31 | 2025-03-25 |  | Yes |  |  | 4
TEL-0041 | Draft 5G core capacity forecast for next 2 quarters | In Progress | High | Ravi Shankar | Network Operations | Sprint 14 | 5G Core Network Rollout | 5 | 3 | 2025-03-31 | 2025-04-02 | 2025-04-01 |  | Yes |  |  | 5
TEL-0042 | Track BSS API gateway latency regression from v3.2 upgrade | Done | High | Arun Patel | Service Assurance | Sprint 14 | OSS/BSS Platform Migration | 2 | 2 | 2025-04-08 | 2025-04-10 | 2025-04-08 | 2025-04-12 | Yes |  |  | 6
TEL-0043 | Validate E2E VoLTE call setup time against SLA baseline | To Do | Critical | Suresh Babu | Customer Experience | Sprint 14 | VoLTE Quality Enhancement | 8 | 8 | 2025-04-02 | 2025-04-08 |  |  | No |  |  | 5
TEL-0044 | Validate GPON OLT activation schedule against plan | Done | High | Karthik Nair | Infrastructure Planning | Sprint 14 | Fibre-to-the-Home Expansion | 8 | 8 | 2025-04-07 | 2025-04-11 | 2025-04-07 | 2025-04-11 | No |  |  | 6
TEL-0045 | Review resource allocation model for mMTC slice | Blocked | High | Meena Iyer | Network Operations | Sprint 14 | Network Slicing Configuration | 2 | 2 | 2025-04-02 | 2025-04-04 | 2025-04-02 |  | Yes | Core network freeze window active | TEL-0004 | 5
TEL-0046 | Validate bulk-activation API for MVNO partner launch | In Progress | High | Divya Krishnan | Service Assurance | Sprint 14 | Customer Onboarding Automation | 8 | 4 | 2025-04-09 | 2025-04-13 | 2025-04-09 |  | No |  |  | 6
TEL-0047 | Validate coverage prediction after 900 MHz re-assignment | Blocked | High | Priya Venkat | Customer Experience | Sprint 14 | Spectrum Refarming Programme | 8 | 8 | 2025-03-31 | 2025-04-04 | 2025-03-31 |  | Yes | Regulatory approval pending from TRAI | TEL-0044 | 5
TEL-0048 | Validate SLA report data against NOC ticketing system | In Progress | High | Lakshmi Rao | Infrastructure Planning | Sprint 14 | SLA Compliance Monitoring | 13 | 9 | 2025-04-07 | 2025-04-15 | 2025-04-07 |  | No |  |  | 6
TEL-0049 | Prepare edge computing business case for CFO review | Blocked | High | Ravi Shankar | Network Operations | Sprint 14 | Edge Computing Deployment | 8 | 8 | 2025-04-02 | 2025-04-06 | 2025-04-03 |  | Yes | Awaiting NOC from tower company | TEL-0043 | 5
TEL-0050 | Validate number portability SLA adherence for regulator | Blocked | Critical | Arun Patel | Service Assurance | Sprint 14 | Regulatory Compliance Upgrade | 8 | 8 | 2025-04-08 | 2025-04-12 | 2025-04-09 |  | Yes | Third-party SLA breach under investigation | TEL-0016 | 6
TEL-0051 | Review UDM provisioning backlog with delivery team | In Progress | Medium | Suresh Babu | Customer Experience | Sprint 14 | 5G Core Network Rollout | 5 | 1 | 2025-04-02 | 2025-04-06 | 2025-04-03 |  | Yes |  |  | 5
TEL-0052 | Align OSS migration deliverables with PMO reporting cadence | Supervisor Review | Medium | Karthik Nair | Infrastructure Planning | Sprint 14 | OSS/BSS Platform Migration | 5 | 5 | 2025-04-07 | 2025-04-09 | 2025-04-08 |  | Yes |  |  | 6
TEL-0053 | Escalate persistent overbilling anomaly on VoLTE bundles | Supervisor Review | High | Meena Iyer | Network Operations | Sprint 14 | VoLTE Quality Enhancement | 8 | 8 | 2025-03-31 | 2025-04-04 | 2025-03-31 |  | Yes |  |  | 5
TEL-0054 | Prepare FTTH subscriber forecast for investor update | In Progress | Medium | Divya Krishnan | Service Assurance | Sprint 14 | Fibre-to-the-Home Expansion | 8 | 5 | 2025-04-08 | 2025-04-12 | 2025-04-08 |  | Yes |  |  | 6
TEL-0055 | Update slice lifecycle management runbook | Supervisor Review | Medium | Priya Venkat | Customer Experience | Sprint 14 | Network Slicing Configuration | 5 | 5 | 2025-03-31 | 2025-04-03 | 2025-04-01 |  | Yes |  |  | 5
TEL-0056 | Prepare onboarding process maturity assessment for audit | Done | Critical | Lakshmi Rao | Infrastructure Planning | Sprint 14 | Customer Onboarding Automation | 8 | 8 | 2025-04-09 | 2025-04-13 | 2025-04-10 | 2025-04-14 | Yes |  |  | 6
TEL-0057 | Update refarming risk register with latest field data | In Progress | Medium | Ravi Shankar | Network Operations | Sprint 14 | Spectrum Refarming Programme | 8 | 7 | 2025-04-01 | 2025-04-05 | 2025-04-01 |  | Yes |  |  | 5
TEL-0058 | Escalate repeated SLA miss on Mumbai-Delhi backbone link | To Do | High | Arun Patel | Service Assurance | Sprint 14 | SLA Compliance Monitoring | 8 | 8 | 2025-04-07 | 2025-04-12 |  |  | No |  |  | 6
TEL-0059 | Document edge node failover procedure for ops runbook | Blocked | High | Suresh Babu | Customer Experience | Sprint 14 | Edge Computing Deployment | 5 | 5 | 2025-04-02 | 2025-04-05 | 2025-04-02 |  | Yes | Third-party SLA breach under investigation | TEL-0044 | 5
TEL-0060 | Track compliance training completion for field engineers | In Progress | Medium | Karthik Nair | Infrastructure Planning | Sprint 14 | Regulatory Compliance Upgrade | 8 | 1 | 2025-04-09 | 2025-04-14 | 2025-04-10 |  | No |  |  | 6
FACILITATOR NOTE — Traps & Expected Outputs: 1. Status counts are fixed: Done=25, In Progress=15, Blocked=9, Supervisor Review=7, To Do=4 (total 60). 2. Sprint 12 has 14 Done tickets (healthy); Sprint 14 has only 3 Done (unhealthy) — participants must detect this gradient. 3. 'Supervisor Review' replaces 'Code Review' — VBA must count this label exactly. 4. Blocker column is non-empty for exactly 9 rows — macro must filter Status='Blocked' AND Blocker not blank. 5. Week Number 1-6 maps to Sprints: Weeks 1-2 → Sprint 12, Weeks 3-4 → Sprint 13, Weeks 5-6 → Sprint 14. 6. Burndown: participants must sum Original Points per week to derive ideal line; actual = cumulative Done points by week.

## Squad Targets
Squad | Sprint | Planned Velocity | On-Time Target % | Max Blockers Allowed
Network Operations | Sprint 12 | 40 | 85% | 2
Network Operations | Sprint 13 | 42 | 85% | 2
Network Operations | Sprint 14 | 45 | 90% | 1
Service Assurance | Sprint 12 | 38 | 80% | 2
Service Assurance | Sprint 13 | 40 | 82% | 2
Service Assurance | Sprint 14 | 42 | 85% | 1
Customer Experience | Sprint 12 | 35 | 80% | 2
Customer Experience | Sprint 13 | 38 | 82% | 2
Customer Experience | Sprint 14 | 40 | 85% | 1
Infrastructure Planning | Sprint 12 | 36 | 80% | 2
Infrastructure Planning | Sprint 13 | 38 | 82% | 2
Infrastructure Planning | Sprint 14 | 40 | 85% | 1
FACILITATOR NOTE — Traps & Expected Outputs: 1. Planned Velocity is in story points — participants must sum Original Points for each squad/sprint to compare. 2. On-Time Target is the % of tickets that must finish by Planned End — macro should compute actual on-time rate and compare. 3. Max Blockers Allowed: Sprint 14 allows only 1 per squad — any squad with 2+ blockers in Sprint 14 should flag RED in the scorecard. 4. Radar chart normalisation: each metric must be scaled 0-1 before plotting; Blocker Resistance must be INVERTED (fewer blockers = higher score).

## Sprint Ceremonies
Sprint | Ceremony | Date | Duration (min) | Key Notes
Sprint 12 | Planning | 2025-03-03 | 60 | Backlog groomed; Network Operations took highest velocity target. Service Assurance flagged dependency on vendor firmware. Program Manager confirmed scope with all 4 squad leads.
Sprint 12 | Daily Standup Summary (Week 1) | 2025-03-07 | 15 | Network Operations ahead of plan. Service Assurance raised RAN equipment delay risk. Customer Experience on track. Infrastructure Planning waiting on fibre permits.
Sprint 12 | Mid-Sprint Review | 2025-03-10 | 30 | 72% of Sprint 12 tickets in progress or done. One blocker in Service Assurance (vendor firmware). Program Manager re-prioritised 2 tickets from Infrastructure Planning to unblock fibre route dependency.
Sprint 12 | Sprint Review | 2025-03-14 | 45 | Sprint 12 velocity met target for 3 of 4 squads. Infrastructure Planning missed by 4 points due to permit delay. Stakeholder demo covered 5G core UPF activation and OSS migration Phase 1.
Sprint 12 | Retrospective | 2025-03-14 | 30 | Action item: improve cross-squad dependency tracking. Network Operations proposed shared blocker board. Program Manager committed to weekly vendor follow-up cadence.
Sprint 13 | Planning | 2025-03-17 | 60 | Carried over 3 tickets from Sprint 12. Service Assurance velocity target increased to 40. Program Manager flagged spectrum refarming as cross-squad risk. Customer Experience onboarding automation reprioritised to High.
Sprint 13 | Daily Standup Summary (Week 3) | 2025-03-21 | 15 | Mixed progress. Network Operations hit a core network freeze window blocker. Customer Experience eKYC integration delayed by third-party SLA breach. Infrastructure Planning on track.
Sprint 13 | Mid-Sprint Review | 2025-03-24 | 30 | 55% completion at mid-sprint — below target. Three blockers active: core freeze, eKYC vendor, and TRAI regulatory hold on spectrum. Program Manager escalated vendor SLA breach to procurement.
Sprint 13 | Sprint Review | 2025-03-28 | 45 | Sprint 13 delivered 65% of planned velocity. Two squads below target. Blocker count (3) exceeded threshold for Service Assurance. Stakeholder feedback: VoLTE quality improvement visible but FTTH behind schedule.
Sprint 13 | Retrospective | 2025-03-28 | 30 | Key learning: external dependencies account for 60% of blockers. Program Manager to introduce dependency pre-check in planning. Agreed to add 'regulatory risk' as standing agenda item.
Sprint 14 | Planning | 2025-03-31 | 60 | High-risk sprint. 5 tickets already blocked at planning start. Program Manager escalated fibre permit and RAN shipment delays to executive steering committee. Sprint 14 velocity target reduced by 10% across all squads.
Sprint 14 | Daily Standup Summary (Week 5) | 2025-04-04 | 15 | 5 blockers active. Network Operations and Service Assurance both reporting external dependency hold-ups. Program Manager initiated daily blocker triage with vendor management. Customer Experience self-service portal bug causing order fallout.
Sprint 14 | Mid-Sprint Review | 2025-04-07 | 30 | Only 25% of Sprint 14 tickets in Done status. 5 blocked, 7 in progress. Program Manager triggered risk escalation protocol — presented blocker analysis to programme director. Infrastructure Planning fibre permits partially unblocked (3 of 5 districts).
Sprint 14 | Sprint Review | 2025-04-11 | 45 | Sprint 14 completed only 35% of planned velocity. Red status across all health metrics. Program Manager recommended scope reduction for Sprint 15 and dedicated blocker-resolution sprint. Stakeholder concern: FTTH expansion timeline at risk for investor commitment.
FACILITATOR NOTE — Traps & Expected Outputs: 1. Sprint 14 ceremonies explicitly reference 'Program Manager' escalating issues — the VBA macro for Level 3 Ceremony Insights must pull Sprint 14 rows and the participant should see role-specific actions. 2. Sprint 12 has 5 ceremonies, Sprint 13 has 5, Sprint 14 has 4 (no Retrospective yet — sprint still in progress). 3. Key Notes contain squad names — Level 3 radar chart metrics should correlate with ceremony qualitative data. 4. Daily Standup rows are labelled with week number — macro must parse '(Week N)' to align with burndown week axis.