## Sprint Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
BPO-201 | Configure agent role access in CRM portal | Done | Critical | Arjun | Claims Processing | Sprint 12 | Agent Onboarding | 13 | 13 | 2026-03-06 | 2026-03-08 | 2026-03-05 | 2026-03-11 | Yes |  |  | 1
BPO-202 | Build payment plan setup workflow for claims | Done | Low | Priya | Claims Processing | Sprint 12 | Collections Workflow | 8 | 8 | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-03-05 | Yes |  |  | 1
BPO-203 | Build client reporting dashboard layout | Done | Low | Karthik | Collections | Sprint 12 | Client Reporting | 8 | 8 | 2026-03-09 | 2026-03-12 | 2026-03-08 | 2026-03-11 | No |  |  | 2
BPO-204 | Implement SLA breach filter in ticket tracker | Done | High | Meera | Collections | Sprint 12 | SLA Monitoring | 2 | 2 | 2026-03-03 | 2026-03-04 | 2026-03-04 | 2026-03-04 | No |  |  | 1
BPO-205 | Set up escalation triggers for P1 breaches | Done | Low | Sneha | Quality Assurance | Sprint 12 | Escalation Management | 13 | 13 | 2026-03-08 | 2026-03-09 | 2026-03-09 | 2026-03-11 | Yes |  |  | 1
BPO-206 | Automate daily QA scorecard generation | Done | Medium | Divya | Quality Assurance | Sprint 12 | Process Automation | 2 | 2 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-09 | Yes |  |  | 1
BPO-207 | Document standard operating procedures for agents | Done | High | Vikram | Process Automation | Sprint 12 | Knowledge Base | 3 | 3 | 2026-03-03 | 2026-03-08 | 2026-03-03 | 2026-03-07 | No |  |  | 1
BPO-208 | Optimise batch job processing for nightly reports | Done | High | Rohit | Process Automation | Sprint 12 | Operational Efficiency | 13 | 13 | 2026-03-02 | 2026-03-04 | 2026-03-03 | 2026-03-05 | Yes |  | BPO-202 | 1
BPO-209 | Integrate CRM with claims management system | Done | Medium | Arjun | Claims Processing | Sprint 12 | System Integration | 8 | 8 | 2026-03-09 | 2026-03-13 | 2026-03-11 | 2026-03-12 | No |  | BPO-204 | 2
BPO-210 | Build monthly MI report template for client | Done | Medium | Priya | Claims Processing | Sprint 12 | MI Reporting | 8 | 8 | 2026-03-11 | 2026-03-13 | 2026-03-11 | 2026-03-15 | Yes |  |  | 2
BPO-211 | Design IVR routing logic for collections team | In Progress | High | Karthik | Collections | Sprint 12 | Agent Onboarding | 1 | 1 | 2026-03-08 | 2026-03-13 | 2026-03-10 |  | Yes |  |  | 1
BPO-212 | Configure callback scheduling for outstanding accounts | Done | Critical | Meera | Collections | Sprint 12 | Collections Workflow | 3 | 3 | 2026-03-10 | 2026-03-12 | 2026-03-11 | 2026-03-10 | No |  | BPO-203 | 2
BPO-213 | Build quality scorecard template for QA team | Done | Medium | Sneha | Quality Assurance | Sprint 12 | Client Reporting | 13 | 13 | 2026-03-10 | 2026-03-11 | 2026-03-11 | 2026-03-14 | Yes |  |  | 2
BPO-214 | Set up SLA dashboard for supervisor review | Done | High | Divya | Quality Assurance | Sprint 12 | SLA Monitoring | 3 | 3 | 2026-03-11 | 2026-03-13 | 2026-03-10 | 2026-03-13 | No |  |  | 2
BPO-215 | Configure escalation notification pipeline | Blocked | High | Vikram | Process Automation | Sprint 12 | Escalation Management | 3 | 3 | 2026-03-05 | 2026-03-10 | 2026-03-04 |  | Yes | Dependency on BPO-207 not complete |  | 1
BPO-216 | Deploy automated compliance check script | Done | High | Rohit | Process Automation | Sprint 12 | Process Automation | 2 | 2 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-10 | No |  |  | 2
BPO-217 | Document claims exception handling procedures | Done | High | Arjun | Claims Processing | Sprint 12 | Knowledge Base | 13 | 13 | 2026-03-08 | 2026-03-11 | 2026-03-10 | 2026-03-09 | No |  | BPO-203 | 1
BPO-218 | Streamline agent handoff process for complex claims | Done | High | Priya | Claims Processing | Sprint 12 | Operational Efficiency | 8 | 8 | 2026-03-02 | 2026-03-03 | 2026-03-02 | 2026-03-02 | No |  | BPO-202 | 1
BPO-219 | Integrate collections system with payment gateway | Done | High | Karthik | Collections | Sprint 12 | System Integration | 1 | 1 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-03-10 | No |  |  | 2
BPO-220 | Set up weekly MI pack for collections team | Done | Critical | Meera | Collections | Sprint 12 | MI Reporting | 2 | 7 | 2026-03-08 | 2026-03-11 | 2026-03-10 | 2026-03-14 | Yes |  | BPO-204 | 1
BPO-221 | Complete agent certification tracking module | Done | Critical | Arjun | Claims Processing | Sprint 13 | Agent Onboarding | 3 | 3 | 2026-03-19 | 2026-03-21 | 2026-03-19 | 2026-03-22 | Yes |  | BPO-215 | 3
BPO-222 | Finalise payment dispute resolution workflow | Done | Low | Priya | Claims Processing | Sprint 13 | Collections Workflow | 1 | 1 | 2026-03-16 | 2026-03-21 | 2026-03-16 | 2026-03-20 | No |  | BPO-216 | 3
BPO-223 | Configure auto-dialler IVR routing script | Blocked | Critical | Karthik | Collections | Sprint 13 | Client Reporting | 5 | 5 | 2026-03-22 | 2026-03-23 | 2026-03-23 |  | Yes | CRM integration API unavailable |  | 3
BPO-224 | Build real-time SLA breach alert for collections | In Progress | Low | Meera | Collections | Sprint 13 | SLA Monitoring | 8 | 8 | 2026-03-19 | 2026-03-22 | 2026-03-18 |  | Yes |  |  | 3
BPO-225 | Build P2 escalation handling procedure | Supervisor Review | Medium | Sneha | Quality Assurance | Sprint 13 | Escalation Management | 13 | 13 | 2026-03-16 | 2026-03-21 | 2026-03-16 |  | Yes |  | BPO-217 | 3
BPO-226 | Automate QA audit report distribution | Blocked | Critical | Divya | Quality Assurance | Sprint 13 | Process Automation | 1 | 1 | 2026-03-22 | 2026-03-23 | 2026-03-22 |  | Yes | Client process documentation not yet received |  | 3
BPO-227 | Draft agent knowledge base for onboarding portal | In Progress | Medium | Vikram | Process Automation | Sprint 13 | Knowledge Base | 8 | 8 | 2026-03-19 | 2026-03-22 | 2026-03-21 |  | Yes |  | BPO-221 | 3
BPO-228 | Tune RPA bot for claims data extraction | In Progress | Critical | Rohit | Process Automation | Sprint 13 | Operational Efficiency | 3 | 6 | 2026-03-23 | 2026-03-24 | 2026-03-23 |  | Yes |  |  | 4
BPO-229 | Map data fields for legacy claims system migration | Supervisor Review | High | Arjun | Claims Processing | Sprint 13 | System Integration | 1 | 1 | 2026-03-20 | 2026-03-22 | 2026-03-21 |  | Yes |  |  | 3
BPO-230 | Build daily operational MI dashboard | In Progress | Critical | Priya | Claims Processing | Sprint 13 | MI Reporting | 13 | 13 | 2026-03-17 | 2026-03-19 | 2026-03-16 |  | Yes |  |  | 3
BPO-231 | Complete agent scripting guide for debt recovery | Done | High | Karthik | Collections | Sprint 13 | Agent Onboarding | 3 | 3 | 2026-03-19 | 2026-03-22 | 2026-03-20 | 2026-03-20 | No |  | BPO-214 | 3
BPO-232 | Configure multi-channel contact preference tracker | In Progress | Critical | Meera | Collections | Sprint 13 | Collections Workflow | 1 | 1 | 2026-03-18 | 2026-03-21 | 2026-03-20 |  | Yes |  |  | 3
BPO-233 | Draft monthly quality report for client review | To Do | Critical | Sneha | Quality Assurance | Sprint 13 | Client Reporting | 1 | 1 | 2026-03-18 | 2026-03-23 |  |  | Yes |  |  | 3
BPO-234 | Build SLA compliance heatmap report | Blocked | High | Divya | Quality Assurance | Sprint 13 | SLA Monitoring | 5 | 5 | 2026-03-20 | 2026-03-23 | 2026-03-19 |  | Yes | Client sign-off on SLA thresholds pending |  | 3
BPO-235 | Automate P1 ticket escalation to account lead | Blocked | Low | Vikram | Process Automation | Sprint 13 | Escalation Management | 3 | 3 | 2026-03-19 | 2026-03-21 | 2026-03-19 |  | Yes | Client process documentation not yet received | BPO-222 | 3
BPO-236 | Deploy scheduled batch job for overnight processing | Supervisor Review | High | Rohit | Process Automation | Sprint 13 | Process Automation | 5 | 5 | 2026-03-18 | 2026-03-19 | 2026-03-17 |  | Yes |  |  | 3
BPO-237 | Create FAQs for agent knowledge base portal | To Do | Medium | Arjun | Claims Processing | Sprint 13 | Knowledge Base | 5 | 5 | 2026-03-19 | 2026-03-21 |  |  | Yes |  | BPO-222 | 3
BPO-238 | Reduce manual steps in claims verification flow | Done | Medium | Priya | Claims Processing | Sprint 13 | Operational Efficiency | 1 | 1 | 2026-03-24 | 2026-03-26 | 2026-03-25 | 2026-03-24 | No |  | BPO-217 | 4
BPO-239 | Integrate debt recovery platform with CRM | In Progress | Critical | Karthik | Collections | Sprint 13 | System Integration | 3 | 3 | 2026-03-25 | 2026-03-27 | 2026-03-26 |  | Yes |  |  | 4
BPO-240 | Produce weekly collections performance pack | Done | Low | Meera | Collections | Sprint 13 | MI Reporting | 1 | 1 | 2026-03-20 | 2026-03-21 | 2026-03-19 | 2026-03-23 | Yes |  |  | 3
BPO-241 | Roll out revised agent onboarding process | Blocked | High | Arjun | Claims Processing | Sprint 14 | Agent Onboarding | 13 | 13 | 2026-04-05 | 2026-04-06 | 2026-04-06 |  | Yes | Awaiting process design sign-off |  | 5
BPO-242 | Update payment plan SLA thresholds in system | Supervisor Review | Medium | Priya | Claims Processing | Sprint 14 | Collections Workflow | 8 | 8 | 2026-04-04 | 2026-04-08 | 2026-04-04 |  | No |  | BPO-225 | 5
BPO-243 | Build executive summary slide for client QBR | In Progress | Medium | Karthik | Collections | Sprint 14 | Client Reporting | 2 | 2 | 2026-04-07 | 2026-04-08 | 2026-04-07 |  | No |  |  | 6
BPO-244 | Configure SLA breach report with trend analysis | Supervisor Review | Medium | Meera | Collections | Sprint 14 | SLA Monitoring | 13 | 13 | 2026-04-06 | 2026-04-10 | 2026-04-08 |  | No |  |  | 6
BPO-245 | Create escalation playbook for P1 incidents | Supervisor Review | High | Sneha | Quality Assurance | Sprint 14 | Escalation Management | 13 | 13 | 2026-04-03 | 2026-04-08 | 2026-04-04 |  | No |  | BPO-216 | 5
BPO-246 | Automate QA sampling selection process | In Progress | High | Divya | Quality Assurance | Sprint 14 | Process Automation | 2 | 2 | 2026-03-30 | 2026-03-31 | 2026-04-01 |  | Yes |  |  | 5
BPO-247 | Publish agent knowledge base to intranet portal | In Progress | Low | Vikram | Process Automation | Sprint 14 | Knowledge Base | 5 | 7 | 2026-04-05 | 2026-04-09 | 2026-04-05 |  | No |  |  | 5
BPO-248 | Benchmark processing time vs SLA for all workflows | To Do | High | Rohit | Process Automation | Sprint 14 | Operational Efficiency | 5 | 5 | 2026-04-07 | 2026-04-09 |  |  | No |  | BPO-208 | 6
BPO-249 | Complete CRM-to-claims-portal data mapping | Blocked | Medium | Arjun | Claims Processing | Sprint 14 | System Integration | 5 | 5 | 2026-04-08 | 2026-04-10 | 2026-04-10 |  | No | Data compliance review pending |  | 6
BPO-250 | Automate monthly MI report generation | In Progress | Medium | Priya | Claims Processing | Sprint 14 | MI Reporting | 13 | 13 | 2026-04-02 | 2026-04-05 | 2026-04-03 |  | Yes |  | BPO-222 | 5
BPO-251 | Train collections team on updated debt recovery script | In Progress | Critical | Karthik | Collections | Sprint 14 | Agent Onboarding | 8 | 11 | 2026-04-01 | 2026-04-03 | 2026-04-01 |  | Yes |  |  | 5
BPO-252 | Configure payment gateway integration for new scheme | Blocked | Low | Meera | Collections | Sprint 14 | Collections Workflow | 3 | 3 | 2026-03-30 | 2026-04-01 | 2026-04-01 |  | Yes | Client process documentation not yet received |  | 5
BPO-253 | Deliver Q1 quality performance report to client | Done | Low | Sneha | Quality Assurance | Sprint 14 | Client Reporting | 5 | 5 | 2026-04-04 | 2026-04-07 | 2026-04-06 | 2026-04-09 | Yes |  |  | 5
BPO-254 | Build SLA compliance monitoring script for QA team | In Progress | High | Divya | Quality Assurance | Sprint 14 | SLA Monitoring | 8 | 8 | 2026-04-02 | 2026-04-05 | 2026-04-01 |  | Yes |  |  | 5
BPO-255 | Test P2 escalation automation in staging environment | In Progress | High | Vikram | Process Automation | Sprint 14 | Escalation Management | 5 | 5 | 2026-04-01 | 2026-04-06 | 2026-04-03 |  | Yes |  |  | 5
BPO-256 | Schedule automated end-of-day reconciliation job | To Do | Low | Rohit | Process Automation | Sprint 14 | Process Automation | 1 | 1 | 2026-04-06 | 2026-04-08 |  |  | No |  |  | 6
BPO-257 | Review and update claims SOP documentation | In Progress | Medium | Arjun | Claims Processing | Sprint 14 | Knowledge Base | 3 | 3 | 2026-04-03 | 2026-04-07 | 2026-04-02 |  | Yes |  |  | 5
BPO-258 | Simplify claims re-assignment workflow | Done | Medium | Priya | Claims Processing | Sprint 14 | Operational Efficiency | 1 | 1 | 2026-03-31 | 2026-04-01 | 2026-03-31 | 2026-03-31 | No |  |  | 5
BPO-259 | Integrate callback scheduler with CRM contact records | Blocked | High | Karthik | Collections | Sprint 14 | System Integration | 2 | 2 | 2026-03-31 | 2026-04-05 | 2026-04-02 |  | Yes | Awaiting process design sign-off | BPO-239 | 5
BPO-260 | Build collections MI pack for sprint review | Supervisor Review | Critical | Meera | Collections | Sprint 14 | MI Reporting | 13 | 13 | 2026-04-03 | 2026-04-04 | 2026-04-04 |  | Yes |  |  | 5

## Squad Targets
Squad | Sprint | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
Claims Processing | Sprint 12 | 30 | 85 | 3
Claims Processing | Sprint 13 | 24 | 80 | 3
Claims Processing | Sprint 14 | 25 | 80 | 3
Collections | Sprint 12 | 27 | 90 | 3
Collections | Sprint 13 | 21 | 90 | 1
Collections | Sprint 14 | 29 | 90 | 2
Quality Assurance | Sprint 12 | 29 | 80 | 3
Quality Assurance | Sprint 13 | 28 | 80 | 2
Quality Assurance | Sprint 14 | 33 | 80 | 2
Process Automation | Sprint 12 | 29 | 90 | 2
Process Automation | Sprint 13 | 22 | 85 | 1
Process Automation | Sprint 14 | 34 | 90 | 2

## Sprint Ceremonies
Sprint | Ceremony | Date | Key Decisions / Notes
Sprint 12 | Sprint Planning | 2026-03-02 | 20 tickets committed, 2 carried over from previous delivery cycle
Sprint 12 | Daily Standup Summary (Week 1) | 2026-03-06 | Claims Processing blocker on CRM API — escalated to account lead
Sprint 12 | Mid-Sprint Review | 2026-03-09 | 3 tickets re-estimated upward, QA flagged staging environment instability
Sprint 12 | Sprint Review | 2026-03-13 | 16 of 20 tickets done, 2 blocked, 2 carried to Sprint 13
Sprint 12 | Retrospective | 2026-03-13 | Action: improve dependency tracking, add blocker column to daily standup
Sprint 13 | Sprint Planning | 2026-03-16 | 20 tickets committed including 2 carryovers, 1 new P1 incident added
Sprint 13 | Daily Standup Summary (Week 1) | 2026-03-20 | Collections team ahead of schedule, Process Automation blocked on staging access
Sprint 13 | Mid-Sprint Review | 2026-03-23 | Client requested scope addition — 2 new tickets added mid-sprint
Sprint 13 | Sprint Review | 2026-03-27 | 14 of 22 tickets done, velocity dip flagged, 4 blocked tickets escalated
Sprint 13 | Retrospective | 2026-03-27 | Action: no mid-sprint scope additions without Tech Lead approval, blocker SLA of 24 hours
Sprint 14 | Sprint Planning | 2026-03-30 | 20 tickets committed, team flagged resource risk — Divya on leave week 2
Sprint 14 | Daily Standup Summary (Week 1) | 2026-04-03 | 6 tickets blocked — highest blocker count in 3 sprints
Sprint 14 | Mid-Sprint Review | 2026-04-06 | Only 2 tickets done at midpoint, Tech Lead escalated to delivery head
Sprint 14 | Sprint Review | 2026-04-10 | Sprint still in progress — review scheduled for April 10