## Sprint Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
NGM-301 | Set up SEA regional office infrastructure | To Do | Low | Ankita | LatAm Expansion | Sprint 12 | Market Entry | 2 | 2 | 2026-03-04 | 2026-03-05 |  |  | Yes |  |  | 1
NGM-302 | Configure CEE client portal access | Done | Medium | Huali | SEA Go-to-Market | Sprint 12 | Client Onboarding | 3 | 3 | 2026-03-04 | 2026-03-05 | 2026-03-03 | 2026-03-06 | Yes |  |  | 1
NGM-303 | Build MEA compliance checklist for regulators | Done | Medium | Digvijay | MEA Delivery | Sprint 12 | Regional Compliance | 1 | 1 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-05 | No |  |  | 1
NGM-304 | Deliver MEA market analysis report to leadership | Done | High | Xianhua | CEE Integration | Sprint 12 | Delivery Acceleration | 13 | 15 | 2026-03-04 | 2026-03-05 | 2026-03-04 | 2026-03-03 | No |  |  | 1
NGM-305 | Integrate CEE vendor payment gateway | Done | Medium | Deepu | LatAm Expansion | Sprint 12 | Vendor Management | 2 | 2 | 2026-03-03 | 2026-03-06 | 2026-03-02 | 2026-03-08 | Yes |  |  | 1
NGM-306 | Deploy SEA revenue tracking dashboard | Done | High | Ravi | SEA Go-to-Market | Sprint 12 | Revenue Tracking | 5 | 5 | 2026-03-07 | 2026-03-12 | 2026-03-07 | 2026-03-15 | Yes |  |  | 1
NGM-307 | Prepare LatAm stakeholder QBR slide deck | Done | High | Prerna | MEA Delivery | Sprint 12 | Stakeholder Reporting | 1 | 1 | 2026-03-05 | 2026-03-08 | 2026-03-04 | 2026-03-07 | No |  | NGM-305 | 1
NGM-308 | Map MEA operational workflows for delivery | Supervisor Review | High | Thomas | CEE Integration | Sprint 12 | Operational Setup | 13 | 13 | 2026-03-07 | 2026-03-11 | 2026-03-07 |  | No |  |  | 1
NGM-309 | Complete MEA partner onboarding documentation | Done | Low | Ankita | LatAm Expansion | Sprint 12 | Market Entry | 8 | 8 | 2026-03-03 | 2026-03-05 | 2026-03-05 | 2026-03-03 | No |  | NGM-302 | 1
NGM-310 | Automate SEA invoice reconciliation process | Done | High | Huali | SEA Go-to-Market | Sprint 12 | Client Onboarding | 13 | 13 | 2026-03-02 | 2026-03-06 | 2026-03-04 | 2026-03-08 | Yes |  | NGM-309 | 1
NGM-311 | Train MEA local team on delivery standards | Blocked | Critical | Digvijay | MEA Delivery | Sprint 12 | Regional Compliance | 13 | 13 | 2026-03-07 | 2026-03-12 | 2026-03-08 |  | Yes | Vendor API integration delayed |  | 2
NGM-312 | Finalise CEE contract terms with regional vendor | Done | High | Xianhua | CEE Integration | Sprint 12 | Delivery Acceleration | 5 | 8 | 2026-03-06 | 2026-03-08 | 2026-03-05 | 2026-03-11 | Yes |  |  | 2
NGM-313 | Design SEA escalation matrix for delivery risks | Done | High | Deepu | LatAm Expansion | Sprint 12 | Vendor Management | 3 | 3 | 2026-03-06 | 2026-03-11 | 2026-03-05 | 2026-03-13 | Yes |  |  | 2
NGM-314 | Roll out LatAm client feedback collection system | Done | Critical | Ravi | SEA Go-to-Market | Sprint 12 | Revenue Tracking | 3 | 3 | 2026-03-04 | 2026-03-06 | 2026-03-03 | 2026-03-05 | No |  | NGM-302 | 2
NGM-315 | Build LatAm resource utilisation tracker | Done | Low | Prerna | MEA Delivery | Sprint 12 | Stakeholder Reporting | 1 | 1 | 2026-03-06 | 2026-03-08 | 2026-03-06 | 2026-03-11 | Yes |  |  | 2
NGM-316 | Set up SEA SLA monitoring for regional accounts | In Progress | Medium | Thomas | CEE Integration | Sprint 12 | Operational Setup | 8 | 8 | 2026-03-05 | 2026-03-07 | 2026-03-05 |  | Yes |  |  | 2
NGM-317 | Configure MEA cross-border data transfer pipeline | Done | Low | Ankita | LatAm Expansion | Sprint 12 | Market Entry | 8 | 8 | 2026-03-03 | 2026-03-05 | 2026-03-02 | 2026-03-05 | No |  |  | 2
NGM-318 | Document SEA go-to-market playbook | Done | High | Huali | SEA Go-to-Market | Sprint 12 | Client Onboarding | 1 | 3 | 2026-03-03 | 2026-03-04 | 2026-03-02 | 2026-03-04 | No |  |  | 2
NGM-319 | Run SEA pilot programme with anchor client | Done | Medium | Digvijay | MEA Delivery | Sprint 12 | Regional Compliance | 13 | 13 | 2026-03-06 | 2026-03-08 | 2026-03-08 | 2026-03-07 | No |  | NGM-314 | 2
NGM-320 | Create SEA weekly MI pack for regional head | Done | Critical | Xianhua | CEE Integration | Sprint 12 | Delivery Acceleration | 1 | 1 | 2026-03-04 | 2026-03-08 | 2026-03-06 | 2026-03-09 | Yes |  | NGM-302 | 2
NGM-321 | Set up LatAm regional office infrastructure | Blocked | Critical | Ankita | LatAm Expansion | Sprint 13 | Market Entry | 1 | 1 | 2026-03-17 | 2026-03-19 | 2026-03-19 |  | Yes | Client contract amendment pending | NGM-302 | 3
NGM-322 | Configure SEA client portal access | In Progress | Low | Huali | SEA Go-to-Market | Sprint 13 | Client Onboarding | 1 | 1 | 2026-03-18 | 2026-03-22 | 2026-03-19 |  | Yes |  | NGM-318 | 3
NGM-323 | Build CEE compliance checklist for regulators | Done | High | Digvijay | MEA Delivery | Sprint 13 | Regional Compliance | 2 | 2 | 2026-03-16 | 2026-03-21 | 2026-03-15 | 2026-03-24 | Yes |  |  | 3
NGM-324 | Deliver LatAm market analysis report to leadership | Done | Low | Xianhua | CEE Integration | Sprint 13 | Delivery Acceleration | 8 | 8 | 2026-03-20 | 2026-03-22 | 2026-03-19 | 2026-03-24 | Yes |  |  | 3
NGM-325 | Integrate SEA vendor payment gateway | To Do | Critical | Deepu | LatAm Expansion | Sprint 13 | Vendor Management | 8 | 10 | 2026-03-19 | 2026-03-20 |  |  | Yes |  |  | 3
NGM-326 | Deploy LatAm revenue tracking dashboard | Supervisor Review | Critical | Ravi | SEA Go-to-Market | Sprint 13 | Revenue Tracking | 5 | 5 | 2026-03-20 | 2026-03-25 | 2026-03-21 |  | Yes |  |  | 3
NGM-327 | Prepare MEA stakeholder QBR slide deck | Supervisor Review | High | Prerna | MEA Delivery | Sprint 13 | Stakeholder Reporting | 3 | 3 | 2026-03-21 | 2026-03-24 | 2026-03-23 |  | No |  | NGM-303 | 3
NGM-328 | Map LatAm operational workflows for delivery | In Progress | Low | Thomas | CEE Integration | Sprint 13 | Operational Setup | 8 | 8 | 2026-03-16 | 2026-03-17 | 2026-03-16 |  | Yes |  |  | 3
NGM-329 | Complete MEA partner onboarding documentation | In Progress | Critical | Ankita | LatAm Expansion | Sprint 13 | Market Entry | 2 | 2 | 2026-03-17 | 2026-03-21 | 2026-03-18 |  | Yes |  | NGM-321 | 3
NGM-330 | Automate LatAm invoice reconciliation process | Done | Medium | Huali | SEA Go-to-Market | Sprint 13 | Client Onboarding | 13 | 15 | 2026-03-18 | 2026-03-19 | 2026-03-17 | 2026-03-22 | Yes |  |  | 3
NGM-331 | Train MEA local team on delivery standards | In Progress | Medium | Digvijay | MEA Delivery | Sprint 13 | Regional Compliance | 8 | 8 | 2026-03-18 | 2026-03-20 | 2026-03-19 |  | Yes |  |  | 4
NGM-332 | Finalise LatAm contract terms with regional vendor | In Progress | Critical | Xianhua | CEE Integration | Sprint 13 | Delivery Acceleration | 13 | 13 | 2026-03-18 | 2026-03-19 | 2026-03-17 |  | No |  |  | 4
NGM-333 | Design MEA escalation matrix for delivery risks | Blocked | High | Deepu | LatAm Expansion | Sprint 13 | Vendor Management | 13 | 13 | 2026-03-21 | 2026-03-25 | 2026-03-20 |  | No | Partner sign-off on delivery scope pending | NGM-303 | 4
NGM-334 | Roll out MEA client feedback collection system | Blocked | High | Ravi | SEA Go-to-Market | Sprint 13 | Revenue Tracking | 5 | 8 | 2026-03-18 | 2026-03-19 | 2026-03-19 |  | No | Client contract amendment pending | NGM-323 | 4
NGM-335 | Build CEE resource utilisation tracker | Supervisor Review | High | Prerna | MEA Delivery | Sprint 13 | Stakeholder Reporting | 2 | 2 | 2026-03-17 | 2026-03-21 | 2026-03-16 |  | No |  | NGM-327 | 4
NGM-336 | Set up SEA SLA monitoring for regional accounts | To Do | Medium | Thomas | CEE Integration | Sprint 13 | Operational Setup | 2 | 2 | 2026-03-16 | 2026-03-20 |  |  | Yes |  | NGM-315 | 4
NGM-337 | Configure SEA cross-border data transfer pipeline | In Progress | Low | Ankita | LatAm Expansion | Sprint 13 | Market Entry | 3 | 3 | 2026-03-17 | 2026-03-19 | 2026-03-16 |  | Yes |  |  | 4
NGM-338 | Document MEA go-to-market playbook | Blocked | Critical | Huali | SEA Go-to-Market | Sprint 13 | Client Onboarding | 3 | 3 | 2026-03-20 | 2026-03-24 | 2026-03-21 |  | Yes | Awaiting regional regulatory approval | NGM-317 | 4
NGM-339 | Run SEA pilot programme with anchor client | Done | Medium | Digvijay | MEA Delivery | Sprint 13 | Regional Compliance | 1 | 4 | 2026-03-18 | 2026-03-21 | 2026-03-20 | 2026-03-23 | Yes |  | NGM-308 | 4
NGM-340 | Create CEE weekly MI pack for regional head | Done | High | Xianhua | CEE Integration | Sprint 13 | Delivery Acceleration | 3 | 6 | 2026-03-16 | 2026-03-21 | 2026-03-16 | 2026-03-21 | No |  |  | 4
NGM-341 | Set up CEE regional office infrastructure | Done | Critical | Ankita | LatAm Expansion | Sprint 14 | Market Entry | 3 | 3 | 2026-04-02 | 2026-04-07 | 2026-04-03 | 2026-04-08 | Yes |  |  | 5
NGM-342 | Configure SEA client portal access | Blocked | Low | Huali | SEA Go-to-Market | Sprint 14 | Client Onboarding | 13 | 13 | 2026-03-30 | 2026-04-02 | 2026-03-31 |  | No | Client contract amendment pending | NGM-315 | 5
NGM-343 | Build SEA compliance checklist for regulators | Blocked | High | Digvijay | MEA Delivery | Sprint 14 | Regional Compliance | 1 | 4 | 2026-04-03 | 2026-04-04 | 2026-04-05 |  | Yes | Partner sign-off on delivery scope pending |  | 5
NGM-344 | Deliver CEE market analysis report to leadership | Done | Low | Xianhua | CEE Integration | Sprint 14 | Delivery Acceleration | 5 | 5 | 2026-04-04 | 2026-04-05 | 2026-04-03 | 2026-04-06 | Yes |  |  | 5
NGM-345 | Integrate CEE vendor payment gateway | In Progress | Critical | Deepu | LatAm Expansion | Sprint 14 | Vendor Management | 8 | 8 | 2026-03-30 | 2026-04-03 | 2026-03-30 |  | Yes |  | NGM-336 | 5
NGM-346 | Deploy MEA revenue tracking dashboard | Blocked | Low | Ravi | SEA Go-to-Market | Sprint 14 | Revenue Tracking | 8 | 8 | 2026-04-03 | 2026-04-07 | 2026-04-05 |  | Yes | Partner sign-off on delivery scope pending | NGM-329 | 5
NGM-347 | Prepare MEA stakeholder QBR slide deck | In Progress | High | Prerna | MEA Delivery | Sprint 14 | Stakeholder Reporting | 13 | 13 | 2026-04-03 | 2026-04-07 | 2026-04-03 |  | No |  |  | 5
NGM-348 | Map MEA operational workflows for delivery | Supervisor Review | High | Thomas | CEE Integration | Sprint 14 | Operational Setup | 3 | 3 | 2026-04-03 | 2026-04-04 | 2026-04-03 |  | No |  |  | 5
NGM-349 | Complete SEA partner onboarding documentation | Done | High | Ankita | LatAm Expansion | Sprint 14 | Market Entry | 1 | 1 | 2026-04-01 | 2026-04-06 | 2026-04-03 | 2026-04-07 | Yes |  |  | 5
NGM-350 | Automate CEE invoice reconciliation process | In Progress | Low | Huali | SEA Go-to-Market | Sprint 14 | Client Onboarding | 8 | 8 | 2026-03-30 | 2026-04-04 | 2026-04-01 |  | Yes |  | NGM-320 | 5
NGM-351 | Train CEE local team on delivery standards | In Progress | Low | Digvijay | MEA Delivery | Sprint 14 | Regional Compliance | 8 | 8 | 2026-04-03 | 2026-04-08 | 2026-04-03 |  | Yes |  |  | 6
NGM-352 | Finalise CEE contract terms with regional vendor | Blocked | Critical | Xianhua | CEE Integration | Sprint 14 | Delivery Acceleration | 5 | 5 | 2026-04-04 | 2026-04-08 | 2026-04-04 |  | Yes | Client contract amendment pending | NGM-335 | 6
NGM-353 | Design LatAm escalation matrix for delivery risks | In Progress | Low | Deepu | LatAm Expansion | Sprint 14 | Vendor Management | 8 | 8 | 2026-03-30 | 2026-03-31 | 2026-04-01 |  | No |  |  | 6
NGM-354 | Roll out LatAm client feedback collection system | In Progress | Medium | Ravi | SEA Go-to-Market | Sprint 14 | Revenue Tracking | 5 | 5 | 2026-04-02 | 2026-04-05 | 2026-04-03 |  | Yes |  |  | 6
NGM-355 | Build CEE resource utilisation tracker | Supervisor Review | Medium | Prerna | MEA Delivery | Sprint 14 | Stakeholder Reporting | 1 | 1 | 2026-04-04 | 2026-04-09 | 2026-04-03 |  | Yes |  |  | 6
NGM-356 | Set up LatAm SLA monitoring for regional accounts | Supervisor Review | Critical | Thomas | CEE Integration | Sprint 14 | Operational Setup | 1 | 1 | 2026-03-31 | 2026-04-01 | 2026-03-31 |  | No |  |  | 6
NGM-357 | Configure LatAm cross-border data transfer pipeline | In Progress | High | Ankita | LatAm Expansion | Sprint 14 | Market Entry | 5 | 5 | 2026-04-01 | 2026-04-03 | 2026-03-31 |  | Yes |  |  | 6
NGM-358 | Document MEA go-to-market playbook | Done | Critical | Huali | SEA Go-to-Market | Sprint 14 | Client Onboarding | 8 | 11 | 2026-04-03 | 2026-04-07 | 2026-04-05 | 2026-04-10 | Yes |  |  | 6
NGM-359 | Run SEA pilot programme with anchor client | To Do | Critical | Digvijay | MEA Delivery | Sprint 14 | Regional Compliance | 13 | 13 | 2026-04-04 | 2026-04-09 |  |  | Yes |  | NGM-337 | 6
NGM-360 | Create LatAm weekly MI pack for regional head | In Progress | Medium | Xianhua | CEE Integration | Sprint 14 | Delivery Acceleration | 8 | 8 | 2026-04-01 | 2026-04-02 | 2026-04-02 |  | No |  |  | 6

## Squad Targets
Squad | Sprint | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
LatAm Expansion | Sprint 12 | 28 | 85 | 3
LatAm Expansion | Sprint 13 | 25 | 80 | 3
LatAm Expansion | Sprint 14 | 27 | 80 | 2
SEA Go-to-Market | Sprint 12 | 30 | 90 | 2
SEA Go-to-Market | Sprint 13 | 22 | 85 | 2
SEA Go-to-Market | Sprint 14 | 32 | 90 | 1
MEA Delivery | Sprint 12 | 26 | 80 | 3
MEA Delivery | Sprint 13 | 24 | 80 | 2
MEA Delivery | Sprint 14 | 30 | 85 | 2
CEE Integration | Sprint 12 | 27 | 90 | 2
CEE Integration | Sprint 13 | 23 | 85 | 1
CEE Integration | Sprint 14 | 33 | 90 | 2

## Sprint Ceremonies
Sprint | Ceremony | Date | Key Decisions / Notes
Sprint 12 | Sprint Planning | 2026-03-02 | 20 tickets committed, 2 carried over from previous delivery cycle
Sprint 12 | Daily Standup Summary (Week 1) | 2026-03-06 | LatAm Expansion blocker on vendor API — escalated to regional head
Sprint 12 | Mid-Sprint Review | 2026-03-09 | 3 tickets re-estimated upward, MEA flagged regulatory delay risk
Sprint 12 | Sprint Review | 2026-03-13 | 16 of 20 tickets done, 1 blocked, 3 carried to Sprint 13
Sprint 12 | Retrospective | 2026-03-13 | Action: improve cross-region dependency tracking, add blocker column to standup
Sprint 13 | Sprint Planning | 2026-03-16 | 20 tickets committed including 3 carryovers, 1 new critical escalation added
Sprint 13 | Daily Standup Summary (Week 1) | 2026-03-20 | SEA team ahead of schedule, CEE Integration blocked on compliance review
Sprint 13 | Mid-Sprint Review | 2026-03-23 | Client requested scope addition — 2 new tickets added mid-sprint
Sprint 13 | Sprint Review | 2026-03-27 | 12 of 22 tickets done, velocity dip flagged, 4 blocked tickets escalated
Sprint 13 | Retrospective | 2026-03-27 | Action: no mid-sprint scope additions without Delivery Manager approval, blocker SLA of 24 hours
Sprint 14 | Sprint Planning | 2026-03-30 | 20 tickets committed, team flagged resource risk — Huali on leave week 2
Sprint 14 | Daily Standup Summary (Week 1) | 2026-04-03 | 6 tickets blocked — highest blocker count in 3 sprints
Sprint 14 | Mid-Sprint Review | 2026-04-06 | Only 3 tickets done at midpoint, Delivery Manager escalated to account head
Sprint 14 | Sprint Review | 2026-04-10 | Sprint still in progress — review scheduled for April 10