## Employee Action Tracker
Action ID | Summary | Status | Priority | Assignee | Team | Quarter | Initiative | Original Effort | Current Effort | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Month Number
HR-001 | Map critical role succession pipeline | Completed | High | Kavitha | Talent Acquisition | Q1 | Talent Pipeline | 3 | 3 | 2026-01-13 | 2026-01-16 | 2026-01-13 | 2026-01-18 | Yes |  |  | 1
HR-002 | Configure policy acknowledgement workflow | Manager Review | Medium | Rajesh | Employee Relations | Q1 | Policy Compliance | 3 | 3 | 2026-01-19 | 2026-01-27 | 2026-01-20 |  | Yes |  |  | 2
HR-003 | Create mentorship programme matching criteria | Completed | Low | Swathi | Learning & Development | Q1 | Learning Programs | 13 | 13 | 2026-01-12 | 2026-01-19 | 2026-01-11 | 2026-01-18 | No |  |  | 1
HR-004 | Analyse engagement scores by department | Completed | Critical | Vivek | Compensation & Benefits | Q1 | Employee Engagement | 5 | 5 | 2026-01-17 | 2026-01-23 | 2026-01-16 | 2026-01-22 | No |  |  | 2
HR-005 | Draft wellness program calendar for H2 | Completed | High | Kavitha | Talent Acquisition | Q1 | Employee Engagement | 13 | 13 | 2026-01-15 | 2026-01-20 | 2026-01-17 | 2026-01-21 | Yes |  |  | 1
HR-006 | Audit leave policy adherence across regions | Completed | Medium | Rajesh | Employee Relations | Q1 | Policy Compliance | 8 | 8 | 2026-01-09 | 2026-01-15 | 2026-01-09 | 2026-01-14 | No |  | HR-005 | 2
HR-007 | Draft certification reimbursement policy update | In Progress | Low | Swathi | Learning & Development | Q1 | Learning Programs | 5 | 7 | 2026-01-23 | 2026-01-31 | 2026-01-24 |  | Yes |  |  | 1
HR-008 | Design mandatory compliance training schedule | In Progress | Critical | Vivek | Compensation & Benefits | Q1 | Learning Programs | 3 | 4 | 2026-01-06 | 2026-01-09 | 2026-01-06 |  | Yes |  |  | 2
HR-009 | Create talent pool segmentation criteria | Completed | High | Kavitha | Talent Acquisition | Q1 | Talent Pipeline | 8 | 8 | 2026-01-24 | 2026-01-27 | 2026-01-26 | 2026-01-28 | Yes |  |  | 1
HR-010 | Implement engagement score alert thresholds | Completed | Medium | Rajesh | Employee Relations | Q1 | Employee Engagement | 8 | 8 | 2026-01-21 | 2026-01-27 | 2026-01-20 | 2026-01-30 | Yes |  | HR-009 | 2
HR-011 | Build hiring manager onboarding toolkit | Completed | Low | Swathi | Learning & Development | Q1 | Onboarding Redesign | 5 | 5 | 2026-01-25 | 2026-02-01 | 2026-01-24 | 2026-02-01 | No |  |  | 1
HR-012 | Build offer-to-join conversion tracking report | Completed | Critical | Vivek | Compensation & Benefits | Q1 | Talent Pipeline | 8 | 8 | 2026-01-05 | 2026-01-11 | 2026-01-05 | 2026-01-13 | Yes |  | HR-011 | 2
HR-013 | Design referral program incentive structure | Completed | High | Kavitha | Talent Acquisition | Q1 | Talent Pipeline | 5 | 5 | 2026-01-25 | 2026-02-04 | 2026-01-25 | 2026-02-03 | No |  |  | 1
HR-014 | Create performance bell curve analytics view | Completed | Medium | Rajesh | Employee Relations | Q1 | Performance Review | 3 | 3 | 2026-01-22 | 2026-02-01 | 2026-01-21 | 2026-02-03 | Yes |  |  | 2
HR-015 | Build campus recruitment calendar for FY27 | Completed | Low | Swathi | Learning & Development | Q1 | Talent Pipeline | 2 | 2 | 2026-01-08 | 2026-01-15 | 2026-01-09 | 2026-01-14 | No |  |  | 1
HR-016 | Build manager performance coaching toolkit | Completed | Critical | Vivek | Compensation & Benefits | Q1 | Performance Review | 13 | 13 | 2026-01-07 | 2026-01-10 | 2026-01-09 | 2026-01-08 | No |  | HR-009 | 2
HR-017 | Set up buddy system assignment workflow | Completed | High | Kavitha | Talent Acquisition | Q1 | Onboarding Redesign | 3 | 3 | 2026-01-09 | 2026-01-18 | 2026-01-09 | 2026-01-18 | No |  |  | 1
HR-018 | Update anti-harassment policy documentation | Completed | Medium | Rajesh | Employee Relations | Q1 | Policy Compliance | 13 | 13 | 2026-01-18 | 2026-01-23 | 2026-01-18 | 2026-01-26 | Yes |  |  | 2
HR-019 | Launch leadership development programme cohort | Completed | Low | Swathi | Learning & Development | Q1 | Learning Programs | 5 | 5 | 2026-01-19 | 2026-01-29 | 2026-01-21 | 2026-01-27 | No |  |  | 1
HR-020 | Design pre-boarding communication sequence | To Do | Critical | Vivek | Compensation & Benefits | Q1 | Onboarding Redesign | 2 | 2 | 2026-01-15 | 2026-01-17 | 2026-01-15 |  | No |  |  | 2
HR-021 | Create policy exception approval workflow | Manager Review | High | Kavitha | Talent Acquisition | Q2 | Policy Compliance | 8 | 8 | 2026-03-08 | 2026-03-11 | 2026-03-07 |  | Yes |  |  | 3
HR-022 | Launch quarterly pulse survey for all BUs | On Hold | Medium | Rajesh | Employee Relations | Q2 | Employee Engagement | 5 | 5 | 2026-03-16 | 2026-03-18 | 2026-03-15 |  | Yes | Pending HRMS vendor API access |  | 4
HR-023 | Implement learning ROI measurement framework | On Hold | Low | Swathi | Learning & Development | Q2 | Learning Programs | 5 | 6 | 2026-03-09 | 2026-03-14 | 2026-03-09 |  | Yes | Budget approval delayed by finance |  | 3
HR-024 | Build compliance training completion tracker | In Progress | Critical | Vivek | Compensation & Benefits | Q2 | Policy Compliance | 3 | 3 | 2026-03-10 | 2026-03-19 | 2026-03-10 |  | Yes |  | HR-003 | 4
HR-025 | Design calibration session facilitation guide | In Progress | High | Kavitha | Talent Acquisition | Q2 | Performance Review | 8 | 11 | 2026-03-05 | 2026-03-07 | 2026-03-04 |  | Yes |  | HR-008 | 3
HR-026 | Draft remote work policy amendment | In Progress | Medium | Rajesh | Employee Relations | Q2 | Policy Compliance | 3 | 3 | 2026-03-17 | 2026-03-22 | 2026-03-19 |  | Yes |  | HR-006 | 4
HR-027 | Redesign new hire welcome kit materials | In Progress | Low | Swathi | Learning & Development | Q2 | Onboarding Redesign | 8 | 8 | 2026-03-14 | 2026-03-20 | 2026-03-16 |  | Yes |  |  | 3
HR-028 | Set up 360-feedback survey distribution | Manager Review | Critical | Vivek | Compensation & Benefits | Q2 | Performance Review | 13 | 13 | 2026-03-17 | 2026-03-21 | 2026-03-17 |  | Yes |  |  | 4
HR-029 | Set up whistleblower case tracking system | Completed | High | Kavitha | Talent Acquisition | Q2 | Policy Compliance | 2 | 2 | 2026-03-20 | 2026-03-30 | 2026-03-19 | 2026-04-02 | Yes |  |  | 3
HR-030 | Design skill gap assessment questionnaire | Completed | Medium | Rajesh | Employee Relations | Q2 | Learning Programs | 2 | 2 | 2026-03-20 | 2026-03-29 | 2026-03-20 | 2026-03-27 | No |  | HR-003 | 4
HR-031 | Design team-building activity request workflow | In Progress | Low | Swathi | Learning & Development | Q2 | Employee Engagement | 3 | 3 | 2026-03-04 | 2026-03-09 | 2026-03-06 |  | Yes |  |  | 3
HR-032 | Map POSH committee meeting schedule | Manager Review | Critical | Vivek | Compensation & Benefits | Q2 | Policy Compliance | 13 | 13 | 2026-03-09 | 2026-03-11 | 2026-03-08 |  | Yes |  |  | 4
HR-033 | Implement diversity hiring metrics dashboard | Completed | High | Kavitha | Talent Acquisition | Q2 | Talent Pipeline | 13 | 13 | 2026-03-20 | 2026-03-30 | 2026-03-21 | 2026-03-30 | No |  |  | 3
HR-034 | Automate compliance certificate renewal alerts | To Do | Medium | Rajesh | Employee Relations | Q2 | Policy Compliance | 5 | 5 | 2026-03-09 | 2026-03-15 | 2026-03-11 |  | No |  |  | 4
HR-035 | Map promotion eligibility validation rules | On Hold | Low | Swathi | Learning & Development | Q2 | Performance Review | 5 | 5 | 2026-03-04 | 2026-03-06 | 2026-03-06 |  | Yes | Waiting for legal review of policy draft |  | 3
HR-036 | Design recognition program nomination form | To Do | Critical | Vivek | Compensation & Benefits | Q2 | Employee Engagement | 13 | 13 | 2026-03-05 | 2026-03-08 | 2026-03-05 |  | No |  |  | 4
HR-037 | Configure interview panel scheduling automation | In Progress | High | Kavitha | Talent Acquisition | Q2 | Talent Pipeline | 3 | 4 | 2026-03-09 | 2026-03-16 | 2026-03-10 |  | Yes |  |  | 3
HR-038 | Build PIP tracking and escalation workflow | Completed | Medium | Rajesh | Employee Relations | Q2 | Performance Review | 13 | 13 | 2026-03-11 | 2026-03-21 | 2026-03-10 | 2026-03-24 | Yes |  | HR-020 | 4
HR-039 | Set up ATS integration with career portal | Completed | Low | Swathi | Learning & Development | Q2 | Talent Pipeline | 2 | 2 | 2026-03-06 | 2026-03-12 | 2026-03-05 | 2026-03-10 | No |  | HR-010 | 3
HR-040 | Configure LMS course assignment automation | Completed | Critical | Vivek | Compensation & Benefits | Q2 | Learning Programs | 5 | 5 | 2026-03-11 | 2026-03-16 | 2026-03-12 | 2026-03-15 | No |  |  | 4
HR-041 | Set up town hall scheduling automation | In Progress | High | Kavitha | Talent Acquisition | Q3 | Employee Engagement | 13 | 13 | 2026-05-06 | 2026-05-10 | 2026-05-05 |  | Yes |  | HR-038 | 5
HR-042 | Automate review completion reminder sequence | On Hold | Medium | Rajesh | Employee Relations | Q3 | Performance Review | 13 | 13 | 2026-05-08 | 2026-05-10 | 2026-05-09 |  | Yes | Dependent module not yet deployed |  | 6
HR-043 | Build functional skills matrix per department | On Hold | Low | Swathi | Learning & Development | Q3 | Learning Programs | 2 | 3 | 2026-05-11 | 2026-05-14 | 2026-05-12 |  | Yes | Key stakeholder on extended leave | HR-027 | 5
HR-044 | Create first-week orientation schedule template | In Progress | Critical | Vivek | Compensation & Benefits | Q3 | Onboarding Redesign | 13 | 14 | 2026-05-09 | 2026-05-13 | 2026-05-11 |  | Yes |  |  | 6
HR-045 | Review overtime policy against labour regulations | On Hold | High | Kavitha | Talent Acquisition | Q3 | Policy Compliance | 5 | 7 | 2026-05-11 | 2026-05-17 | 2026-05-11 |  | Yes | Data migration from legacy system incomplete | HR-007 | 5
HR-046 | Design lateral hiring assessment framework | In Progress | Medium | Rajesh | Employee Relations | Q3 | Talent Pipeline | 8 | 10 | 2026-05-11 | 2026-05-16 | 2026-05-13 |  | Yes |  |  | 6
HR-047 | Automate offer letter generation process | Manager Review | Low | Swathi | Learning & Development | Q3 | Onboarding Redesign | 3 | 3 | 2026-05-11 | 2026-05-13 | 2026-05-11 |  | Yes |  |  | 5
HR-048 | Draft employer branding content calendar | Completed | Critical | Vivek | Compensation & Benefits | Q3 | Talent Pipeline | 5 | 5 | 2026-05-06 | 2026-05-12 | 2026-05-07 | 2026-05-15 | Yes |  |  | 6
HR-049 | Build learning hour compliance dashboard | In Progress | High | Kavitha | Talent Acquisition | Q3 | Learning Programs | 13 | 13 | 2026-05-04 | 2026-05-07 | 2026-05-05 |  | Yes |  |  | 5
HR-050 | Draft goal-setting framework for FY27 | On Hold | Medium | Rajesh | Employee Relations | Q3 | Performance Review | 5 | 5 | 2026-05-23 | 2026-05-31 | 2026-05-24 |  | Yes | Third-party vendor contract under renegotiation | HR-021 | 6
HR-051 | Configure probation review reminder triggers | Completed | Low | Swathi | Learning & Development | Q3 | Onboarding Redesign | 8 | 8 | 2026-05-23 | 2026-06-02 | 2026-05-22 | 2026-06-03 | Yes |  | HR-013 | 5
HR-052 | Set up training feedback aggregation pipeline | In Progress | Critical | Vivek | Compensation & Benefits | Q3 | Learning Programs | 5 | 5 | 2026-05-17 | 2026-05-19 | 2026-05-17 |  | Yes |  |  | 6
HR-053 | Map cross-functional induction touchpoints | In Progress | High | Kavitha | Talent Acquisition | Q3 | Onboarding Redesign | 2 | 4 | 2026-05-23 | 2026-05-30 | 2026-05-22 |  | Yes |  | HR-020 | 5
HR-054 | Create manager engagement action plan template | On Hold | Medium | Rajesh | Employee Relations | Q3 | Employee Engagement | 13 | 13 | 2026-05-17 | 2026-05-24 | 2026-05-19 |  | Yes | Cross-functional alignment meeting pending |  | 6
HR-055 | Build skip-level meeting tracking dashboard | Manager Review | Low | Swathi | Learning & Development | Q3 | Employee Engagement | 13 | 13 | 2026-05-08 | 2026-05-13 | 2026-05-10 |  | Yes |  |  | 5
HR-056 | Configure exit interview analytics pipeline | Completed | Critical | Vivek | Compensation & Benefits | Q3 | Employee Engagement | 8 | 8 | 2026-05-09 | 2026-05-15 | 2026-05-11 | 2026-05-17 | Yes |  | HR-020 | 6
HR-057 | Design high-performer retention risk scorecard | To Do | High | Kavitha | Talent Acquisition | Q3 | Performance Review | 5 | 5 | 2026-05-10 | 2026-05-18 | 2026-05-11 |  | No |  |  | 5
HR-058 | Build digital onboarding checklist in HRMS | On Hold | Medium | Rajesh | Employee Relations | Q3 | Onboarding Redesign | 8 | 11 | 2026-05-19 | 2026-05-23 | 2026-05-18 |  | Yes | IT security clearance not yet granted |  | 6
HR-059 | Draft onboarding feedback survey questions | Manager Review | Low | Swathi | Learning & Development | Q3 | Onboarding Redesign | 13 | 13 | 2026-05-14 | 2026-05-17 | 2026-05-14 |  | Yes |  |  | 5
HR-060 | Configure mid-year review cycle in HRMS | In Progress | Critical | Vivek | Compensation & Benefits | Q3 | Performance Review | 3 | 4 | 2026-05-04 | 2026-05-06 | 2026-05-04 |  | Yes |  | HR-040 | 6

## Team Targets
Team | Quarter | Planned Capacity (Points) | On-Time Target (%) | Max Holds Allowed
Talent Acquisition | Q1 | 30 | 85 | 3
Talent Acquisition | Q2 | 24 | 80 | 3
Talent Acquisition | Q3 | 25 | 80 | 3
Employee Relations | Q1 | 27 | 90 | 3
Employee Relations | Q2 | 21 | 90 | 1
Employee Relations | Q3 | 22 | 85 | 2
Learning & Development | Q1 | 25 | 80 | 2
Learning & Development | Q2 | 20 | 80 | 3
Learning & Development | Q3 | 24 | 85 | 2
Compensation & Benefits | Q1 | 28 | 85 | 2
Compensation & Benefits | Q2 | 22 | 80 | 3
Compensation & Benefits | Q3 | 26 | 85 | 2

## HR Initiatives
Quarter | Initiative Type | Date | Key Decisions / Notes
Q1 | Quarterly Planning | 2026-01-05 | 20 actions committed, 2 carried over from previous cycle
Q1 | Weekly Sync Summary (Week 1) | 2026-01-12 | Talent Acquisition flagged HRMS integration delay — escalated to IT head
Q1 | Mid-Quarter Review | 2026-01-26 | 3 actions re-estimated upward, L&D flagged LMS environment instability
Q1 | Quarterly Review | 2026-02-27 | 16 of 20 actions completed, 1 on hold, 3 carried to Q2
Q1 | Retrospective | 2026-02-27 | Action: improve dependency tracking, add blocker column to weekly sync
Q2 | Quarterly Planning | 2026-03-02 | 20 actions committed including 3 carried from Q1, stretch goal on engagement survey
Q2 | Weekly Sync Summary (Week 1) | 2026-03-09 | Employee Relations blocked on legal review for policy update — escalated to GC office
Q2 | Mid-Quarter Review | 2026-03-23 | 5 actions re-prioritised, compensation team flagged budget freeze impact
Q2 | Quarterly Review | 2026-04-24 | 6 of 20 actions completed, 3 on hold, velocity drop flagged to CHRO
Q3 | Quarterly Planning | 2026-05-04 | 20 actions committed, CHRO mandated focus on critical compliance items
Q3 | Weekly Sync Summary (Week 1) | 2026-05-11 | Multiple vendor delays across TA and C&B — risk of Q3 targets being missed
Q3 | Mid-Quarter Review | 2026-05-25 | 8 actions still in progress, 6 on hold — emergency resource reallocation approved
Q3 | Quarterly Review | 2026-06-26 | 3 of 20 actions completed, 6 on hold, lowest completion in 4 quarters
Q3 | Retrospective | 2026-06-26 | Root cause: vendor dependency and budget freeze; action: pre-approve Q4 vendor contracts