## Delivery Backlog
Ticket ID | Summary | Status | Priority | Assignee | Project Stream | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
HC-201 | Migrate patient demographics from legacy Meditech | Blocked | High | Kavitha R. | EMR Migration | Sprint 22 | Go-Live Prep | 13 | 13 | 2026-03-02 | 2026-03-05 |  |  | No | Integration partner certificate expired — renewal in progress |  | 1
HC-202 | Build denial root-cause classification model | Done | High | Arun M. | RCM Optimization | Sprint 22 | Claims Automation | 13 | 13 | 2026-03-03 | 2026-03-07 | 2026-03-03 | 2026-03-06 | No |  |  | 1
HC-203 | Develop duplicate order detection logic | In Progress | Critical | Sneha I. | Clinical Decision Support | Sprint 22 | Alert Framework | 3 | 3 | 2026-03-04 | 2026-03-09 | 2026-03-04 |  | No |  |  | 1
HC-204 | Develop insurance card upload and OCR module | Done | Critical | Deepak N. | Patient Portal | Sprint 22 | API Layer | 13 | 13 | 2026-03-05 | 2026-03-07 | 2026-03-05 | 2026-03-05 | No |  |  | 1
HC-205 | Run parallel-run reconciliation for pharmacy orders | Done | Medium | Preethi D. | EMR Migration | Sprint 22 | Go-Live Prep | 5 | 5 | 2026-03-06 | 2026-03-08 | 2026-03-05 | 2026-03-11 | Yes |  |  | 2
HC-206 | Build KPI dashboard for clean claim rate | Done | Critical | Rajesh K. | RCM Optimization | Sprint 22 | Denial Management | 5 | 5 | 2026-03-07 | 2026-03-09 | 2026-03-07 | 2026-03-09 | No |  |  | 2
HC-207 | Test alert fatigue reduction threshold tuning | In Progress | High | Meera K. | Clinical Decision Support | Sprint 22 | Alert Framework | 8 | 8 | 2026-03-08 | 2026-03-12 | 2026-03-08 |  | Yes |  | HC-206 | 2
HC-208 | Build prescription refill request workflow | Supervisor Review | Critical | Vikram S. | Patient Portal | Sprint 22 | Security & Compliance | 5 | 5 | 2026-03-09 | 2026-03-12 | 2026-03-09 |  | No |  |  | 2
HC-209 | Test single sign-on integration with provider directory | Done | High | Kavitha R. | EMR Migration | Sprint 22 | Go-Live Prep | 8 | 8 | 2026-03-10 | 2026-03-12 | 2026-03-09 | 2026-03-10 | No |  | HC-207 | 3
HC-210 | Test claim scrubbing rules for Medicare Advantage | Done | Critical | Arun M. | RCM Optimization | Sprint 22 | Denial Management | 5 | 5 | 2026-03-11 | 2026-03-15 | 2026-03-10 | 2026-03-18 | Yes |  |  | 3
HC-211 | Build clinical quality measure CQM-eligible extraction | Supervisor Review | Low | Sneha I. | Clinical Decision Support | Sprint 22 | Clinical Validation | 5 | 5 | 2026-03-12 | 2026-03-16 | 2026-03-12 |  | No |  |  | 3
HC-212 | Develop patient cost estimator for common procedures | Done | Low | Deepak N. | Patient Portal | Sprint 22 | API Layer | 13 | 13 | 2026-03-13 | 2026-03-17 | 2026-03-12 | 2026-03-16 | No |  |  | 3
HC-213 | Configure order entry templates for clinical staff | Done | Critical | Preethi D. | EMR Migration | Sprint 22 | Data Migration | 3 | 3 | 2026-03-14 | 2026-03-17 | 2026-03-15 | 2026-03-16 | No |  | HC-207 | 4
HC-214 | Validate CARC/RARC code mapping accuracy | Done | Critical | Rajesh K. | RCM Optimization | Sprint 22 | Payer Integration | 13 | 13 | 2026-03-15 | 2026-03-20 | 2026-03-16 | 2026-03-21 | Yes |  |  | 4
HC-215 | Configure critical lab value auto-notification | Done | Critical | Meera K. | Clinical Decision Support | Sprint 22 | Clinical Validation | 3 | 3 | 2026-03-16 | 2026-03-20 | 2026-03-17 | 2026-03-20 | No |  |  | 4
HC-216 | Design patient appointment self-scheduling UI | In Progress | High | Vikram S. | Patient Portal | Sprint 22 | API Layer | 13 | 13 | 2026-03-17 | 2026-03-19 | 2026-03-19 |  | Yes |  |  | 4
HC-217 | Build HL7 ADT feed for real-time admission sync | Done | High | Kavitha R. | EMR Migration | Sprint 22 | Go-Live Prep | 3 | 3 | 2026-03-18 | 2026-03-22 | 2026-03-19 | 2026-03-24 | Yes |  |  | 5
HC-218 | Configure auto-appeal workflow for CO-16 denials | Done | Medium | Arun M. | RCM Optimization | Sprint 22 | Claims Automation | 5 | 5 | 2026-03-19 | 2026-03-21 | 2026-03-20 | 2026-03-21 | No |  |  | 5
HC-219 | Set up clinical pathway adherence scorecard | Done | Medium | Sneha I. | Clinical Decision Support | Sprint 22 | Rules Engine | 8 | 8 | 2026-03-20 | 2026-03-23 | 2026-03-19 | 2026-03-22 | No |  | HC-203 | 5
HC-220 | Build patient education content delivery engine | Done | Low | Deepak N. | Patient Portal | Sprint 22 | Portal UI | 3 | 3 | 2026-03-21 | 2026-03-24 | 2026-03-20 | 2026-03-27 | Yes |  |  | 5
HC-221 | Migrate patient demographics from legacy Meditech | Done | Medium | Kavitha R. | EMR Migration | Sprint 23 | Data Migration | 3 | 3 | 2026-03-16 | 2026-03-19 | 2026-03-17 | 2026-03-18 | No |  |  | 3
HC-222 | Build denial root-cause classification model | Done | Critical | Arun M. | RCM Optimization | Sprint 23 | Payer Integration | 5 | 5 | 2026-03-17 | 2026-03-19 | 2026-03-16 | 2026-03-19 | No |  |  | 3
HC-223 | Develop duplicate order detection logic | Done | Medium | Sneha I. | Clinical Decision Support | Sprint 23 | Rules Engine | 13 | 13 | 2026-03-18 | 2026-03-21 | 2026-03-19 | 2026-03-20 | No |  | HC-219 | 3
HC-224 | Develop insurance card upload and OCR module | Done | Low | Deepak N. | Patient Portal | Sprint 23 | Security & Compliance | 5 | 5 | 2026-03-19 | 2026-03-24 | 2026-03-19 | 2026-03-23 | No |  |  | 3
HC-225 | Run parallel-run reconciliation for pharmacy orders | Supervisor Review | Low | Preethi D. | EMR Migration | Sprint 23 | Go-Live Prep | 8 | 8 | 2026-03-20 | 2026-03-25 | 2026-03-21 |  | No |  | HC-222 | 4
HC-226 | Build KPI dashboard for clean claim rate | In Progress | Critical | Rajesh K. | RCM Optimization | Sprint 23 | Payer Integration | 3 | 3 | 2026-03-21 | 2026-03-26 | 2026-03-23 |  | No |  | HC-208 | 4
HC-227 | Test alert fatigue reduction threshold tuning | In Progress | High | Meera K. | Clinical Decision Support | Sprint 23 | Rules Engine | 13 | 13 | 2026-03-22 | 2026-03-25 | 2026-03-23 |  | No |  |  | 4
HC-228 | Build prescription refill request workflow | Blocked | Low | Vikram S. | Patient Portal | Sprint 23 | Portal UI | 3 | 3 | 2026-03-23 | 2026-03-25 |  |  | No | Scope change request under client CTO review | HC-203 | 4
HC-229 | Test single sign-on integration with provider directory | Done | High | Kavitha R. | EMR Migration | Sprint 23 | Data Migration | 13 | 13 | 2026-03-24 | 2026-03-29 | 2026-03-24 | 2026-03-28 | No |  | HC-229 | 5
HC-230 | Test claim scrubbing rules for Medicare Advantage | Done | High | Arun M. | RCM Optimization | Sprint 23 | Claims Automation | 13 | 13 | 2026-03-25 | 2026-03-27 | 2026-03-25 | 2026-03-27 | No |  | HC-226 | 5
HC-231 | Build clinical quality measure CQM-eligible extraction | Supervisor Review | Medium | Sneha I. | Clinical Decision Support | Sprint 23 | Alert Framework | 13 | 13 | 2026-03-26 | 2026-03-31 | 2026-03-26 |  | No |  |  | 5
HC-232 | Develop patient cost estimator for common procedures | In Progress | Critical | Deepak N. | Patient Portal | Sprint 23 | Portal UI | 8 | 8 | 2026-03-27 | 2026-03-29 | 2026-03-27 |  | Yes |  |  | 5
HC-233 | Configure order entry templates for clinical staff | In Progress | High | Preethi D. | EMR Migration | Sprint 23 | Go-Live Prep | 3 | 3 | 2026-03-28 | 2026-03-30 | 2026-03-28 |  | No |  |  | 6
HC-234 | Validate CARC/RARC code mapping accuracy | Blocked | Low | Rajesh K. | RCM Optimization | Sprint 23 | Claims Automation | 3 | 3 | 2026-03-29 | 2026-04-01 |  |  | No | Awaiting client VPN access for test environment |  | 6
HC-235 | Configure critical lab value auto-notification | Done | Medium | Meera K. | Clinical Decision Support | Sprint 23 | Alert Framework | 8 | 8 | 2026-03-30 | 2026-04-02 | 2026-03-31 | 2026-04-05 | Yes |  |  | 6
HC-236 | Design patient appointment self-scheduling UI | Supervisor Review | Low | Vikram S. | Patient Portal | Sprint 23 | API Layer | 5 | 5 | 2026-03-31 | 2026-04-04 | 2026-04-01 |  | No |  | HC-205 | 6
HC-237 | Build HL7 ADT feed for real-time admission sync | To Do | Low | Kavitha R. | EMR Migration | Sprint 23 | Data Migration | 3 | 3 | 2026-04-01 | 2026-04-03 |  |  | No |  |  | 6
HC-238 | Configure auto-appeal workflow for CO-16 denials | In Progress | Medium | Arun M. | RCM Optimization | Sprint 23 | Payer Integration | 5 | 5 | 2026-04-02 | 2026-04-06 | 2026-04-02 |  | Yes |  |  | 6
HC-239 | Set up clinical pathway adherence scorecard | Done | Low | Sneha I. | Clinical Decision Support | Sprint 23 | Rules Engine | 8 | 8 | 2026-04-03 | 2026-04-05 | 2026-04-04 | 2026-04-07 | Yes |  |  | 6
HC-240 | Build patient education content delivery engine | Blocked | Critical | Deepak N. | Patient Portal | Sprint 23 | Security & Compliance | 5 | 5 | 2026-04-04 | 2026-04-08 |  |  | No | Third-party vendor API documentation not received | HC-236 | 6
HC-241 | Migrate patient demographics from legacy Meditech | Done | High | Kavitha R. | EMR Migration | Sprint 24 | Interface Build | 8 | 11 | 2026-03-30 | 2026-04-04 | 2026-03-31 | 2026-04-02 | No |  |  | 5
HC-242 | Build denial root-cause classification model | To Do | High | Arun M. | RCM Optimization | Sprint 24 | Payer Integration | 3 | 3 | 2026-03-31 | 2026-04-03 |  |  | No |  |  | 5
HC-243 | Develop duplicate order detection logic | Blocked | Medium | Sneha I. | Clinical Decision Support | Sprint 24 | Rules Engine | 8 | 8 | 2026-04-01 | 2026-04-03 |  |  | No | Network firewall rule change request stuck in approval |  | 5
HC-244 | Develop insurance card upload and OCR module | Done | Critical | Deepak N. | Patient Portal | Sprint 24 | Portal UI | 8 | 8 | 2026-04-02 | 2026-04-07 | 2026-04-03 | 2026-04-10 | Yes |  |  | 5
HC-245 | Run parallel-run reconciliation for pharmacy orders | To Do | High | Preethi D. | EMR Migration | Sprint 24 | Data Migration | 5 | 5 | 2026-04-03 | 2026-04-05 |  |  | No |  |  | 6
HC-246 | Build KPI dashboard for clean claim rate | In Progress | Low | Rajesh K. | RCM Optimization | Sprint 24 | Denial Management | 5 | 10 | 2026-04-04 | 2026-04-06 | 2026-04-05 |  | Yes |  | HC-215 | 6
HC-247 | Test alert fatigue reduction threshold tuning | Blocked | Low | Meera K. | Clinical Decision Support | Sprint 24 | Rules Engine | 8 | 8 | 2026-04-05 | 2026-04-08 |  |  | No | Dependency on upstream data feed from legacy system |  | 6
HC-248 | Build prescription refill request workflow | Done | Low | Vikram S. | Patient Portal | Sprint 24 | Portal UI | 8 | 10 | 2026-04-06 | 2026-04-10 | 2026-04-06 | 2026-04-13 | Yes |  |  | 6
HC-249 | Test single sign-on integration with provider directory | To Do | Medium | Kavitha R. | EMR Migration | Sprint 24 | Go-Live Prep | 3 | 6 | 2026-04-07 | 2026-04-10 |  |  | No |  |  | 6
HC-250 | Test claim scrubbing rules for Medicare Advantage | Supervisor Review | Critical | Arun M. | RCM Optimization | Sprint 24 | Denial Management | 3 | 3 | 2026-04-08 | 2026-04-12 | 2026-04-10 |  | Yes |  |  | 6
HC-251 | Build clinical quality measure CQM-eligible extraction | Blocked | Critical | Sneha I. | Clinical Decision Support | Sprint 24 | Clinical Validation | 13 | 13 | 2026-04-09 | 2026-04-12 |  |  | No | Client resource unavailable for UAT sign-off |  | 6
HC-252 | Develop patient cost estimator for common procedures | Blocked | Critical | Deepak N. | Patient Portal | Sprint 24 | API Layer | 5 | 5 | 2026-04-10 | 2026-04-12 |  |  | No | Network firewall rule change request stuck in approval |  | 6
HC-253 | Configure order entry templates for clinical staff | To Do | Critical | Preethi D. | EMR Migration | Sprint 24 | Go-Live Prep | 8 | 8 | 2026-04-11 | 2026-04-16 |  |  | No |  |  | 6
HC-254 | Validate CARC/RARC code mapping accuracy | Blocked | Medium | Rajesh K. | RCM Optimization | Sprint 24 | Payer Integration | 5 | 10 | 2026-04-12 | 2026-04-17 |  |  | No | Regulatory review pending from client compliance team |  | 6
HC-255 | Configure critical lab value auto-notification | In Progress | Low | Meera K. | Clinical Decision Support | Sprint 24 | Alert Framework | 3 | 3 | 2026-04-13 | 2026-04-16 | 2026-04-14 |  | Yes |  |  | 6
HC-256 | Design patient appointment self-scheduling UI | To Do | Low | Vikram S. | Patient Portal | Sprint 24 | API Layer | 13 | 13 | 2026-04-14 | 2026-04-17 |  |  | No |  |  | 6
HC-257 | Build HL7 ADT feed for real-time admission sync | In Progress | High | Kavitha R. | EMR Migration | Sprint 24 | Go-Live Prep | 3 | 8 | 2026-04-15 | 2026-04-19 | 2026-04-15 |  | Yes |  | HC-244 | 6
HC-258 | Configure auto-appeal workflow for CO-16 denials | To Do | High | Arun M. | RCM Optimization | Sprint 24 | Denial Management | 5 | 7 | 2026-04-16 | 2026-04-19 |  |  | No |  | HC-240 | 6
HC-259 | Set up clinical pathway adherence scorecard | Supervisor Review | Low | Sneha I. | Clinical Decision Support | Sprint 24 | Rules Engine | 13 | 13 | 2026-04-17 | 2026-04-20 | 2026-04-19 |  | Yes |  |  | 6
HC-260 | Build patient education content delivery engine | In Progress | High | Deepak N. | Patient Portal | Sprint 24 | Portal UI | 3 | 3 | 2026-04-18 | 2026-04-20 | 2026-04-19 |  | No |  | HC-245 | 6

## Stream Targets
Project Stream | Sprint | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
EMR Migration | Sprint 22 | 40 | 80 | 2
EMR Migration | Sprint 23 | 25 | 85 | 2
EMR Migration | Sprint 24 | 40 | 90 | 3
RCM Optimization | Sprint 22 | 40 | 90 | 3
RCM Optimization | Sprint 23 | 40 | 80 | 3
RCM Optimization | Sprint 24 | 40 | 85 | 2
Clinical Decision Support | Sprint 22 | 35 | 90 | 3
Clinical Decision Support | Sprint 23 | 30 | 85 | 3
Clinical Decision Support | Sprint 24 | 25 | 90 | 3
Patient Portal | Sprint 22 | 30 | 85 | 3
Patient Portal | Sprint 23 | 35 | 90 | 2
Patient Portal | Sprint 24 | 30 | 80 | 2

## Sprint Ceremonies
Sprint | Ceremony | Date | Key Decisions / Notes
Sprint 22 | Sprint Planning | 2026-03-02 | 20 tickets committed across 4 streams; EMR Migration prioritised for client demo on Mar 13
Sprint 22 | Daily Standup Summary (Week 1) | 2026-03-06 | HL7 interface blocker escalated to TCS integration CoE; Claims automation on track
Sprint 22 | Mid-Sprint Review | 2026-03-09 | 14 of 20 tickets in progress or done; no scope changes; client satisfied with velocity
Sprint 22 | Sprint Review | 2026-03-13 | 18 tickets completed; EMR data migration demo well-received; 2 carried to Sprint 23
Sprint 22 | Retrospective | 2026-03-13 | Action: improve handoff documentation between streams; celebrate clean claim rate milestone
Sprint 23 | Sprint Planning | 2026-03-16 | 20 tickets planned; 3 carry-overs from Sprint 22; RCM denial management epic escalated to High
Sprint 23 | Daily Standup Summary (Week 3) | 2026-03-20 | Two blockers on payer integration — vendor API rate limits hitting batch jobs; Patient Portal MFA delayed
Sprint 23 | Mid-Sprint Review | 2026-03-23 | 11 of 20 in progress or done; 3 blocked; client flagged concern on CDS alert fatigue tuning timeline
Sprint 23 | Sprint Review | 2026-03-27 | 13 completed; client requested additional scope for care gap notifications in Sprint 24
Sprint 23 | Retrospective | 2026-03-27 | Action: add vendor API health check to daily standup; blocker resolution SLA to be tracked
Sprint 24 | Sprint Planning | 2026-03-30 | 20 tickets planned including 4 carry-overs; scope expansion on Patient Portal adds 15 points; team capacity concern raised
Sprint 24 | Daily Standup Summary (Week 5) | 2026-04-03 | 5 tickets blocked — VPN access, vendor cert, PHI de-id queue, client UAT resource, firewall rule; escalation to delivery head
Sprint 24 | Mid-Sprint Review | 2026-04-06 | Only 5 of 20 tickets in progress or done; 5 blocked; emergency scope review meeting scheduled with client
Sprint 24 | Sprint Review | 2026-04-10 | 8 completed; client escalated blockers to their CTO; Sprint 25 re-planning triggered