## Engineering Backlog
Ticket ID | Summary | Status | Priority | Assignee | Cell | Sprint | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
PLT-301 | Calibrate 5-axis CNC spindle alignment tolerances | Done | Critical | Ravi | Machining Cell | Sprint 12 | Tool Life Optimization | 3 | 3 | 2026-03-02 | 2026-03-04 | 2026-03-01 | 2026-03-05 | Yes |  |  | 1
PLT-302 | Qualify new filler wire for stainless MIG process | Done | High | Suman | Welding Cell | Sprint 12 | Weld Quality Improvement | 13 | 13 | 2026-03-03 | 2026-03-06 | 2026-03-02 | 2026-03-08 | Yes |  |  | 1
PLT-303 | Balance takt time across 12 workstations | In Progress | Medium | Nisha | Assembly Line | Sprint 12 | Line Balancing | 13 | 13 | 2026-03-04 | 2026-03-08 | 2026-03-04 |  | No |  |  | 1
PLT-304 | Validate powder coat thickness on sample panels | Supervisor Review | Low | Deepak | Finishing & Packaging | Sprint 12 | Surface Treatment Upgrade | 5 | 6 | 2026-03-05 | 2026-03-09 | 2026-03-04 |  | Yes |  |  | 1
PLT-305 | Programme adaptive feed rate for titanium roughing | Blocked | Critical | Ananya | Machining Cell | Sprint 12 | Fixture Design | 3 | 3 | 2026-03-06 | 2026-03-07 | 2026-03-06 |  | No | Waiting for spare part delivery from Germany | PLT-303 | 2
PLT-306 | Tune robot weld parameters for 3mm lap joint | Blocked | High | Vikash | Welding Cell | Sprint 12 | Robot Integration | 8 | 8 | 2026-03-07 | 2026-03-08 | 2026-03-07 |  | No | Blocked by electrical lockout-tagout compliance review |  | 2
PLT-307 | Install torque verification sensors on Station 5 | In Progress | Medium | Megha | Assembly Line | Sprint 12 | Safety Compliance | 13 | 13 | 2026-03-08 | 2026-03-12 | 2026-03-09 |  | Yes |  |  | 2
PLT-308 | Programme robot for automated masking tape removal | In Progress | Low | Tarun | Finishing & Packaging | Sprint 12 | Energy Efficiency | 2 | 2 | 2026-03-09 | 2026-03-11 | 2026-03-08 |  | No |  |  | 2
PLT-309 | Replace worn ball screw on VMC-3 Z-axis | Done | Critical | Ravi | Machining Cell | Sprint 12 | Tool Life Optimization | 1 | 3 | 2026-03-10 | 2026-03-14 | 2026-03-09 | 2026-03-15 | Yes |  |  | 3
PLT-310 | Build weld sequence program for sub-assembly frame | Supervisor Review | High | Suman | Welding Cell | Sprint 12 | Weld Quality Improvement | 13 | 15 | 2026-03-11 | 2026-03-12 | 2026-03-11 |  | Yes |  |  | 3
PLT-311 | Design error-proofing poka-yoke for wiring harness | Done | Medium | Nisha | Assembly Line | Sprint 12 | Line Balancing | 3 | 5 | 2026-03-12 | 2026-03-14 | 2026-03-11 | 2026-03-13 | No |  |  | 3
PLT-312 | Set up colour spectrophotometer for batch approval | Done | Low | Deepak | Finishing & Packaging | Sprint 12 | Surface Treatment Upgrade | 5 | 5 | 2026-03-13 | 2026-03-17 | 2026-03-12 | 2026-03-17 | No |  |  | 3
PLT-313 | Set up tool presetter interface with DNC server | Supervisor Review | Critical | Ananya | Machining Cell | Sprint 12 | Fixture Design | 13 | 13 | 2026-03-02 | 2026-03-03 | 2026-03-01 |  | Yes |  |  | 4
PLT-314 | Install fume extraction upgrade on Cell W-04 | Done | High | Vikash | Welding Cell | Sprint 12 | Robot Integration | 13 | 13 | 2026-03-03 | 2026-03-05 | 2026-03-04 | 2026-03-06 | Yes |  |  | 4
PLT-315 | Build Andon board display for real-time status | Done | Medium | Megha | Assembly Line | Sprint 12 | Safety Compliance | 1 | 2 | 2026-03-04 | 2026-03-07 | 2026-03-03 | 2026-03-06 | No |  |  | 4
PLT-316 | Build packaging BOM for new export variant | Done | Low | Tarun | Finishing & Packaging | Sprint 12 | Energy Efficiency | 5 | 6 | 2026-03-05 | 2026-03-08 | 2026-03-05 | 2026-03-07 | No |  |  | 4
PLT-317 | Implement chip conveyor auto-flush cycle | Done | Critical | Ravi | Machining Cell | Sprint 12 | Tool Life Optimization | 3 | 5 | 2026-03-06 | 2026-03-08 | 2026-03-07 | 2026-03-06 | No |  |  | 5
PLT-318 | Calibrate seam-tracking laser sensor on robot arm | Done | High | Suman | Welding Cell | Sprint 12 | Weld Quality Improvement | 8 | 8 | 2026-03-07 | 2026-03-08 | 2026-03-07 | 2026-03-07 | No |  |  | 5
PLT-319 | Implement barcode scan verification at kitting area | To Do | Medium | Nisha | Assembly Line | Sprint 12 | Line Balancing | 5 | 5 | 2026-03-08 | 2026-03-12 |  |  | No |  |  | 5
PLT-320 | Implement dunnage design for fragile components | In Progress | Low | Deepak | Finishing & Packaging | Sprint 12 | Surface Treatment Upgrade | 5 | 5 | 2026-03-09 | 2026-03-12 | 2026-03-10 |  | No |  |  | 5
PLT-321 | Calibrate 5-axis CNC spindle alignment tolerances | In Progress | Critical | Ravi | Machining Cell | Sprint 13 | Tool Life Optimization | 5 | 5 | 2026-03-16 | 2026-03-17 | 2026-03-16 |  | Yes |  |  | 3
PLT-322 | Qualify new filler wire for stainless MIG process | Done | High | Suman | Welding Cell | Sprint 13 | Weld Quality Improvement | 5 | 5 | 2026-03-17 | 2026-03-20 | 2026-03-16 | 2026-03-22 | Yes |  |  | 3
PLT-323 | Balance takt time across 12 workstations | In Progress | Medium | Nisha | Assembly Line | Sprint 13 | Line Balancing | 3 | 3 | 2026-03-18 | 2026-03-21 | 2026-03-18 |  | No |  |  | 3
PLT-324 | Validate powder coat thickness on sample panels | Blocked | Low | Deepak | Finishing & Packaging | Sprint 13 | Surface Treatment Upgrade | 8 | 10 | 2026-03-19 | 2026-03-23 | 2026-03-19 |  | Yes | Pending safety risk assessment sign-off |  | 3
PLT-325 | Programme adaptive feed rate for titanium roughing | To Do | Critical | Ananya | Machining Cell | Sprint 13 | Fixture Design | 13 | 13 | 2026-03-20 | 2026-03-22 |  |  | No |  |  | 4
PLT-326 | Tune robot weld parameters for 3mm lap joint | To Do | High | Vikash | Welding Cell | Sprint 13 | Robot Integration | 3 | 3 | 2026-03-21 | 2026-03-25 |  |  | No |  |  | 4
PLT-327 | Install torque verification sensors on Station 5 | Done | Medium | Megha | Assembly Line | Sprint 13 | Safety Compliance | 2 | 2 | 2026-03-22 | 2026-03-24 | 2026-03-22 | 2026-03-22 | No |  |  | 4
PLT-328 | Programme robot for automated masking tape removal | Supervisor Review | Low | Tarun | Finishing & Packaging | Sprint 13 | Energy Efficiency | 13 | 13 | 2026-03-23 | 2026-03-26 | 2026-03-22 |  | No |  |  | 4
PLT-329 | Replace worn ball screw on VMC-3 Z-axis | Supervisor Review | Critical | Ravi | Machining Cell | Sprint 13 | Tool Life Optimization | 13 | 13 | 2026-03-24 | 2026-03-27 | 2026-03-25 |  | No |  |  | 5
PLT-330 | Build weld sequence program for sub-assembly frame | Blocked | High | Suman | Welding Cell | Sprint 13 | Weld Quality Improvement | 5 | 5 | 2026-03-25 | 2026-03-27 | 2026-03-25 |  | Yes | Awaiting vendor commissioning engineer visit | PLT-327 | 5
PLT-331 | Design error-proofing poka-yoke for wiring harness | In Progress | Medium | Nisha | Assembly Line | Sprint 13 | Line Balancing | 13 | 13 | 2026-03-26 | 2026-03-27 | 2026-03-27 |  | No |  |  | 5
PLT-332 | Set up colour spectrophotometer for batch approval | Done | Low | Deepak | Finishing & Packaging | Sprint 13 | Surface Treatment Upgrade | 8 | 8 | 2026-03-27 | 2026-03-30 | 2026-03-28 | 2026-03-29 | No |  |  | 5
PLT-333 | Set up tool presetter interface with DNC server | Done | Critical | Ananya | Machining Cell | Sprint 13 | Fixture Design | 8 | 8 | 2026-03-16 | 2026-03-20 | 2026-03-15 | 2026-03-20 | No |  |  | 6
PLT-334 | Install fume extraction upgrade on Cell W-04 | Done | High | Vikash | Welding Cell | Sprint 13 | Robot Integration | 13 | 13 | 2026-03-17 | 2026-03-21 | 2026-03-17 | 2026-03-23 | Yes |  |  | 6
PLT-335 | Build Andon board display for real-time status | Blocked | Medium | Megha | Assembly Line | Sprint 13 | Safety Compliance | 8 | 8 | 2026-03-18 | 2026-03-21 | 2026-03-17 |  | No | Blocked by crane availability for heavy-lift install | PLT-334 | 6
PLT-336 | Build packaging BOM for new export variant | In Progress | Low | Tarun | Finishing & Packaging | Sprint 13 | Energy Efficiency | 3 | 4 | 2026-03-19 | 2026-03-20 | 2026-03-19 |  | Yes |  |  | 6
PLT-337 | Implement chip conveyor auto-flush cycle | In Progress | Critical | Ravi | Machining Cell | Sprint 13 | Tool Life Optimization | 3 | 3 | 2026-03-20 | 2026-03-23 | 2026-03-19 |  | No |  |  | 6
PLT-338 | Calibrate seam-tracking laser sensor on robot arm | Done | High | Suman | Welding Cell | Sprint 13 | Weld Quality Improvement | 1 | 1 | 2026-03-21 | 2026-03-25 | 2026-03-21 | 2026-03-24 | No |  |  | 6
PLT-339 | Implement barcode scan verification at kitting area | Done | Medium | Nisha | Assembly Line | Sprint 13 | Line Balancing | 3 | 3 | 2026-03-22 | 2026-03-24 | 2026-03-21 | 2026-03-25 | Yes |  |  | 6
PLT-340 | Implement dunnage design for fragile components | Done | Low | Deepak | Finishing & Packaging | Sprint 13 | Surface Treatment Upgrade | 13 | 13 | 2026-03-23 | 2026-03-27 | 2026-03-24 | 2026-03-26 | No |  |  | 6
PLT-341 | Calibrate 5-axis CNC spindle alignment tolerances | Done | Critical | Ravi | Machining Cell | Sprint 14 | Tool Life Optimization | 1 | 1 | 2026-03-30 | 2026-04-03 | 2026-03-29 | 2026-04-03 | No |  |  | 5
PLT-342 | Qualify new filler wire for stainless MIG process | In Progress | High | Suman | Welding Cell | Sprint 14 | Weld Quality Improvement | 13 | 13 | 2026-03-31 | 2026-04-03 | 2026-04-01 |  | No |  |  | 5
PLT-343 | Balance takt time across 12 workstations | Blocked | Medium | Nisha | Assembly Line | Sprint 14 | Line Balancing | 1 | 1 | 2026-04-01 | 2026-04-05 | 2026-04-01 |  | No | Dependent on compressed air line extension |  | 5
PLT-344 | Validate powder coat thickness on sample panels | Done | Low | Deepak | Finishing & Packaging | Sprint 14 | Surface Treatment Upgrade | 8 | 8 | 2026-04-02 | 2026-04-06 | 2026-04-01 | 2026-04-04 | No |  |  | 5
PLT-345 | Programme adaptive feed rate for titanium roughing | Done | Critical | Ananya | Machining Cell | Sprint 14 | Fixture Design | 3 | 3 | 2026-04-03 | 2026-04-06 | 2026-04-02 | 2026-04-07 | Yes |  |  | 6
PLT-346 | Tune robot weld parameters for 3mm lap joint | Done | High | Vikash | Welding Cell | Sprint 14 | Robot Integration | 1 | 1 | 2026-04-04 | 2026-04-08 | 2026-04-03 | 2026-04-07 | No |  |  | 6
PLT-347 | Install torque verification sensors on Station 5 | Done | Medium | Megha | Assembly Line | Sprint 14 | Safety Compliance | 1 | 1 | 2026-04-05 | 2026-04-08 | 2026-04-05 | 2026-04-08 | No |  |  | 6
PLT-348 | Programme robot for automated masking tape removal | In Progress | Low | Tarun | Finishing & Packaging | Sprint 14 | Energy Efficiency | 1 | 1 | 2026-04-06 | 2026-04-08 | 2026-04-07 |  | No |  |  | 6
PLT-349 | Replace worn ball screw on VMC-3 Z-axis | Blocked | Critical | Ravi | Machining Cell | Sprint 14 | Tool Life Optimization | 2 | 2 | 2026-04-07 | 2026-04-08 | 2026-04-08 |  | No | Waiting for calibration certificate from external lab | PLT-347 | 6
PLT-350 | Build weld sequence program for sub-assembly frame | In Progress | High | Suman | Welding Cell | Sprint 14 | Weld Quality Improvement | 2 | 2 | 2026-04-08 | 2026-04-09 | 2026-04-07 |  | Yes |  |  | 6
PLT-351 | Design error-proofing poka-yoke for wiring harness | Done | Medium | Nisha | Assembly Line | Sprint 14 | Line Balancing | 8 | 8 | 2026-04-09 | 2026-04-11 | 2026-04-09 | 2026-04-10 | No |  |  | 6
PLT-352 | Set up colour spectrophotometer for batch approval | Supervisor Review | Low | Deepak | Finishing & Packaging | Sprint 14 | Surface Treatment Upgrade | 8 | 8 | 2026-04-10 | 2026-04-12 | 2026-04-10 |  | No |  |  | 6
PLT-353 | Set up tool presetter interface with DNC server | To Do | Critical | Ananya | Machining Cell | Sprint 14 | Fixture Design | 1 | 1 | 2026-03-30 | 2026-04-03 |  |  | No |  |  | 6
PLT-354 | Install fume extraction upgrade on Cell W-04 | Blocked | High | Vikash | Welding Cell | Sprint 14 | Robot Integration | 2 | 2 | 2026-03-31 | 2026-04-01 | 2026-03-30 |  | No | Blocked by IT firewall rule change for PLC network |  | 6
PLT-355 | Build Andon board display for real-time status | In Progress | Medium | Megha | Assembly Line | Sprint 14 | Safety Compliance | 8 | 8 | 2026-04-01 | 2026-04-02 | 2026-03-31 |  | No |  |  | 6
PLT-356 | Build packaging BOM for new export variant | Blocked | Low | Tarun | Finishing & Packaging | Sprint 14 | Energy Efficiency | 5 | 5 | 2026-04-02 | 2026-04-03 | 2026-04-01 |  | Yes | Awaiting material test report from supplier | PLT-351 | 6
PLT-357 | Implement chip conveyor auto-flush cycle | Supervisor Review | Critical | Ravi | Machining Cell | Sprint 14 | Tool Life Optimization | 1 | 1 | 2026-04-03 | 2026-04-05 | 2026-04-02 |  | No |  |  | 6
PLT-358 | Calibrate seam-tracking laser sensor on robot arm | Done | High | Suman | Welding Cell | Sprint 14 | Weld Quality Improvement | 5 | 5 | 2026-04-04 | 2026-04-07 | 2026-04-05 | 2026-04-05 | No |  |  | 6
PLT-359 | Implement barcode scan verification at kitting area | In Progress | Medium | Nisha | Assembly Line | Sprint 14 | Line Balancing | 8 | 8 | 2026-04-05 | 2026-04-08 | 2026-04-04 |  | Yes |  |  | 6
PLT-360 | Implement dunnage design for fragile components | In Progress | Low | Deepak | Finishing & Packaging | Sprint 14 | Surface Treatment Upgrade | 2 | 2 | 2026-04-06 | 2026-04-09 | 2026-04-07 |  | No |  |  | 6

## Cell Targets
Cell | Sprint | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
Machining Cell | Sprint 12 | 32 | 85 | 3
Machining Cell | Sprint 13 | 26 | 80 | 3
Machining Cell | Sprint 14 | 28 | 80 | 3
Welding Cell | Sprint 12 | 28 | 90 | 3
Welding Cell | Sprint 13 | 23 | 90 | 1
Welding Cell | Sprint 14 | 30 | 90 | 2
Assembly Line | Sprint 12 | 30 | 80 | 3
Assembly Line | Sprint 13 | 27 | 80 | 2
Assembly Line | Sprint 14 | 35 | 80 | 2
Finishing & Packaging | Sprint 12 | 26 | 90 | 2
Finishing & Packaging | Sprint 13 | 24 | 85 | 1
Finishing & Packaging | Sprint 14 | 32 | 90 | 2

## Sprint Ceremonies
Sprint | Ceremony | Date | Key Decisions / Notes
Sprint 12 | Sprint Planning | 2026-03-02 | 20 tickets committed, 2 carryovers from previous maintenance window
Sprint 12 | Daily Standup Summary (Week 1) | 2026-03-06 | Machining Cell blocker on spindle bearing shipment — escalated to procurement
Sprint 12 | Mid-Sprint Review | 2026-03-09 | 3 tickets re-estimated upward, Welding Cell flagged gas supply interruption
Sprint 12 | Sprint Review | 2026-03-13 | 16 of 20 tickets done, 2 blocked, 2 carried to Sprint 13
Sprint 12 | Retrospective | 2026-03-13 | Action: add vendor lead time buffer to sprint planning, track blocker ageing daily
Sprint 13 | Sprint Planning | 2026-03-16 | 20 tickets committed including 2 carryovers, 1 urgent safety fix added
Sprint 13 | Daily Standup Summary (Week 1) | 2026-03-20 | Assembly Line ahead of schedule, Finishing Cell blocked on paint booth certification
Sprint 13 | Mid-Sprint Review | 2026-03-23 | Plant manager requested scope addition — 2 new tickets for customer audit prep
Sprint 13 | Sprint Review | 2026-03-27 | 14 of 22 tickets done, velocity dip flagged, 4 blocked tickets escalated to plant head
Sprint 13 | Retrospective | 2026-03-27 | Action: no mid-sprint additions without Tech Architect sign-off, blocker SLA of 24 hours
Sprint 14 | Sprint Planning | 2026-03-30 | 20 tickets committed, team flagged resource risk — Ananya on leave week 2
Sprint 14 | Daily Standup Summary (Week 1) | 2026-04-03 | 6 tickets blocked — highest count in 3 sprints, crane and vendor dependencies dominate
Sprint 14 | Mid-Sprint Review | 2026-04-06 | Only 2 tickets done at midpoint, Tech Architect escalated to VP Manufacturing
Sprint 14 | Sprint Review | 2026-04-10 | Sprint still in progress — formal review deferred to April 10