## Release Backlog
Ticket ID | Summary | Status | Priority | Assignee | Squad | Release | Epic | Original Points | Current Points | Planned Start | Planned End | Actual Start | Actual End | Overdue | Blocker | Dependency | Week Number
TECH-5001 | Task summary for TECH-5001 | Done | Critical | Vikram S | API Platform | Release 7.1 | Microservices Refactor | 3 | 3 | 2026-03-02 | 2026-03-05 | 2026-03-02 | 2026-03-05 | No |  |  | 1
TECH-5002 | Task summary for TECH-5002 | Done | High | Sonal K | Data Engineering | Release 7.1 | Data Pipeline Overhaul | 5 | 7 | 2026-03-03 | 2026-03-08 | 2026-03-02 | 2026-03-07 | No |  |  | 1
TECH-5003 | Task summary for TECH-5003 | Done | Medium | Amit T | Frontend Apps | Release 7.1 | UI Modernization | 3 | 3 | 2026-03-04 | 2026-03-06 | 2026-03-04 | 2026-03-06 | No |  |  | 1
TECH-5004 | Task summary for TECH-5004 | Done | Low | Swati B | QA & DevOps | Release 7.1 | CI/CD Enhancement | 13 | 13 | 2026-03-05 | 2026-03-10 | 2026-03-04 | 2026-03-09 | No |  |  | 1
TECH-5005 | Task summary for TECH-5005 | Done | Critical | Vikram S | API Platform | Release 7.1 | API Gateway Setup | 5 | 5 | 2026-03-06 | 2026-03-09 | 2026-03-05 | 2026-03-09 | No |  |  | 2
TECH-5006 | Task summary for TECH-5006 | Done | High | Sonal K | Data Engineering | Release 7.1 | ETL Automation | 5 | 8 | 2026-03-07 | 2026-03-09 | 2026-03-07 | 2026-03-11 | Yes |  |  | 2
TECH-5007 | Task summary for TECH-5007 | Done | Medium | Amit T | Frontend Apps | Release 7.1 | Microservices Refactor | 3 | 3 | 2026-03-08 | 2026-03-11 | 2026-03-07 | 2026-03-10 | No |  |  | 2
TECH-5008 | Task summary for TECH-5008 | Done | Low | Swati B | QA & DevOps | Release 7.1 | Data Pipeline Overhaul | 13 | 13 | 2026-03-09 | 2026-03-12 | 2026-03-09 | 2026-03-13 | Yes |  |  | 2
TECH-5009 | Task summary for TECH-5009 | Done | Critical | Vikram S | API Platform | Release 7.1 | UI Modernization | 8 | 8 | 2026-03-10 | 2026-03-15 | 2026-03-10 | 2026-03-14 | No |  |  | 3
TECH-5010 | Task summary for TECH-5010 | Done | High | Sonal K | Data Engineering | Release 7.1 | CI/CD Enhancement | 5 | 7 | 2026-03-11 | 2026-03-13 | 2026-03-11 | 2026-03-15 | Yes |  |  | 3
TECH-5011 | Task summary for TECH-5011 | In Progress | Medium | Amit T | Frontend Apps | Release 7.1 | API Gateway Setup | 8 | 8 | 2026-03-12 | 2026-03-15 | 2026-03-12 |  | No |  |  | 3
TECH-5012 | Task summary for TECH-5012 | In Progress | Low | Swati B | QA & DevOps | Release 7.1 | ETL Automation | 5 | 5 | 2026-03-13 | 2026-03-18 | 2026-03-13 |  | Yes |  |  | 3
TECH-5013 | Task summary for TECH-5013 | In Progress | Critical | Vikram S | API Platform | Release 7.1 | Microservices Refactor | 5 | 5 | 2026-03-14 | 2026-03-16 | 2026-03-14 |  | No |  |  | 4
TECH-5014 | Task summary for TECH-5014 | In Progress | High | Sonal K | Data Engineering | Release 7.1 | Data Pipeline Overhaul | 8 | 10 | 2026-03-15 | 2026-03-20 | 2026-03-16 |  | Yes |  |  | 4
TECH-5015 | Task summary for TECH-5015 | Code Review | Medium | Amit T | Frontend Apps | Release 7.1 | UI Modernization | 3 | 3 | 2026-03-16 | 2026-03-18 | 2026-03-17 |  | No |  |  | 4
TECH-5016 | Task summary for TECH-5016 | Code Review | Low | Swati B | QA & DevOps | Release 7.1 | CI/CD Enhancement | 3 | 3 | 2026-03-17 | 2026-03-22 | 2026-03-18 |  | No |  |  | 4
TECH-5017 | Task summary for TECH-5017 | Code Review | Critical | Vikram S | API Platform | Release 7.1 | API Gateway Setup | 13 | 13 | 2026-03-18 | 2026-03-23 | 2026-03-19 |  | No |  |  | 5
TECH-5018 | Task summary for TECH-5018 | To Do | High | Sonal K | Data Engineering | Release 7.1 | ETL Automation | 5 | 5 | 2026-03-19 | 2026-03-24 | 2026-03-20 |  | Yes |  |  | 5
TECH-5019 | Task summary for TECH-5019 | Blocked | Medium | Amit T | Frontend Apps | Release 7.1 | Microservices Refactor | 13 | 16 | 2026-03-20 | 2026-03-23 | 2026-03-20 |  | Yes | Third-party API vendor unresponsive — integration blocked | TECH-5008 | 5
TECH-5020 | Task summary for TECH-5020 | Blocked | Low | Swati B | QA & DevOps | Release 7.1 | Data Pipeline Overhaul | 5 | 5 | 2026-03-21 | 2026-03-23 | 2026-03-21 |  | Yes | Staging environment disk full — deployments halted | TECH-5002 | 5
TECH-5021 | Task summary for TECH-5021 | Done | Critical | Vikram S | API Platform | Release 7.2 | Microservices Refactor | 3 | 3 | 2026-03-16 | 2026-03-18 | 2026-03-15 | 2026-03-17 | No |  |  | 1
TECH-5022 | Task summary for TECH-5022 | Done | High | Sonal K | Data Engineering | Release 7.2 | Data Pipeline Overhaul | 13 | 13 | 2026-03-17 | 2026-03-20 | 2026-03-16 | 2026-03-19 | No |  |  | 1
TECH-5023 | Task summary for TECH-5023 | Done | Medium | Amit T | Frontend Apps | Release 7.2 | UI Modernization | 3 | 3 | 2026-03-18 | 2026-03-23 | 2026-03-17 | 2026-03-24 | Yes |  |  | 1
TECH-5024 | Task summary for TECH-5024 | Done | Low | Swati B | QA & DevOps | Release 7.2 | CI/CD Enhancement | 3 | 3 | 2026-03-19 | 2026-03-21 | 2026-03-18 | 2026-03-20 | No |  |  | 1
TECH-5025 | Task summary for TECH-5025 | Done | Critical | Vikram S | API Platform | Release 7.2 | API Gateway Setup | 8 | 10 | 2026-03-20 | 2026-03-25 | 2026-03-20 | 2026-03-26 | Yes |  |  | 2
TECH-5026 | Task summary for TECH-5026 | Done | High | Sonal K | Data Engineering | Release 7.2 | ETL Automation | 5 | 5 | 2026-03-21 | 2026-03-23 | 2026-03-21 | 2026-03-24 | Yes |  |  | 2
TECH-5027 | Task summary for TECH-5027 | Done | Medium | Amit T | Frontend Apps | Release 7.2 | Microservices Refactor | 13 | 13 | 2026-03-22 | 2026-03-25 | 2026-03-21 | 2026-03-25 | No |  |  | 2
TECH-5028 | Task summary for TECH-5028 | Done | Low | Swati B | QA & DevOps | Release 7.2 | Data Pipeline Overhaul | 3 | 3 | 2026-03-23 | 2026-03-28 | 2026-03-23 | 2026-03-27 | No |  |  | 2
TECH-5029 | Task summary for TECH-5029 | In Progress | Critical | Vikram S | API Platform | Release 7.2 | UI Modernization | 13 | 15 | 2026-03-24 | 2026-03-26 | 2026-03-25 |  | Yes |  |  | 3
TECH-5030 | Task summary for TECH-5030 | In Progress | High | Sonal K | Data Engineering | Release 7.2 | CI/CD Enhancement | 5 | 5 | 2026-03-25 | 2026-03-30 | 2026-03-26 |  | Yes |  |  | 3
TECH-5031 | Task summary for TECH-5031 | In Progress | Medium | Amit T | Frontend Apps | Release 7.2 | API Gateway Setup | 5 | 8 | 2026-03-26 | 2026-03-31 | 2026-03-27 |  | No |  |  | 3
TECH-5032 | Task summary for TECH-5032 | In Progress | Low | Swati B | QA & DevOps | Release 7.2 | ETL Automation | 13 | 13 | 2026-03-27 | 2026-03-29 | 2026-03-27 |  | No |  |  | 3
TECH-5033 | Task summary for TECH-5033 | Code Review | Critical | Vikram S | API Platform | Release 7.2 | Microservices Refactor | 5 | 5 | 2026-03-28 | 2026-03-30 | 2026-03-28 |  | Yes |  |  | 4
TECH-5034 | Task summary for TECH-5034 | Code Review | High | Sonal K | Data Engineering | Release 7.2 | Data Pipeline Overhaul | 3 | 3 | 2026-03-29 | 2026-03-31 | 2026-03-30 |  | No |  |  | 4
TECH-5035 | Task summary for TECH-5035 | Code Review | Medium | Amit T | Frontend Apps | Release 7.2 | UI Modernization | 5 | 5 | 2026-03-30 | 2026-04-02 | 2026-03-30 |  | Yes |  |  | 4
TECH-5036 | Task summary for TECH-5036 | To Do | Low | Swati B | QA & DevOps | Release 7.2 | CI/CD Enhancement | 13 | 13 | 2026-03-31 | 2026-04-03 | 2026-04-01 |  | No |  |  | 4
TECH-5037 | Task summary for TECH-5037 | To Do | Critical | Vikram S | API Platform | Release 7.2 | API Gateway Setup | 3 | 3 | 2026-04-01 | 2026-04-04 | 2026-04-02 |  | No |  |  | 5
TECH-5038 | Task summary for TECH-5038 | Blocked | High | Sonal K | Data Engineering | Release 7.2 | ETL Automation | 3 | 3 | 2026-04-02 | 2026-04-07 | 2026-04-02 |  | Yes | Third-party API vendor unresponsive — integration blocked | TECH-5007 | 5
TECH-5039 | Task summary for TECH-5039 | Blocked | Medium | Amit T | Frontend Apps | Release 7.2 | Microservices Refactor | 3 | 3 | 2026-04-03 | 2026-04-06 | 2026-04-03 |  | Yes | Staging environment disk full — deployments halted | TECH-5007 | 5
TECH-5040 | Task summary for TECH-5040 | Blocked | Low | Swati B | QA & DevOps | Release 7.2 | Data Pipeline Overhaul | 5 | 5 | 2026-04-04 | 2026-04-09 | 2026-04-04 |  | Yes | Security review pending from compliance team | TECH-5029 | 5
TECH-5041 | Task summary for TECH-5041 | Done | Critical | Vikram S | API Platform | Release 7.3 | Microservices Refactor | 5 | 5 | 2026-03-30 | 2026-04-02 | 2026-03-29 | 2026-04-02 | No |  |  | 1
TECH-5042 | Task summary for TECH-5042 | Done | High | Sonal K | Data Engineering | Release 7.3 | Data Pipeline Overhaul | 3 | 3 | 2026-03-31 | 2026-04-05 | 2026-03-31 | 2026-04-04 | No |  |  | 1
TECH-5043 | Task summary for TECH-5043 | Done | Medium | Amit T | Frontend Apps | Release 7.3 | UI Modernization | 3 | 5 | 2026-04-01 | 2026-04-03 | 2026-03-31 | 2026-04-05 | Yes |  |  | 1
TECH-5044 | Task summary for TECH-5044 | Done | Low | Swati B | QA & DevOps | Release 7.3 | CI/CD Enhancement | 13 | 13 | 2026-04-02 | 2026-04-05 | 2026-04-02 | 2026-04-05 | No |  |  | 1
TECH-5045 | Task summary for TECH-5045 | Done | Critical | Vikram S | API Platform | Release 7.3 | API Gateway Setup | 13 | 13 | 2026-04-03 | 2026-04-06 | 2026-04-02 | 2026-04-08 | Yes |  |  | 2
TECH-5046 | Task summary for TECH-5046 | In Progress | High | Sonal K | Data Engineering | Release 7.3 | ETL Automation | 8 | 8 | 2026-04-04 | 2026-04-09 | 2026-04-05 |  | No |  |  | 2
TECH-5047 | Task summary for TECH-5047 | In Progress | Medium | Amit T | Frontend Apps | Release 7.3 | Microservices Refactor | 8 | 8 | 2026-04-05 | 2026-04-07 | 2026-04-05 |  | Yes |  |  | 2
TECH-5048 | Task summary for TECH-5048 | In Progress | Low | Swati B | QA & DevOps | Release 7.3 | Data Pipeline Overhaul | 3 | 3 | 2026-04-06 | 2026-04-09 | 2026-04-06 |  | No |  |  | 2
TECH-5049 | Task summary for TECH-5049 | In Progress | Critical | Vikram S | API Platform | Release 7.3 | UI Modernization | 3 | 5 | 2026-04-07 | 2026-04-12 | 2026-04-07 |  | Yes |  |  | 3
TECH-5050 | Task summary for TECH-5050 | In Progress | High | Sonal K | Data Engineering | Release 7.3 | CI/CD Enhancement | 5 | 5 | 2026-04-08 | 2026-04-13 | 2026-04-08 |  | Yes |  |  | 3
TECH-5051 | Task summary for TECH-5051 | Code Review | Medium | Amit T | Frontend Apps | Release 7.3 | API Gateway Setup | 3 | 3 | 2026-04-09 | 2026-04-12 | 2026-04-10 |  | Yes |  |  | 3
TECH-5052 | Task summary for TECH-5052 | Code Review | Low | Swati B | QA & DevOps | Release 7.3 | ETL Automation | 5 | 5 | 2026-04-10 | 2026-04-13 | 2026-04-10 |  | No |  |  | 3
TECH-5053 | Task summary for TECH-5053 | Code Review | Critical | Vikram S | API Platform | Release 7.3 | Microservices Refactor | 5 | 5 | 2026-04-11 | 2026-04-14 | 2026-04-12 |  | No |  |  | 4
TECH-5054 | Task summary for TECH-5054 | To Do | High | Sonal K | Data Engineering | Release 7.3 | Data Pipeline Overhaul | 3 | 3 | 2026-04-12 | 2026-04-17 | 2026-04-12 |  | No |  |  | 4
TECH-5055 | Task summary for TECH-5055 | To Do | Medium | Amit T | Frontend Apps | Release 7.3 | UI Modernization | 5 | 5 | 2026-04-13 | 2026-04-15 | 2026-04-14 |  | Yes |  |  | 4
TECH-5056 | Task summary for TECH-5056 | To Do | Low | Swati B | QA & DevOps | Release 7.3 | CI/CD Enhancement | 5 | 5 | 2026-04-14 | 2026-04-16 | 2026-04-15 |  | Yes |  |  | 4
TECH-5057 | Task summary for TECH-5057 | Blocked | Critical | Vikram S | API Platform | Release 7.3 | API Gateway Setup | 8 | 8 | 2026-04-15 | 2026-04-20 | 2026-04-15 |  | Yes | Third-party API vendor unresponsive — integration blocked | TECH-5034 | 5
TECH-5058 | Task summary for TECH-5058 | Blocked | High | Sonal K | Data Engineering | Release 7.3 | ETL Automation | 3 | 3 | 2026-04-16 | 2026-04-21 | 2026-04-16 |  | Yes | Staging environment disk full — deployments halted | TECH-5020 | 5
TECH-5059 | Task summary for TECH-5059 | Blocked | Medium | Amit T | Frontend Apps | Release 7.3 | Microservices Refactor | 3 | 5 | 2026-04-17 | 2026-04-20 | 2026-04-17 |  | Yes | Security review pending from compliance team | TECH-5008 | 5
TECH-5060 | Task summary for TECH-5060 | Blocked | Low | Swati B | QA & DevOps | Release 7.3 | Data Pipeline Overhaul | 3 | 5 | 2026-04-18 | 2026-04-21 | 2026-04-18 |  | Yes | Dependency on upstream data pipeline not yet delivered | TECH-5019 | 5

## Team Targets
Squad | Release | Planned Velocity (Points) | On-Time Target (%) | Max Blockers Allowed
API Platform | Release 7.1 | 35 | 85 | 2
API Platform | Release 7.2 | 30 | 80 | 2
API Platform | Release 7.3 | 28 | 80 | 2
Data Engineering | Release 7.1 | 32 | 85 | 2
Data Engineering | Release 7.2 | 28 | 80 | 3
Data Engineering | Release 7.3 | 30 | 80 | 2
Frontend Apps | Release 7.1 | 28 | 85 | 2
Frontend Apps | Release 7.2 | 25 | 80 | 2
Frontend Apps | Release 7.3 | 26 | 80 | 3
QA & DevOps | Release 7.1 | 30 | 85 | 2
QA & DevOps | Release 7.2 | 28 | 80 | 2
QA & DevOps | Release 7.3 | 25 | 80 | 2

## Release Ceremonies
Release | Ceremony | Date | Key Decisions / Notes
Release 7.1 | Release Planning | 2026-03-02 | 20 tickets committed; API Gateway epic prioritised over ETL backlog items
Release 7.1 | Daily Standup Summary (Week 1) | 2026-03-06 | API Platform blocker on vendor API — escalated to account manager
Release 7.1 | Mid-Release Review | 2026-03-09 | 2 tickets re-estimated upward; staging environment instability flagged
Release 7.1 | Release Review | 2026-03-13 | 18 tickets closed; 2 blockers carried forward to Release 7.2
Release 7.1 | Retrospective | 2026-03-13 | Action: improve vendor SLA tracking; pre-provision staging before next release
Release 7.2 | Release Planning | 2026-03-16 | 20 tickets committed; carried 2 blockers from 7.1; Data Pipeline epic added
Release 7.2 | Daily Standup Summary (Week 1) | 2026-03-20 | Data Engineering blocked on schema migration; DBA sign-off pending
Release 7.2 | Mid-Release Review | 2026-03-23 | 3 tickets scope-increased; security review dependency identified
Release 7.2 | Release Review | 2026-03-27 | 16 tickets closed; 3 blockers unresolved; velocity below target
Release 7.3 | Release Planning | 2026-03-30 | 20 tickets committed; highest blocker carry-forward in 3 releases — risk flagged
Release 7.3 | Daily Standup Summary (Week 1) | 2026-04-03 | Cloud infra provisioning delayed; 2 tickets reassigned to unblock Frontend
Release 7.3 | Mid-Release Review | 2026-04-06 | 4 tickets blocked — escalation to delivery head; completion rate at 25%
Release 7.3 | Release Review | 2026-04-10 | 13 tickets closed; 4 blockers open; lowest completion across all 3 releases
Release 7.3 | Retrospective | 2026-04-10 | Action: pre-clear all vendor and compliance dependencies before release planning; institute blocker SLA of 48 hrs