## Budget Summary
PROJECT NOVA-FIN ¦ Budget Tracker — FY 2024-25
Client: Meridian Bank ¦ TCS Project Code: TCS-BFSI-2024-0847 ¦ PM: Renu Gupta ¦ Reporting Period: Q3 FY25 (Oct–Dec 2024)
Workstream | Planned ($K) | Actual Q1 ($K) | Actual Q2 ($K) | Actual Q3 ($K) | Total Actual ($K) | Forecast to Complete ($K) | Total at Completion ($K) | Variance ($K)
Cloud Infrastructure Setup | 2800 | 680 | 720 | 810 |  | 520
Core Banking Integration | 3200 | 720 | 810 | 890 |  | 680
Data Migration & Validation | 1800 | 380 | 420 | 510 |  | 310
Security & Compliance | 1200 | 210 | 260 | 310 |  | 180
AI/ML Model Development | 2200 | 480 | 560 | 620 |  | 340
Testing & QA | 1400 | 280 | 320 | 390 |  | 280
Change Management & Training | 800 | 120 | 160 | 210 |  | 180
Project Management | 600 | 145 | 148 | 152 |  | 155
Contingency Reserve | 700 | 0 | 0 | 0 |  | 420
TOTAL PROJECT
Notes:
1. Core Banking Integration is 8.4% over budget — scope creep due to additional regulatory API requirements added in Q2.
2. Contingency Reserve draw of $420K approved by Steering Committee on 18-Nov-2024 for security compliance gap.
3. AI/ML workstream tracking well — $340K remaining FTC vs $600K original plan; efficiency gains from reusable model components.

## Monthly Spend Trend
Monthly Spend vs Baseline Budget — Project NOVA-FIN
Month | Baseline Monthly ($K) | Actual Spend ($K) | Cumulative Actual ($K) | Cumulative Baseline ($K)
Apr 2024 | 1150 | 980 | 980 | 1150
May 2024 | 1150 | 1080 | 2060 | 2300
Jun 2024 | 1150 | 1220 | 3280 | 3450
Jul 2024 | 1150 | 1340 | 4620 | 4600
Aug 2024 | 1150 | 1180 | 5800 | 5750
Sep 2024 | 1150 | 1290 | 7090 | 6900
Oct 2024 | 1150 | 1410 | 8500 | 8050
Nov 2024 | 1150 | 1560 | 10060 | 9200
Dec 2024 | 1150 | 1490 | 11550 | 10350