PROJECT NOVA-FIN

Steering Committee Meeting Minutes

MEETING #8 — November 18, 2024 ¦ 10:00 AM – 12:00 PM IST ¦ Microsoft Teams

| Attendees | James Whitfield (Meridian CTO), Sarah Chen (Meridian CFO), Renu Gupta (TCS PM), Susnaata Naskar (TCS Delivery Partner), Shankar Raj (Risk Lead), Ramya Ramapriyan (Security Lead), Ankita Nanda (TCS Account Head) |
| --- | --- |
| Apologies | Anuja Majumdar (TCS Finance) |
| Minutes By | Renu Gupta |
| Next Meeting | December 16, 2024 ¦ 10:00 AM IST |

## Agenda Item 1: PCI-DSS Compliance Gap — Status & Mitigation

Ramya Ramapriyan presented the findings from the third-party security audit completed November 12. A misconfiguration in the Azure Blob Storage encryption policy was identified, allowing potential unencrypted data-at-rest in the staging environment. No production data was at risk.

Discussion: James Whitfield expressed concern about regulatory implications and asked for a formal root cause analysis. Ramya confirmed the issue was limited to staging and presented a 2-week remediation plan including storage policy reconfiguration, mandatory security review of all cloud components, and a penetration test scheduled for January 2025.

DECISION: Steering Committee approved 2-week remediation sprint (Nov 18 – Dec 2). PCI-DSS sign-off rescheduled to January 15, 2025. Formal RCA to be shared by Nov 25.

## Agenda Item 2: Recovery Plan — Schedule Rebaseline

Renu Gupta presented the recovery plan following accumulated delays from the API instability (M-03, 2 weeks) and the PCI-DSS remediation sprint (2 weeks). The proposed revised go-live date is May 15, 2025 — a 6-week extension from the original March 31 target.

Recovery levers presented: (1) Parallel execution of Phase 2 API integration and UAT environment setup, (2) Additional resource deployment — 2 FTE migration specialists and 1 FTE QA engineer, (3) Daily standup between TCS leads and Meridian integration team, (4) Freeze on all non-critical change requests until go-live.

Sarah Chen raised concern about the commercial implications of the delay and requested a formal impact assessment on the Meridian Q1 FY26 operating plan. Ankita Nanda agreed to provide this by November 25.

DECISION: Recovery plan accepted in principle. Formal approval of revised go-live date (May 15, 2025) deferred to next SC meeting (Dec 16) pending commercial impact assessment.

## Agenda Item 3: Change Request CR-14 — Regulatory Reporting Module

Shankar Raj presented CR-14 raised by Meridian compliance team. The Reserve Bank of India's November 2024 circular (RBI/2024-25/112) requires additional audit trail capabilities for AI-assisted credit decisions. CR-14 scope includes a new reporting module, additional audit log schema, and regulatory dashboard.

Estimated impact: +$280,000 and +6 weeks to project timeline. James Whitfield confirmed this is mandatory for regulatory compliance and cannot be deferred. However, the financial approval requires sign-off from Meridian's Group CFO.

ACTION: James Whitfield to obtain Group CFO approval for CR-14 by December 20, 2024. TCS to hold design resources in readiness. CR-14 will not be activated until written approval received.

## Action Items from This Meeting

| # | Action | Owner | Due Date |
| --- | --- | --- | --- |
| 1 | Share formal RCA for PCI-DSS gap | Ramya Ramapriyan | Nov 25, 2024 |
| 2 | Provide commercial impact assessment of delay on Meridian Q1 FY26 | Ankita Nanda | Nov 25, 2024 |
| 3 | Obtain Group CFO approval for CR-14 | James Whitfield | Dec 20, 2024 |
| 4 | Mobilize 2 additional migration FTEs | Renu Gupta | Nov 25, 2024 |
| 5 | Schedule Dec 16 SC meeting and circulate agenda | Renu Gupta | Nov 20, 2024 |
| 6 | Confirm end-user training dates with Meridian HR | Sarah Chen / Meridian HR | Dec 15, 2024 |

MEETING #9 — December 16, 2024 ¦ 10:00 AM – 11:30 AM IST ¦ Microsoft Teams

## Agenda Item 1: Recovery Plan Formal Approval

Renu Gupta presented the updated recovery plan incorporating the commercial impact assessment prepared by Ankita Nanda. The delay is estimated to have a $1.2M opportunity cost for Meridian in Q1 FY26 due to deferred digital-first product launch. Meridian leadership acknowledged this and agreed the revised timeline is the most realistic path.

DECISION: Steering Committee formally approved revised go-live date of May 15, 2025. Recovery plan accepted. Budget rebaseline of $14.98M (original: $14.7M) approved.

## Agenda Item 2: Q4 Priorities

- Complete PCI-DSS remediation and obtain compliance sign-off by January 15

- Complete Core Banking Phase 2 integration by January 31

- Begin UAT by February 3 with full Meridian UAT team mobilized

- Complete data migration full load by February 28

- Activate CR-14 (pending CFO approval) from January 2025

- Training program execution: February – March 2025