PROJECT NOVA-FIN

Q3 FY25 Project Status Report

Meridian Bank | Core Banking AI Transformation

Reporting Period: Q3 FY25 (October – December 2024) Project Manager: Renu Gupta ¦ Delivery Partner: Susnaata Naskar ¦ Client Sponsor: James Whitfield (CTO, Meridian Bank) TCS Project Code: TCS-BFSI-2024-0847 ¦ Contract Value: $14.7M ¦ Go-Live Target: March 31, 2025

# 1. Overall Project Health

| 🔴 SCHEDULE 6 weeks behind plan | 🟡 BUDGET 8% over on 2 workstreams | 🟡 SCOPE 1 CR pending approval | 🟢 QUALITY Zero critical defects in prod |
| --- | --- | --- | --- |

Overall project status is AMBER-RED. The project faces a significant schedule risk following the discovery of data migration volume underestimation and a PCI-DSS compliance gap that required an unplanned 2-week remediation sprint in November. A recovery plan has been presented to the Steering Committee and is awaiting formal approval.

# 2. Milestone Status

| ID | Milestone | Baseline Date | Forecast Date | Status |
| --- | --- | --- | --- | --- |
| M-01 | Project Kickoff & Governance Setup | Apr 15, 2024 | Apr 15, 2024 | 🟢 Complete |
| M-02 | Cloud Infrastructure Provisioned | Jun 30, 2024 | Jun 28, 2024 | 🟢 Complete |
| M-03 | Core Banking API Integration (Phase 1) | Aug 31, 2024 | Sep 14, 2024 | 🟡 Complete (Delayed) |
| M-04 | AI/ML Model v1.0 — Dev Complete | Oct 15, 2024 | Oct 22, 2024 | 🟢 Complete |
| M-05 | Data Migration Dry Run #1 | Nov 15, 2024 | Nov 15, 2024 | 🟢 Complete |
| M-06 | PCI-DSS Compliance Sign-off | Nov 30, 2024 | Jan 15, 2025 | 🔴 Delayed |
| M-07 | Core Banking Integration (Phase 2) | Dec 15, 2024 | Jan 31, 2025 | 🔴 Delayed |
| M-08 | UAT Start | Jan 6, 2025 | Feb 3, 2025 | 🔴 At Risk |
| M-09 | Data Migration — Full Load Complete | Jan 31, 2025 | Feb 28, 2025 | 🔴 At Risk |
| M-10 | Go-Live — Production Launch | Mar 31, 2025 | May 15, 2025 | 🔴 At Risk |

# 3. Workstream Progress

| Workstream | % Complete | RAG | Key Achievement Q3 | Next Steps |
| --- | --- | --- | --- | --- |
| Cloud Infrastructure | 95% | 🟢 GREEN | Multi-region failover configured; 99.97% uptime achieved | Final DR test in Jan 2025 |
| Core Banking Integration | 62% | 🔴 RED | Phase 1 complete; Phase 2 APIs unstable | Stability sprint + Phase 2 completion by Jan 31 |
| Data Migration | 58% | 🔴 RED | Dry run 1 complete; 18% data quality issues found | Cleansing sprint; Dry Run 2 in Jan 2025 |
| Security & Compliance | 71% | 🔴 RED | Gap identified in cloud storage PCI config | Remediation sprint; pen test Jan 2025 |
| AI/ML Model Development | 88% | 🟢 GREEN | Model v1.0 deployed to staging; 94.2% accuracy | Performance tuning; bias testing complete |
| Testing & QA | 44% | 🟡 AMBER | Test automation at 74%; UAT environment issues | Fix UAT env; resume SIT by Dec 20 |
| Change Mgmt & Training | 52% | 🟡 AMBER | Training content 100% ready; schedule not confirmed | Confirm client training dates by Dec 31 |
| Project Management | Ongoing | 🟡 AMBER | Recovery plan drafted and presented | SC approval by Dec 20, 2024 |

# 4. Key Decisions Required

The following decisions are required from the Steering Committee and/or Client by December 20, 2024:

| # | Decision Required | Decision Owner | Deadline |
| --- | --- | --- | --- |
| 1 | Approve revised go-live date of May 15, 2025 and recovery plan | James Whitfield (Meridian CTO) | Dec 20, 2024 |
| 2 | Approve Change Request CR-14 for regulatory reporting module (+$280K, +6 weeks) | Meridian PMO + TCS Account Head | Dec 20, 2024 |
| 3 | Confirm end-user training schedule for 200 Meridian staff | Meridian HR / Change Lead | Dec 31, 2024 |
| 4 | Approve budget rebaseline including contingency draw of $420K | TCS Delivery Partner + Finance | Dec 18, 2024 |