## Risk Register
PROJECT NOVA-FIN ¦ Risk Register — Updated: December 2024
Client: Meridian Bank ¦ Owner: Shankar Raj (Risk Lead) ¦ Next Review: 15-Jan-2025
Risk ID | Category | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Rating | Owner | Mitigation Action | Status | Last Updated
R-001 | Technical | Core banking API instability causing integration failures | 4 | 5 |  | HIGH | Shankar Raj | Dedicated API sandbox environment; weekly stability reviews with Meridian infra team; rollback plan documented | Open | Dec 2024
R-002 | Schedule | Data migration volume 40% higher than initial estimates — risk of Q4 go-live delay | 4 | 4 |  | HIGH | Renu Gupta | Additional migration resources (2 FTEs) onboarded; parallel run strategy approved; go-live date under review with client | Open | Dec 2024
R-003 | Budget | Contingency reserve at 60% utilization by Q3 — risk of budget overrun | 3 | 4 |  | MEDIUM | Renu Gupta | Change request raised for additional $300K; scope freeze enforced from Nov 2024; weekly budget review cadence | Escalated | Nov 2024
R-004 | Security | PCI-DSS compliance gap identified in cloud storage configuration | 3 | 5 |  | HIGH | Ramya Ramapriyan | Immediate remediation sprint (2 weeks); third-party pen test scheduled for Jan 2025; compliance sign-off required before UAT | Open | Dec 2024
R-005 | Resource | Key SME (Core Banking Lead) at risk of rolling off to another engagement in Feb 2025 | 3 | 4 |  | MEDIUM | Renu Gupta | Knowledge transfer plan initiated; backup SME identified internally; contract extension request submitted to BU head | Open | Nov 2024
R-006 | Vendor | Azure service degradation impacting CI/CD pipeline — 2 incidents in Q3 | 2 | 3 |  | MEDIUM | Prasanna Rajasekar | Multi-region failover configured; SLA review with Microsoft CSM; monitoring dashboard enhanced | Mitigated | Oct 2024
R-007 | Scope | Client requesting additional regulatory reporting module not in original SOW | 4 | 3 |  | MEDIUM | Renu Gupta | Formal change request CR-14 raised; impact assessment: +$280K and 6-week timeline extension; pending client approval | Open | Dec 2024
R-008 | Data | Data quality issues in Meridian legacy system — 18% records with missing/invalid fields | 3 | 3 |  | MEDIUM | Aditi Shahiry | Data cleansing sprint underway; data quality dashboard created; client data steward assigned for remediation | Open | Nov 2024
R-009 | Compliance | RBI regulatory update (Nov 2024) requiring additional audit trail capability | 2 | 4 |  | MEDIUM | Sarathraj Selvaraj | Legal & compliance team review completed; design changes scoped (3 weeks effort); no schedule impact expected | Monitoring | Dec 2024
R-010 | People | Team burnout risk — 3 team members flagging workload concerns in Q3 pulse survey | 2 | 3 |  | LOW | Renu Gupta | Workload rebalancing done; one additional resource approved; mandatory EL tracker review weekly | Mitigated | Dec 2024

## Issue Log
PROJECT NOVA-FIN ¦ Active Issue Log — Q3 FY25
Issue ID | Raised By | Description | Priority | Assigned To | Target Resolution | Status | Days Open
I-001 | Meridian QA Team | UAT environment not matching production config — 14 test cases failing | Critical | Prasanna Rajasekar | 20-Dec-2024 | Open | 28
I-002 | Renu Gupta | Steering Committee decision on go-live date still pending — blocking sprint planning | High | Renu Gupta | 15-Dec-2024 | Overdue | 42
I-003 | Shankar Raj | Missing API documentation for 3 Meridian legacy endpoints | High | Shankar Raj | 22-Dec-2024 | In Progress | 15
I-004 | Aditi Shahiry | Data pipeline failing for date fields with pre-2000 records — affects 12K records | Medium | Aditi Shahiry | 27-Dec-2024 | In Progress | 8
I-005 | Ramya Ramapriyan | SSL certificate renewal overdue on staging server | Medium | Prasanna Rajasekar | 18-Dec-2024 | Resolved | 21
I-006 | Change Mgmt Lead | Training schedule not confirmed by client HR — 200 users pending | Medium | Renu Gupta | 31-Dec-2024 | Open | 12