PROJECT NOVA-FIN — EXECUTIVE STAKEHOLDER UPDATE

Meridian Bank Core Banking AI Transformation | December 2024

Prepared for: Meridian Bank Executive Leadership & TCS Account Leadership

| 67% Overall Completion (target was 81% by Q3) | $11.2M Spent to Date vs $14.7M contract value | +6 Wks Schedule Delay New go-live: May 15, 2025 | 94.2% AI Model Accuracy exceeds 92% target |
| --- | --- | --- | --- |

# What Has Been Achieved

- Cloud infrastructure fully provisioned across 3 Azure regions with 99.97% uptime in Q3

- AI/ML credit risk models (v1.0) deployed to staging — 94.2% accuracy, exceeding the 92% target

- Core Banking Phase 1 API integration complete — 47 of 63 planned APIs connected

- Data migration dry run #1 complete — 8.2M records validated successfully

- Security remediation sprint completed on schedule — PCI-DSS sign-off on track for Jan 15

- Recovery plan approved by Steering Committee on December 16, 2024

# Top 3 Concerns

|  | Concern | Why It Matters | What TCS Is Doing |
| --- | --- | --- | --- |
| 🔴 | Go-Live Delay (6 weeks) | Meridian's digital-first product launch depends on this system. Each week of delay = ~$200K opportunity cost. | Recovery plan with parallel workstreams; daily PM-to-PM sync; 2 additional FTEs deployed |
| 🟡 | CR-14 Approval Pending | RBI regulatory requirement — cannot go live without this module. Client CFO approval still outstanding. | Design ready to activate immediately upon approval. TCS holding resources in readiness. |
| 🟡 | Data Quality in Legacy System | 18% of Meridian legacy records have data issues — risk to migration completeness and go-live quality. | Dedicated data cleansing sprint; client data steward engaged; second dry run planned for Jan 2025 |

# Decisions Needed From Leadership

- James Whitfield / Meridian CFO: Approve CR-14 (+$280K regulatory module) by December 20

- Meridian HR: Confirm end-user training schedule for 200 staff by December 31

- TCS Delivery Partner: Sign off budget rebaseline of $14.98M by December 18

# What to Expect Next Quarter (Q4 FY25)

| Month | Key Deliverable | Owner | Success Metric |
| --- | --- | --- | --- |
| January 2025 | PCI-DSS compliance sign-off + Phase 2 API integration complete | Ramya / Shankar | Signed compliance certificate; all 63 APIs live |
| February 2025 | UAT commenced with 50 Meridian business users; Data migration full load | Meridian UAT Lead + TCS | Zero P1 defects after 2 weeks UAT |
| March 2025 | Training for 200 end users complete; Performance testing passed | Change Mgmt Lead | 95% training completion; <3s response time |
| April 2025 | Go-live dress rehearsal; Cutover planning finalized | Renu Gupta | Dry run completed; cutover plan signed off |
| May 15, 2025 | GO-LIVE — Production Launch | All Leads | System live; zero critical incidents in first 48 hrs |

TCS is committed to delivering Project NOVA-FIN to the highest quality standard. PM: Renu Gupta — renu.gupta@tcs.com ¦ Account Head: Ankita Nanda — ankita.nanda@tcs.com