MERIDIAN FINANCIAL GROUP

Wealth Management & Financial Services

REQUEST FOR PROPOSAL

Data Centre Modernisation & Cloud Migration Programme

RFP Reference: RFP-MFG-2025-001

Issue Date: April 1, 2025

Submission Deadline: April 30, 2025 at 17:00 CST

Issued By: Meridian Financial Group – Office of the CTO

Contact: rfp-cloud@meridianfg.com

This document is confidential and intended solely for the named recipient. Unauthorised disclosure, reproduction, or distribution is strictly prohibited.

# 1. Executive Summary

Meridian Financial Group (MFG) is a leading mid-market financial services and wealth management firm headquartered in Chicago, Illinois, with regional offices in New York, Dallas, and Toronto. With over 2,400 employees and USD 48 billion in assets under management, MFG serves a diverse client base of high-net-worth individuals, institutional investors, and corporate clients across North America.

MFG is undertaking a strategic initiative to modernise its on-premises data centre estate and migrate workloads to a secure, scalable public cloud environment. This Request for Proposal (RFP) invites qualified IT services organisations to submit detailed proposals outlining their capabilities, methodology, and commercial terms to become MFG's preferred Cloud Migration Partner.

The selected partner will be responsible for delivering a structured, risk-managed migration programme spanning discovery and assessment through to post-migration operations. MFG expects a partner who brings deep cloud architecture expertise, strong financial services sector experience, and a proven delivery methodology.

This RFP is not a commitment to award a contract. MFG reserves the right to accept or reject any proposal, in whole or in part, at its sole discretion.

# 2. Company Background

Founded in 1987, Meridian Financial Group has grown from a regional brokerage into a full-service wealth management and financial services conglomerate. MFG's core business lines include:

- Wealth Management & Private Banking

- Institutional Asset Management

- Corporate Treasury & Trade Finance

- Insurance & Annuities

- Digital Banking (launched 2021)

## 2.1 Technology Landscape

MFG currently operates two primary data centres — one in Chicago (primary) and one in Columbus, Ohio (DR site) — housing over 1,200 physical and virtual servers. The IT estate supports approximately 180 enterprise applications, ranging from core banking platforms to customer-facing digital portals and regulatory reporting systems.

Key technology facts:

| Attribute | Details |
| --- | --- |
| Primary DC Location | Chicago, IL (owned facility) |
| DR DC Location | Columbus, OH (co-location) |
| Total Servers | 1,240 (620 physical, 620 virtual) |
| Total Applications | ~180 across all business lines |
| Current Virtualisation | VMware vSphere 6.7 |
| Storage Capacity | ~2.8 PB usable (SAN + NAS) |
| Primary Network Fabric | Cisco Nexus |
| Employees (IT) | ~320 globally |

# 3. Business Drivers & Objectives

MFG's decision to modernise and migrate is driven by a convergence of strategic, operational, and regulatory pressures:

## 3.1 Cost Pressures

- Both Chicago and Columbus data centres are approaching end-of-life for major hardware refresh cycles, with estimated CapEx of USD 28M required over the next three years if on-premises operations continue.

- Energy and facility costs have risen 34% over the past four years.

- Current infrastructure is significantly over-provisioned for average load, resulting in low utilisation rates (avg. 22% CPU, 31% storage).

## 3.2 Agility & Scalability

- MFG's Digital Banking division requires elastic compute capacity to support rapid product launches and variable transaction volumes.

- Time-to-provision new environments is currently 14–21 days, constraining the pace of digital initiatives.

## 3.3 Regulatory & Compliance

- Evolving SEC, FINRA, and OCC guidance on data residency, encryption, and audit traceability requires a more robust and auditable infrastructure posture.

- MFG's internal risk function has flagged single-site DR dependency as a Critical risk in the last two ITGC audits.

## 3.4 Strategic Objectives

- Decommission the Chicago primary data centre by Q4 2027.

- Migrate 100% of Tier 2 and Tier 3 workloads to public cloud within 18 months.

- Retain a hybrid posture for regulated Tier 1 core banking workloads pending regulatory clarity.

- Achieve 30% reduction in total infrastructure run cost within 24 months of migration completion.

- Establish a Cloud Centre of Excellence (CCoE) within MFG by end of Year 1.

# 4. Current State Overview

## 4.1 Application Portfolio

MFG has conducted a preliminary application inventory. The 180 applications are classified into four tiers:

| Tier | Description |
| --- | --- |
| Tier 1 – Mission Critical | Core banking, trading platforms, settlement systems (32 apps). Zero-downtime requirement. Regulatory constraints apply. |
| Tier 2 – Business Critical | CRM, risk analytics, reporting, compliance monitoring (54 apps). RTO < 4 hours. |
| Tier 3 – Standard | HR systems, collaboration tools, internal portals, dev/test environments (68 apps). RTO < 24 hours. |
| Tier 4 – Candidates for Retirement | Legacy systems, duplicate tools, end-of-life applications (26 apps). To be decommissioned during migration. |

## 4.2 Key Pain Points

- Hardware refresh backlog causing stability incidents — 18 P2 outages in the past 12 months attributed to ageing infrastructure.

- Siloed monitoring tooling with no single pane of glass across network, compute, and storage.

- Manual change management processes with average change lead time of 9 days.

- Limited DR capability — last full DR failover test took 72 hours and was only partially successful.

- Skills gap in cloud-native technologies within the current IT operations team.

# 5. Scope of Work

The scope is structured into five workstreams. Vendors are required to respond to all capability questions within each workstream. Responses should be specific, evidence-based, and reference comparable engagements where possible.

## 5.1  Discovery & Assessment

MFG requires a comprehensive discovery of the current IT estate to establish a reliable, data-driven migration baseline. This includes automated tooling-based discovery, dependency mapping, application rationalisation, and TCO modelling.

- Deploy discovery agents across all physical and virtual servers in both DC sites.

- Produce a complete application dependency map (ADM) covering all 180 applications.

- Classify each application using a 6-R framework (Rehost, Replatform, Refactor, Repurchase, Retire, Retain).

- Develop a cloud TCO model comparing current run costs to projected cloud spend across a 3-year horizon.

- Deliver a Migration Readiness Assessment (MRA) report with prioritised recommendations.

VENDOR RESPONSE REQUIRED

Q1. Describe the discovery tooling you use (e.g. AWS Migration Evaluator, CloudAmize, Movere). How do you ensure 100% inventory coverage in complex on-premises environments with restricted network zones? Response:

Q2. Walk us through your methodology for building an application dependency map. How do you handle undocumented dependencies and legacy applications with no owners? Response:

Q3. How do you apply the 6-R framework in a financial services context where regulatory constraints may override the technically optimal migration strategy? Response:

Q4. Provide an example TCO model structure you have delivered for a comparable financial services migration. What inputs do you require from the client, and what assumptions do you make? Response:

Q5. What is your typical timeline and resource model to complete a Discovery & Assessment for an estate of MFG's size (~180 apps, ~1,240 servers)? Response:

## 5.2  Migration Planning & Wave Design

Based on discovery outputs, the selected partner will develop a detailed migration plan and wave strategy that sequences workloads for migration in a risk-managed, business-aligned manner.

- Define migration waves aligned to business priority, technical dependency, and risk appetite.

- Develop a Migration Runbook template and cutover plan for each wave.

- Establish a Migration Factory operating model — tooling, roles, RACI, and governance cadence.

- Define rollback procedures for each migration wave and application tier.

- Produce a detailed project plan with milestones, critical path, and resource allocation.

VENDOR RESPONSE REQUIRED

Q1. Describe your wave planning methodology. How do you determine the sequencing of workloads across waves, particularly when Tier 1 and Tier 2 applications share infrastructure dependencies? Response:

Q2. What does your Migration Factory model look like? How do you scale the factory to handle high-velocity migration waves while maintaining quality and rollback safety? Response:

Q3. How do you manage business stakeholder alignment during wave planning — specifically, how do you handle business units that resist migration of their applications? Response:

Q4. Describe your rollback strategy for a failed Tier 2 migration where the application has been partially migrated and the source environment has been decommissioned. Response:

Q5. What project governance and reporting cadence do you recommend for a programme of this complexity, and what tooling do you use to track migration progress? Response:

## 5.3  Cloud Architecture Design

The vendor will design a secure, resilient, and cost-optimised target cloud architecture for MFG's workloads, aligned to financial services best practices and regulatory requirements.

- Design a Landing Zone architecture on the preferred cloud platform (AWS preferred; Azure will be considered).

- Define network topology: hub-and-spoke VPC/VNet design, transit connectivity, and on-premises integration via Direct Connect / ExpressRoute.

- Establish security architecture: IAM frameworks, encryption standards (data at rest and in transit), SIEM integration, and WAF/DDoS controls.

- Design a multi-region Active-Active or Active-Passive DR architecture with defined RTO/RPO targets per tier.

- Define FinOps governance model: tagging taxonomy, cost allocation, reserved instance strategy, and anomaly alerting.

VENDOR RESPONSE REQUIRED

Q1. Describe your Landing Zone design approach. Do you use AWS Control Tower, a custom IaC-based approach, or another framework? How do you customise it for financial services compliance requirements? Response:

Q2. How do you design for network segmentation in a regulated financial services environment where different application tiers have different data sensitivity levels and network access requirements? Response:

Q3. MFG is subject to PCI-DSS, SOC 2 Type II, and SEC Rule 17a-4 (WORM storage). Describe how your architecture design addresses each of these requirements natively. Response:

Q4. What is your recommended DR architecture for a firm of MFG's profile? How do you validate RTO/RPO targets prior to migration, and how frequently do you recommend DR testing post-migration? Response:

Q5. Describe your FinOps practice. How do you help clients achieve and sustain cloud cost optimisation beyond the initial migration, including governance mechanisms to prevent cost sprawl? Response:

## 5.4  Migration Execution

The vendor will lead and deliver the phased migration of all in-scope workloads across agreed waves, using automated tooling and a structured change management process.

- Execute server and workload migrations using industry-standard tooling (e.g. AWS MGN, Azure Migrate, Carbonite).

- Manage all pre-migration validation, cut-over execution, and post-migration smoke testing.

- Coordinate with MFG's application owners, infrastructure team, and business stakeholders throughout each wave.

- Deliver a Migration Status Dashboard providing real-time visibility into wave progress, risk items, and go/no-go status.

- Conduct post-migration performance benchmarking to validate that workloads meet SLA requirements in the cloud environment.

VENDOR RESPONSE REQUIRED

Q1. Which migration execution tools do you use for lift-and-shift migrations, and how do you handle edge cases such as bare-metal servers, proprietary OS images, and applications with hardware licensing dependencies? Response:

Q2. Describe your cut-over process for a Tier 2 application migration. What pre-cut-over checks do you perform, what is your go/no-go criteria, and who has final sign-off authority? Response:

Q3. How do you manage parallel running (source and target) during cut-over, and how long do you recommend maintaining the source environment post-migration before decommissioning? Response:

Q4. What does your Migration Status Dashboard look like? Can you provide a sample or screenshot from a previous engagement, and how is it customised for executive vs. technical audiences? Response:

Q5. Describe your approach to post-migration performance optimisation — specifically, how do you right-size instances after initial lift-and-shift to avoid cloud cost overruns? Response:

## 5.5  Post-Migration Support & Cloud Operations

Following migration completion, the vendor will provide a structured hypercare period and support MFG in transitioning to a sustainable cloud operating model.

- Provide a 90-day hypercare support period post each wave migration, including 24x7 on-call support for Tier 1 and Tier 2 workloads.

- Deliver cloud operations runbooks, operational dashboards, and alerting frameworks for handover to MFG's internal team.

- Conduct a Cloud Centre of Excellence (CCoE) enablement programme for MFG's IT team, covering governance, FinOps, security operations, and DevOps practices.

- Provide ongoing Managed Cloud Services (optional, to be priced separately) covering monitoring, patching, and cost optimisation.

- Deliver a final Post-Migration Report summarising outcomes, lessons learned, and recommendations for cloud maturity advancement.

VENDOR RESPONSE REQUIRED

Q1. Describe your hypercare model. What SLAs do you commit to during hypercare, and how is the hypercare team structured relative to the migration delivery team? Response:

Q2. How do you approach the knowledge transfer from your team to MFG's internal IT operations team? What documentation standards do you follow, and how do you validate readiness before handover? Response:

Q3. Describe the structure and content of a CCoE enablement programme you have delivered for a financial services client. How long did it take, and what measurable outcomes were achieved? Response:

Q4. If MFG chooses to engage you for ongoing Managed Cloud Services post-migration, what is your operating model, escalation path, and how do you handle major incident management in a 24x7 financial services context? Response:

Q5. How do you measure and report on cloud maturity progression over time? What benchmarks or frameworks do you use, and how frequently do you conduct reviews? Response:

# 6. Technical Requirements

All proposals must address the following mandatory technical requirements. Non-compliance with any Mandatory requirement will result in the proposal being disqualified.

| Requirement | Specification |
| --- | --- |
| Cloud Platform | AWS (preferred); Azure will be considered. Multi-cloud proposals are welcome but must include a primary platform recommendation. |
| Security Standards | SOC 2 Type II certified delivery organisation. All cloud environments must meet CIS Benchmark Level 2. |
| Compliance | Architectures must natively support PCI-DSS v4.0, SEC Rule 17a-4 (WORM), and FINRA data retention rules. |
| Data Residency | All production data must remain within US regions. No data to transit through non-US infrastructure. |
| Encryption | AES-256 at rest; TLS 1.2 minimum in transit. KMS-managed keys with customer-managed key option for Tier 1 workloads. |
| Network Connectivity | Dedicated Direct Connect (AWS) or ExpressRoute (Azure) circuits — minimum 10 Gbps. |
| DR / RTO / RPO | Tier 1: RTO 15 min / RPO 5 min. Tier 2: RTO 4 hrs / RPO 1 hr. Tier 3: RTO 24 hrs / RPO 4 hrs. |
| IaC | All infrastructure provisioned via code (Terraform or AWS CloudFormation). Manual console provisioning prohibited in production. |
| ITSM Integration | Cloud operations must integrate with MFG's existing ServiceNow instance (Tokyo release). |

# 7. Proposal Requirements

Vendors must submit proposals that include all of the following sections. Proposals that do not address all sections in full may be disqualified.

- Executive Summary — A concise summary (max 3 pages) of the vendor's proposed approach, key differentiators, and commercial headline.

- Vendor Credentials — Company overview, cloud partner tier status, financial services client references (minimum 3), and relevant certifications (AWS MSP, Azure Expert MSP, ISO 27001, SOC 2).

- Proposed Methodology — Detailed response to all Scope of Work sections (Section 5), including responses to all Vendor Response questions.

- Target Architecture — High-level target state architecture diagrams for Landing Zone, network topology, security, and DR design.

- Project Plan — Indicative programme timeline with phases, milestones, key dependencies, and resource allocation (named key roles required).

- Team Composition — CVs or profiles of the proposed Programme Manager, Cloud Architect, Security Architect, and Migration Lead. Indicative team size per phase.

- Tooling & Accelerators — List of proprietary tooling, automation accelerators, and pre-built assets that will be used in this engagement.

- Risk Register — Initial risk assessment for the MFG migration programme, with likelihood, impact, and proposed mitigations.

- Commercial Proposal — Fully itemised pricing (see Section 9). Fixed-price proposals are preferred.

- References — Contact details for at least three client references in the financial services sector for comparable migration engagements.

# 8. Evaluation Criteria

MFG will evaluate proposals against the following weighted criteria. All evaluations will be conducted by MFG's Technical Evaluation Panel and results will be moderated by the Procurement Committee.

| Evaluation Criteria | Weightage | Max Score |
| --- | --- | --- |
| Technical Capability & Cloud Architecture Depth | 25% | 25 |
| Migration Methodology & Tooling Maturity | 20% | 20 |
| Financial Services Sector Experience & References | 20% | 20 |
| Security, Compliance & Risk Management Approach | 15% | 15 |
| Commercial Competitiveness & Value for Money | 10% | 10 |
| Team Credentials & Proposed Staffing Model | 5% | 5 |
| Innovation, Accelerators & Proprietary Assets | 5% | 5 |
| TOTAL | 100% | 100 |

Shortlisted vendors will be invited to present their proposals in person (or via video conference) before final scoring is completed. MFG reserves the right to conduct reference checks and technical due diligence interviews with proposed key personnel.

# 9. Commercials & Pricing

Vendors must provide a fully itemised commercial proposal. MFG's preferred commercial model is fixed-price per phase. Time-and-materials proposals will be considered only where scope cannot be fixed, and must include not-to-exceed caps.

## 9.1 Required Pricing Breakdown

- Workstream pricing aligned to the five Scope of Work areas (Section 5).

- Phased payment milestones aligned to programme phases and deliverable acceptance.

- Separate pricing for optional Managed Cloud Services post-migration.

- Any licence costs for proprietary tooling used during the engagement.

- Assumed cloud infrastructure costs (pass-through) with clear methodology for estimation.

## 9.2 Commercial Terms

- All prices in USD. Proposals in other currencies will not be accepted.

- Pricing must be valid for a minimum of 90 days from the submission deadline.

- Vendors must disclose any cloud provider referral fees, resale margins, or incentive arrangements that may influence their platform recommendation.

- MFG will not accept proposals that embed undisclosed risk contingency in excess of 10% of total programme value.

# 10. Timelines & Milestones

| Milestone | Date |
| --- | --- |
| RFP Issued | April 1, 2025 |
| Vendor Registration Deadline | April 8, 2025 |
| Clarification Questions Deadline | April 14, 2025 |
| MFG Responses to Clarifications | April 18, 2025 |
| Proposal Submission Deadline | April 30, 2025 – 17:00 CST |
| Shortlisting Notification | May 9, 2025 |
| Vendor Presentations (Shortlisted) | May 19–23, 2025 |
| Final Evaluation & Scoring Complete | May 30, 2025 |
| Contract Award Notification | June 6, 2025 |
| Contract Execution | June 20, 2025 |
| Programme Kick-Off | July 1, 2025 |
| Target: Discovery & Assessment Complete | September 30, 2025 |
| Target: Wave 1 Migration Complete | January 31, 2026 |
| Target: Full Migration Complete | December 31, 2026 |
| Target: Chicago DC Decommission | Q4 2027 |

MFG reserves the right to modify these timelines at its sole discretion. Vendors will be notified of any changes in writing.

# 11. Terms & Conditions

## 11.1 Confidentiality

All information contained in this RFP is proprietary and confidential to Meridian Financial Group. By responding to this RFP, vendors agree to treat all information as strictly confidential and not to disclose it to any third party without prior written consent from MFG.

## 11.2 No Obligation to Award

Issuance of this RFP does not obligate MFG to award a contract. MFG reserves the right to cancel this RFP process at any time, accept or reject any proposal in whole or in part, and negotiate with more than one vendor simultaneously.

## 11.3 Vendor Qualifications

Vendors must meet the following minimum qualifications to be eligible:

- Minimum 5 years of cloud migration delivery experience.

- Demonstrated delivery of at least three cloud migration programmes in the financial services sector, each exceeding USD 5M in programme value.

- AWS Premier Tier Partner or Azure Expert MSP certification (current, not expired).

- ISO 27001 and SOC 2 Type II certified organisation.

- Minimum 200 cloud-certified engineers globally.

## 11.4 Intellectual Property

Any deliverables produced specifically for MFG under the resulting contract will be considered work-for-hire and will be owned by MFG. Vendors retain ownership of their pre-existing tools, frameworks, accelerators, and methodologies.

## 11.5 Submission Instructions

Proposals must be submitted electronically to rfp-cloud@meridianfg.com by the deadline. The subject line must read: RFP-MFG-2025-001 | [Vendor Name]. Late submissions will not be accepted. Proposals must be submitted in PDF format with a maximum size of 50MB. Supporting appendices may be provided as separate attachments.

# 12. Appendices

## Appendix A – Application Inventory Summary

A detailed application inventory will be shared under NDA with registered vendors following the vendor registration deadline (April 8, 2025). The inventory includes application name, business owner, tier classification, technology stack, estimated server count, and current licensing information.

## Appendix B – Application Classification Template

Vendors are requested to use the following template when presenting their 6-R classification recommendations in their proposals:

| Field | Description |
| --- | --- |
| Application Name | Name of the application as per MFG inventory |
| Current Tier | Tier 1 / 2 / 3 / 4 |
| Proposed 6-R Strategy | Rehost / Replatform / Refactor / Repurchase / Retire / Retain |
| Rationale | Brief justification for the proposed strategy |
| Target Cloud Service | e.g. EC2, RDS, EKS, Lambda, SaaS replacement |
| Estimated Effort (Days) | Indicative migration effort in person-days |
| Key Risks | Top 1–2 risks for this application migration |
| Recommended Wave | Wave number in which this application should be migrated |

## Appendix C – Vendor Response Template

Vendors are encouraged (but not required) to use the response template structure outlined below when organising their proposal. Responses to all Vendor Response Required questions (Section 5) must be clearly labelled with the corresponding question number.

## Appendix D – Glossary

| Term | Definition |
| --- | --- |
| 6-R Framework | Migration strategy framework: Rehost, Replatform, Refactor, Repurchase, Retire, Retain |
| ADM | Application Dependency Map — a visual/data representation of inter-application dependencies |
| CCoE | Cloud Centre of Excellence — an internal governance and enablement function for cloud operations |
| DR | Disaster Recovery — the ability to recover systems and data following a disruptive event |
| FinOps | Financial Operations — the practice of managing and optimising cloud spend |
| IaC | Infrastructure as Code — provisioning and managing infrastructure through machine-readable scripts |
| Landing Zone | A secure, scalable, multi-account cloud environment baseline configuration |
| MRA | Migration Readiness Assessment — a structured evaluation of readiness to migrate to cloud |
| RPO | Recovery Point Objective — the maximum acceptable data loss measured in time |
| RTO | Recovery Time Objective — the maximum acceptable time to restore a system after disruption |
| TCO | Total Cost of Ownership — the full cost analysis of running infrastructure over a defined period |
| WORM | Write Once Read Many — a data storage model required for certain regulatory record retention |

## Appendix E – Compliance Requirements Traceability Matrix

Vendors must complete the following Compliance Requirements Traceability Matrix as part of their proposal submission. For each requirement listed, indicate your compliance status, provide a brief description of how the requirement will be met, and reference the relevant section of your proposal where the detailed response can be found. Requirements marked as Mandatory (M) must be fully met; failure to comply will result in disqualification. Requirements marked as Desirable (D) will be scored favourably if addressed.

Compliance Status Definitions:

C = Comply – Requirement is fully met as stated.

PC = Partially Comply – Requirement is partially met; vendor must explain gaps and proposed mitigations.

NC = Non-Comply – Requirement cannot be met; vendor must provide rationale and alternative approach.

N/A = Not Applicable – Vendor believes the requirement does not apply; justification required.

Section A: Mandatory Technical Requirements (Ref: Section 6)

| Req ID | Requirement Description | Type | Status | Vendor Response / Approach | Proposal Section Ref |
| --- | --- | --- | --- | --- | --- |
| TR-01 | Cloud Platform: AWS preferred; Azure will be considered. Multi-cloud proposals must include primary platform recommendation. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| TR-02 | Security Standards: SOC 2 Type II certified delivery organisation. All cloud environments must meet CIS Benchmark Level 2. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| TR-03 | Compliance: Architectures must natively support PCI-DSS v4.0, SEC Rule 17a-4 (WORM), and FINRA data retention rules. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| TR-04 | Data Residency: All production data must remain within US regions. No data to transit through non-US infrastructure. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| TR-05 | Encryption: AES-256 at rest; TLS 1.2 minimum in transit. KMS-managed keys with customer-managed key option for Tier 1 workloads. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| TR-06 | Network Connectivity: Dedicated Direct Connect (AWS) or ExpressRoute (Azure) circuits – minimum 10 Gbps. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| TR-07 | DR / RTO / RPO: Tier 1: RTO 15 min / RPO 5 min. Tier 2: RTO 4 hrs / RPO 1 hr. Tier 3: RTO 24 hrs / RPO 4 hrs. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| TR-08 | Infrastructure as Code: All infrastructure provisioned via Terraform or AWS CloudFormation. Manual console provisioning prohibited in production. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| TR-09 | ITSM Integration: Cloud operations must integrate with MFG’s existing ServiceNow instance (Tokyo release). | M | C/PC/NC | [Vendor to complete] | [Section #] |

Section B: Vendor Qualification Requirements (Ref: Section 11.3)

| Req ID | Requirement Description | Type | Status | Vendor Response / Evidence | Proposal Section Ref |
| --- | --- | --- | --- | --- | --- |
| VQ-01 | Minimum 5 years of cloud migration delivery experience. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| VQ-02 | At least three cloud migration programmes in financial services sector, each exceeding USD 5M in programme value. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| VQ-03 | AWS Premier Tier Partner or Azure Expert MSP certification (current, not expired). | M | C/PC/NC | [Vendor to complete] | [Section #] |
| VQ-04 | ISO 27001 and SOC 2 Type II certified organisation. | M | C/PC/NC | [Vendor to complete] | [Section #] |
| VQ-05 | Minimum 200 cloud-certified engineers globally. | M | C/PC/NC | [Vendor to complete] | [Section #] |

— End of Document — RFP-MFG-2025-001 — Meridian Financial Group — Confidential —